## Master Plan
|  | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Week Start (Mon) | time axis 2019-04-09 to 2020-07-28
|  | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Week End (Fri) | time axis 2019-04-06 to 2020-08-01
[52 empty] | 2018 Q2 | [12 empty] | 20 18 Q3 | [12 empty] | 2018 Q4 | [13 empty] | 2019 Q1 | [11 empty] | 2019 Q2
[52 empty] | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Philippines
| UAT | [49 empty] | Philippines
| Migration | [49 empty] | Philippines
| Go Live | [49 empty] | Philippines | 2019-04-20: Philippines; 2019-06-29: Soft Go Live of the Drop 2 code for Philipinnes
| Floor Walking | [49 empty] | Philippines | bar: 2019-04-13 to 2019-04-20
| Post Go Live support | [49 empty] | Philippines | bar: 2019-04-13 to 2019-05-18
| Drop 2 | [49 empty] | Singapore
| UAT - Migration | [49 empty] | Singapore | bar: 2019-04-06 to 2019-05-18; 2019-06-01 to 2019-06-08; 2019-06-22 to 2019-06-29
| UAT - Everything else | [49 empty] | Singapore | bar: 2019-04-06 to 2019-05-04; 2019-05-18 to 2019-05-25; 2019-06-08 to 2019-06-15; 2019-06-29
| Migration | [49 empty] | Singapore | bar: 2019-08-03 to 2019-08-17
| Training | [49 empty] | Singapore | [70 empty] | NOTE Singapore go live moves to End of Aug. But UAT still signs off End of June | bar: 2019-08-03 to 2019-08-24
| Go Live | [49 empty] | Singapore | 2019-08-31: Singapore | We would still be able to do a sft go live of the Drop 2 code as soon as APAC sign off drop 2 UAT
| Floor Walking | [49 empty] | Singapore | [70 empty] | Which would give Drop 1 users a benefit of bug fixes | bar: 2019-08-24 to 2019-08-31
| Post Go Live support | [49 empty] | Singapore | [70 empty] | BUT we cannot extend UAT past end of june as it would impact Drop 3 UAT | bar: 2019-08-24 to 2019-09-28
| Drop 3 | [49 empty] | HongKong, Australia, New Zealand
| Development | [49 empty] | HongKong, Australia, New Zealand
| SIT | [49 empty] | HongKong, Australia, New Zealand
| UAT - Migration | [49 empty] | HongKong, Australia, New Zealand | bar: 2019-07-13 to 2019-07-20; 2019-08-03 to 2019-08-10; 2019-08-24 to 2019-08-31
| UAT - Everything else | [49 empty] | HongKong, Australia, New Zealand | bar: 2019-07-20 to 2019-07-27; 2019-08-10 to 2019-08-17; 2019-08-31 to 2019-09-07; 2019-09-21 to 2019-09-28
| Migration | [49 empty] | HongKong, Australia, New Zealand | bar: 2019-09-07 to 2019-09-28
HongKong, Australia, New Zealand | bar: 2019-09-14 to 2019-10-05
| Go Live | [49 empty] | HongKong, Australia, New Zealand | 2019-10-12: Hong Kong, Australia, New Zealand | Still need to discuss with APAC desire to split HK< Aus and NZ over different weeks
| Floor Walking | [49 empty] | HongKong, Australia, New Zealand | bar: 2019-10-12 to 2019-10-19
| Post Go Live support | [49 empty] | HongKong, Australia, New Zealand | bar: 2019-10-12 to 2019-11-16
| Drop 4 | [49 empty] | Vietnam, Thailand, Indonesia
| Development | [49 empty] | Vietnam, Thailand, Indonesia
| SIT | [49 empty] | Vietnam, Thailand, Indonesia
| UAT - Migration | [49 empty] | Vietnam, Thailand, Indonesia | bar: 2019-10-26 to 2019-11-02; 2019-11-16 to 2019-11-23
| UAT - Everything else | [49 empty] | Vietnam, Thailand, Indonesia | bar: 2019-11-02 to 2019-11-09; 2019-11-23 to 2019-11-30; 2019-12-14 to 2019-12-21
| Migration | [49 empty] | Vietnam, Thailand, Indonesia | bar: 2019-12-21 to 2020-01-04
Vietnam, Thailand, Indonesia | bar: 2019-12-21 to 2020-01-11
| Go Live | [49 empty] | Vietnam, Thailand, Indonesia | 2020-01-25: Vietnam, Thailand, Indonesia
| Floor Walking | [49 empty] | Vietnam, Thailand, Indonesia | bar: 2020-01-18 to 2020-01-25
| Post Go Live support | [49 empty] | Vietnam, Thailand, Indonesia | bar: 2020-01-18 to 2020-02-22
| Drop 5 | [49 empty] | Taiwan, Korea, Malaysia
| Development | [49 empty] | Taiwan, Korea, Malaysia
| SIT | [49 empty] | Taiwan, Korea, Malaysia
| UAT - Migration | [49 empty] | Taiwan, Korea, Malaysia | bar: 2019-10-26 to 2019-11-02; 2019-11-16 to 2019-11-23
| UAT - Everything else | [49 empty] | Taiwan, Korea, Malaysia | bar: 2019-11-02 to 2019-11-09; 2019-11-23 to 2019-11-30; 2019-12-14 to 2019-12-21
| Migration | [49 empty] | Taiwan, Korea, Malaysia | bar: 2020-01-25 to 2020-02-15
Taiwan, Korea, Malaysia | bar: 2020-02-01 to 2020-02-22
| Go Live | [49 empty] | Taiwan, Korea, Malaysia | 2020-03-07: Taiwan, Korea, Malaysia
| Floor Walking | [49 empty] | Taiwan, Korea, Malaysia | bar: 2020-02-29 to 2020-03-07
| Post Go Live support | [49 empty] | Taiwan, Korea, Malaysia | bar: 2020-02-29 to 2020-04-04
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
| UAT | [49 empty] | Poland, Hungary Czech, South Africa
| Migration | [49 empty] | Poland, Hungary Czech, South Africa
| Go Live | [49 empty] | Poland, Hungary Czech, South Africa | 2019-04-20: GO LIVE: Poland, Hungary Czech, South Africa
| Floor Walking | [49 empty] | Poland, Hungary Czech, South Africa | bar: 2019-04-13 to 2019-04-20
| Post Go Live support | [49 empty] | Poland, Hungary Czech, South Africa | bar: 2019-04-13 to 2019-06-01
| Drop 2 | [49 empty] | Benelux
| UAT - Migration | [49 empty] | Benelux | [70 empty] | Move of Benelux go live until last week in July… but UAT sign off Drop 2 only extends to 6th July | bar: 2019-04-06 to 2019-04-13; 2019-04-27 to 2019-05-04; 2019-05-25 to 2019-06-01; 2019-06-15 to 2019-06-22
| UAT - Everything else | [49 empty] | Benelux | bar: 2019-04-13 to 2019-04-20; 2019-05-04 to 2019-05-11; 2019-05-25 to 2019-06-08; 2019-06-22 to 2019-07-06
| Migration | [49 empty] | Benelux | bar: 2019-07-13 to 2019-07-20
| Training | [49 empty] | Benelux | bar: 2019-07-06 to 2019-07-27
| Go Live | [49 empty] | Benelux | 2019-08-03: Benelux
| Floor Walking | [49 empty] | Benelux | bar: 2019-07-27 to 2019-08-03
| Post Go Live support | [49 empty] | Benelux | bar: 2019-07-27 to 2019-08-31
| Drop 3 | [49 empty] | UK&I
| Development | [49 empty] | UK&I
| SIT | [49 empty] | UK&I
| UAT - Migration | [49 empty] | UK&I | bar: 2019-07-20 to 2019-07-27; 2019-08-10 to 2019-08-17; 2019-08-31 to 2019-09-07
| UAT - Everything else | [49 empty] | UK&I | bar: 2019-07-27 to 2019-08-03; 2019-08-17 to 2019-08-24; 2019-09-07 to 2019-10-05
| Migration | [49 empty] | UK&I | bar: 2019-09-21 to 2019-10-26
| Training | [49 empty] | UK&I | bar: 2019-10-12 to 2019-11-02
| Go Live | [49 empty] | UK&I | 2019-11-16: UK&I
| Floor Walking | [49 empty] | UK&I | bar: 2019-11-09 to 2019-11-16
| Post Go Live support | [49 empty] | UK&I | bar: 2019-11-09 to 2019-12-14
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
| Development | [49 empty] | Germany, Austria, Switzerland, Italy
| SIT | [49 empty] | Germany, Austria, Switzerland, Italy
| UAT - Migration | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2019-10-26 to 2019-11-02; 2019-11-16 to 2019-11-23
| UAT - Everything else | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2019-11-02 to 2019-11-09; 2019-11-23 to 2019-11-30; 2019-12-14 to 2019-12-21
| Migration | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2020-01-18 to 2020-01-25
| Training | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2020-01-11 to 2020-02-01
| Go Live | [49 empty] | Germany, Austria, Switzerland, Italy | 2020-02-15: Germanics(3), Italy
| Floor Walking | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2020-02-08 to 2020-02-15
| Post Go Live support | [49 empty] | Germany, Austria, Switzerland, Italy | bar: 2020-02-08 to 2020-03-14
| Drop 5 | [49 empty] | Spain, Portugal, France, Nordics
| Development | [49 empty] | Spain, Portugal, France, Nordics
| SIT | [49 empty] | Spain, Portugal, France, Nordics
| UAT - Migration | [49 empty] | Spain, Portugal, France, Nordics | bar: 2019-10-26 to 2019-11-02; 2019-11-16 to 2019-11-23
| UAT - Everything else | [49 empty] | Spain, Portugal, France, Nordics | bar: 2019-11-02 to 2019-11-09; 2019-11-23 to 2019-11-30; 2019-12-14 to 2019-12-21
| Migration | [49 empty] | Spain, Portugal, France, Nordics | 2020-03-21: Iberia(2)
| Training | [49 empty] | Spain, Portugal, France, Nordics | bar: 2020-02-08 to 2020-02-29
| Go Live | [49 empty] | Spain, Portugal, France, Nordics | 2020-04-11: France, Nordics then Iberia(2) | Iberia go live moves from Jan to end of March (UAT sign off remains in Dec)
| Floor Walking | [49 empty] | Spain, Portugal, France, Nordics | bar: 2020-03-07 to 2020-03-14; 2020-03-28 to 2020-04-04
| Post Go Live support | [49 empty] | Spain, Portugal, France, Nordics | bar: 2020-03-07 to 2020-05-02
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Development | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| SIT | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| UAT - Migration | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-01-18 to 2020-01-25; 2020-02-08 to 2020-02-15
| UAT - Everything else | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-01-25 to 2020-02-01; 2020-02-15 to 2020-02-22; 2020-03-07 to 2020-03-14
| Migration | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-04-11 to 2020-04-18
| Training | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-04-04 to 2020-04-25
| Go Live | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | 2020-05-09: Low Volume MENA countries
| Floor Walking | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-05-02 to 2020-05-09
| Post Go Live support | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | bar: 2020-05-02 to 2020-06-06
| Drop 1 | [49 empty] | Peru
| UAT | [49 empty] | Peru
| Migration | [49 empty] | Peru
| Go Live | [49 empty] | Peru
| Floor Walking | [49 empty] | Peru
| Post Go Live support | [49 empty] | Peru
| Drop 2 | [49 empty] | Ecuador
| UAT - Migration | [49 empty] | Ecuador | bar: 2019-04-06 to 2019-05-04
| UAT - Everything else | [49 empty] | Ecuador | bar: 2019-04-06 to 2019-04-20
| Migration | [49 empty] | Ecuador
| Training | [49 empty] | Ecuador | bar: 2019-06-01 to 2019-06-22
| Go Live | [49 empty] | Ecuador | 2019-06-29: Ecuador
| Floor Walking | [49 empty] | Ecuador | bar: 2019-06-22 to 2019-06-29
| Post Go Live support | [49 empty] | Ecuador | bar: 2019-06-22 to 2019-08-10
| Drop 3 | [49 empty] | Colombia, Chile
| Development | [49 empty] | Colombia, Chile
| SIT | [49 empty] | Colombia, Chile
| UAT - Migration | [49 empty] | Colombia, Chile | bar: 2019-05-18 to 2019-05-25; 2019-06-08 to 2019-06-15; 2019-06-29 to 2019-07-06
| UAT - Everything else | [49 empty] | Colombia, Chile | bar: 2019-05-25 to 2019-06-01; 2019-06-15 to 2019-06-22; 2019-07-06 to 2019-07-13
| Migration | [49 empty] | Colombia, Chile | bar: 2019-07-13 to 2019-07-20
| Training | [49 empty] | Colombia, Chile | bar: 2019-07-06 to 2019-08-03
| Go Live | [49 empty] | Colombia, Chile | 2019-08-10: Colombia, Chile
| Floor Walking | [49 empty] | Colombia, Chile | bar: 2019-08-03 to 2019-08-10
| Post Go Live support | [49 empty] | Colombia, Chile | bar: 2019-08-03 to 2019-09-07
| Drop 4 | [49 empty] | Argentina, Puerto Rico
| Development | [49 empty] | Argentina, Puerto Rico
| SIT | [49 empty] | Argentina, Puerto Rico
| UAT - Migration | [49 empty] | Argentina, Puerto Rico | bar: 2019-08-03 to 2019-08-10; 2019-08-24 to 2019-08-31
| UAT - Everything else | [49 empty] | Argentina, Puerto Rico | bar: 2019-08-10 to 2019-08-17; 2019-08-31 to 2019-09-07; 2019-09-21 to 2019-09-28
| Migration | [49 empty] | Argentina, Puerto Rico | bar: 2019-09-07 to 2019-09-14
| Training | [49 empty] | Argentina, Puerto Rico | bar: 2019-09-07 to 2019-09-28
| Go Live | [49 empty] | Argentina, Puerto Rico | 2019-10-12: Argentina, Puerto Rico
| Floor Walking | [49 empty] | Argentina, Puerto Rico | bar: 2019-10-05 to 2019-10-12
| Post Go Live support | [49 empty] | Argentina, Puerto Rico | bar: 2019-10-05 to 2019-11-09
| Drop 5 | [49 empty] | Mexico, Panamá
| Development | [49 empty] | Mexico, Panamá
| SIT | [49 empty] | Mexico, Panamá
| UAT - Migration | [49 empty] | Mexico, Panamá | bar: 2019-08-03 to 2019-08-10; 2019-08-24 to 2019-08-31
| UAT - Everything else | [49 empty] | Mexico, Panamá | bar: 2019-08-10 to 2019-08-17; 2019-08-31 to 2019-09-07; 2019-09-21 to 2019-09-28
| Migration | [49 empty] | Mexico, Panamá | bar: 2019-09-21 to 2019-09-28
| Training | [49 empty] | Mexico, Panamá | bar: 2019-11-02 to 2019-11-23
| Go Live | [49 empty] | Mexico, Panamá | 2019-12-07: Mexico, Panamá
| Floor Walking | [49 empty] | Mexico, Panamá | bar: 2019-11-30 to 2019-12-07
| Post Go Live support | [49 empty] | Mexico, Panamá | bar: 2019-11-30 to 2020-01-04
| Drop 6 | [49 empty] | Brazil
| Development | [49 empty] | Brazil
| SIT | [49 empty] | Brazil
| UAT - Migration | [49 empty] | Brazil | bar: 2019-10-19 to 2019-10-26; 2019-11-09 to 2019-11-16
| UAT - Everything else | [49 empty] | Brazil | bar: 2019-10-26 to 2019-11-02; 2019-11-16 to 2019-11-23; 2019-12-07 to 2019-12-14
| Migration | [49 empty] | Brazil | bar: 2020-01-04 to 2020-01-18
| Training | [49 empty] | Brazil | bar: 2019-12-21 to 2020-01-25
| Go Live | [49 empty] | Brazil | 2020-02-08: Brazil
| Floor Walking | [49 empty] | Brazil | bar: 2020-02-01 to 2020-02-08
| Post Go Live support | [49 empty] | Brazil | bar: 2020-02-01 to 2020-03-07
Assumptions
Countries migration in parrallel
Improved migration timelines
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes can comnplete config for Drop 4, 5 & 6 by end of May

## Migration forecasts
|  | Original View | 20% performance improvement | 20% improvement + 3 years | 20% improvement + 5 years | 20% improvement + 7 years | Region | Country | Entities Count | No. of Days (Approx.) | All Data | 3 years only | 5 years only | 7 years only
Region | Country | Weeks | 0.8 | 0.7 | 0.75 | 0.8 | [5 empty] | 0.7 | 0.75 | 0.8
EMEA | UK | 13.67 | 10.93 | 7.65 | 8.2 | 8.75 | LATAM | Chile | 7279108 | 8 | 1.07 | 0.75 | 0.8 | 0.85
EMEA | Ireland | 1.17 | 0.93 | 0.65 | 0.7 | 0.75 | LATAM | Chile Life | 270373 | 0.5 | 0.07 | 0.05 | 0.05 | 0.05
EMEA | Austria | 0.33 | 0.27 | 0.19 | 0.2 | 0.21 | LATAM | Argentina | 14822819 | 15 | 2 | 1.4 | 1.5 | 1.6
EMEA | Germany | 4.33 | 3.47 | 2.43 | 2.6 | 2.77 | LATAM | Colombia | 15412055 | 16 | 2.13 | 1.49 | 1.6 | 1.71
EMEA | Switzerland | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 | LATAM | Mexico | 21312163 | 22 | 2.93 | 2.05 | 2.2 | 2.35
EMEA | Pakistan | 0.08 | 0.07 | 0.05 | 0.05 | 0.05 | LATAM | Puerto Rico | 11032712 | 12 | 1.6 | 1.12 | 1.2 | 1.28
EMEA | Egypt | 0.08 | 0.07 | 0.05 | 0.05 | 0.05 | LATAM | Brazil | 35835500 | 37 | 4.93 | 3.45 | 3.7 | 3.95
EMEA | Italy | 5.67 | 4.53 | 3.17 | 3.4 | 3.63 | LATAM | Brazil Life | 255320 | 0.5 | 0.07 | 0.05 | 0.05 | 0.05
EMEA | Spain | 4 | 3.2 | 2.24 | 2.4 | 2.56 |  | Ecuador
EMEA | Portugal | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 |  | Ecuador Life
EMEA | France | 9.17 | 7.33 | 5.13 | 5.5 | 5.87
EMEA | Russia | 0.33 | 0.27 | 0.19 | 0.2 | 0.21
EMEA | Turkey | 0.33 | 0.27 | 0.19 | 0.2 | 0.21
EMEA | Bahrain | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 | Region | Country | Entities Count | No. of Days (Approx.) | Weeks | 0.8 | 0.7 | 0.75 | 0.8
[7 empty] | APAC | Australia | 44071459 | 45 | 7.5 | 6 | 4.2 | 4.5 | 4.8
[7 empty] | APAC | New Zealand | 10312178 | 11 | 1.8 | 1.47 | 1.03 | 1.1 | 1.17
Region | Country | Entities Count | No. of Days (Approx.) |  |  |  | APAC | Hong Kong | 15953449 | 16 | 2.7 | 2.13 | 1.49 | 1.6 | 1.71
EMEA | Belgium | 4826465 | 5 |  |  |  | APAC | Vietnam | 9962614 | 10 | 1.7 | 1.33 | 0.93 | 1 | 1.07
| Netherlands | 11343367 | 12 |  |  |  | APAC | Malaysia | 34803393 | 35 | 5.8 | 4.67 | 3.27 | 3.5 | 3.73
| Ecuador | 15211207 | 16 |  |  |  | APAC | Indonesia | 25932879 | 26 | 4.3 | 3.47 | 2.43 | 2.6 | 2.77
LATAM | Ecuador Life | 1296750 | 1.5 |  |  |  | APAC | Thailand | 37274170 | 38 | 6.3 | 5.07 | 3.55 | 3.8 | 4.05
[7 empty] | APAC | Taiwan | 10128924 | 11 | 1.8 | 1.47 | 1.03 | 1.1 | 1.17
[7 empty] | APAC | Korea | ??? | ??? | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!