## 2016 (2) (hidden)
5491705 | time axis 2016-01-02 to 2016-12-24
| 2016-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-05 | 2015-03-12 | 2015-03-19 | 2015-03-26 | 2015-04-02 | 2015-04-09 | 2015-04-16 | 2015-04-23 | 2015-04-30 | 2015-05-07 | 2015-05-14 | 2015-05-21 | 2015-05-28 | 2015-06-04 | 2015-06-11 | 2015-06-18 | 2015-06-25 | 2015-07-02 | 2015-07-09 | 2015-07-16 | 2015-07-23 | 2015-07-30 | 2015-08-06 | 2015-08-13 | 2015-08-20 | 2015-08-27 | 2015-09-03 | 2015-09-10 | 2015-09-17 | 2015-09-24 | 2015-10-01 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-05 | 2015-11-12 | 2015-11-19 | 2015-11-26 | 2015-12-03 | 2015-12-10 | 2015-12-17 | 2015-12-24 | 2015-12-31
Resource | 2016-01-01 | 2016-01-02 | 2016-01-09 | 2016-01-16 | 2016-01-23 | 2016-01-30 | 2016-02-06 | 2016-02-13 | 2016-02-20 | 2016-02-27 | 2016-03-05 | 2016-03-12 | 2016-03-19 | 2016-03-26 | 2016-04-02 | 2016-04-09 | 2016-04-16 | 2016-04-23 | 2016-04-30 | 2016-05-07 | 2016-05-14 | 2016-05-21 | 2016-05-28 | 2016-06-04 | 2016-06-11 | 2016-06-18 | 2016-06-25 | 2016-07-02 | 2016-07-09 | 2016-07-16 | 2016-07-23 | 2016-07-30 | 2016-08-06 | 2016-08-13 | 2016-08-20 | 2016-08-27 | 2016-09-03 | 2016-09-10 | 2016-09-17 | 2016-09-24 | 2016-10-01 | 2016-10-08 | 2016-10-15 | 2016-10-22 | 2016-10-29 | 2016-11-05 | 2016-11-12 | 2016-11-19 | 2016-11-26 | 2016-12-03 | 2016-12-10 | 2016-12-17 | 2016-12-24 | SOW hours | F + A Hours | Variance | Notes | Rate | SOW Value | F + A Cost | Variance |  | Q1 | Q2 | Q3 | Q4
Forecast / Actual | F | bar: 2016-01-02 to 2016-12-24
[62 empty] | TOTAL | 1345030 | 1347125 | 1393925 | 1405625 | 3674545
[58 empty] | CTS | 1817160 | 1817160 |  | MGMT+Arch | 323740 | 341900 | 388700 | 400400 | 1454740
[58 empty] | Con | 0 |  |  | UI Build | 561330 | 552825 | 552825 | 552825 | 2219805
[58 empty] | ACE | 0 |  |  | Migration | 0 | 0 | 0 | 0 | 0
Weekly hours | 303 | 2016-01-02: 1454; 2016-01-09: 1454; 2016-01-16: 1454; 2016-01-23: 1454; 2016-01-30: 1454; 2016-02-06: 1454; 2016-02-13: 1454; 2016-02-20: 1454; 2016-02-27: 1454; 2016-03-05: 1494; 2016-03-12: 1494; 2016-03-19: 1494 | 31710 | 31710 | 0 |  | Vega | 3674545 | 3674545 | 0 | Doc Gen | 300960 | 296400 | 296400 | 296400 | 1190160 | 264600 | 1058400 | 4.8109
Project Management and Design Support | [53 empty] | 2614 | 2614 | 0 |  |  | 481120 | 481120 | 0
K. Larison | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 180 | 422820 | 422820 | 0 |  | 106920 | 105300 | 105300 | 105300
J. Baldwin | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 265 | 265 | 0 |  | 220 | 58300 | 58300 | 0 |  | 15400 | 14300 | 14300 | 14300
N. Collis | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Chris Mates | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Anitha | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2088 | 2088 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Deepak | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2088 | 2088 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
UI Application Design and Build | [53 empty] | 23490 | 23490 | 0 |  |  | 2219805 | 2219805 | 0 |  | 0 | 0 | 0 | 0
K. Biziuk | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
A. Dubovik | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 180 | 422820 | 422820 | 0 |  | 106920 | 105300 | 105300 | 105300
D. Maiseyenka | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
A. Savich | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
V. Shmelev | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
S. Talov | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
Y. Karpovich | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
V. Ivanov | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
A. Krutsko | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
A. Shmelev | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 85 | 199665 | 199665 | 0 |  | 50490 | 49725 | 49725 | 49725
[63 empty] | 0 | 0 | 0 | 0
Architecture | [53 empty] | 2089 | 2089 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
R. Levins | 9 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 2349 | 2349 | 0 |  | 180 | 422820 | 422820 | 0 |  | 106920 | 105300 | 105300 | 105300
W. Gross | 9 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1569 | 1569 | 0 |  | 180 | 282420 | 282420 | 0 |  | 71820 | 70200 | 70200 | 70200
J.Nord | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 1491 | 1491 | 0 |  | 180 | 268380 | 268380 | 0 |  | 22680 | 46800 | 93600 | 105300
O. Ferreira | 9 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2089 | 2089 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Phil | 9 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2089 | 2089 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Data and Doc Model | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Design | 48 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3608 | 3608 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Build |  | 2016-03-05: 40; 2016-03-12: 40; 2016-03-19: 40; 2016-03-26: 40; 2016-04-02: 40; 2016-04-09: 40; 2016-04-16: 40; 2016-04-23: 40; 2016-04-30: 40; 2016-05-07: 40; 2016-05-14: 40; 2016-05-21: 40; 2016-05-28: 40; 2016-06-04: 40; 2016-06-11: 40; 2016-06-18: 40; 2016-06-25: 40; 2016-07-02: 40; 2016-07-09: 40; 2016-07-16: 40; 2016-07-23: 40; 2016-07-30: 40; 2016-08-06: 40; 2016-08-13: 40; 2016-08-20: 40; 2016-08-27: 40; 2016-09-03: 40; 2016-09-10: 40 | 1120 | 1120 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT dev |  | 2016-09-17: 40; 2016-09-24: 40; 2016-10-01: 40; 2016-10-08: 40; 2016-10-15: 40; 2016-10-22: 40; 2016-10-29: 40; 2016-11-05: 40; 2016-11-12: 40; 2016-11-19: 40; 2016-11-26: 40; 2016-12-03: 40; 2016-12-10: 40; 2016-12-17: 40; 2016-12-24: 40 | 600 | 600 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Ingestion | [53 empty] | 0 | 0 | 0 |  |  | 627000 | 627000 | 0 |  | 0 | 0 | 0 | 0
CTS Design | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Build | 40 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 8360 | 8360 | 0 |  | 75 | 627000 | 627000 | 0 |  | 159000 | 156000 | 156000 | 156000
CTS SIT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Integration | [53 empty] | 3040 | 3040 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Design | 40 | 2016-01-02: 200; 2016-01-09: 200; 2016-01-16: 200; 2016-01-23: 200; 2016-01-30: 200; 2016-02-06: 200; 2016-02-13: 200; 2016-02-20: 200; 2016-02-27: 200; 2016-03-05: 200; 2016-03-12: 200; 2016-03-19: 200; 2016-03-26: 200; 2016-04-02: 200; 2016-04-09: 200 | 3040 | 3040 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Build | 40 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 200 | 200 | 200 | 200 | 80 | 80 | 80 | 80 | 80 | 80 | 15640 | 15640 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT dev | [19 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 240 | 240 | 200 | 200 | 200 | 200 | 3960 | 3960 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev |  | 2016-10-22: 40; 2016-10-29: 40; 2016-11-05: 40; 2016-11-12: 40; 2016-11-19: 80; 2016-11-26: 80; 2016-12-03: 120; 2016-12-10: 120; 2016-12-17: 120; 2016-12-24: 120 | 800 | 800 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Security | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Design | [53 empty] | 0 | 0 | 0 |  | 180 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Build | 24 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 40 | 40 | 40 | [8 empty] | 5784 | 5784 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT dev |  | 2016-06-04: 40; 2016-06-11: 40; 2016-06-18: 40; 2016-06-25: 40; 2016-07-02: 40; 2016-07-09: 40; 2016-07-16: 40; 2016-07-23: 40; 2016-07-30: 40; 2016-08-06: 40; 2016-08-13: 40; 2016-08-20: 40; 2016-08-27: 40; 2016-09-03: 40; 2016-09-10: 40; 2016-09-17: 40; 2016-09-24: 80; 2016-10-01: 80; 2016-10-08: 80; 2016-10-15: 80; 2016-10-22: 40; 2016-10-29: 40; 2016-11-05: 40; 2016-11-12: 40; 2016-11-19: 40; 2016-11-26: 40; 2016-12-03: 40; 2016-12-10: 40; 2016-12-17: 40; 2016-12-24: 40 | 1360 | 1360 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev |  | 2016-10-22: 40; 2016-10-29: 40; 2016-11-05: 40; 2016-11-12: 40; 2016-11-19: 40; 2016-11-26: 40; 2016-12-03: 40; 2016-12-10: 40; 2016-12-17: 40; 2016-12-24: 40 | 400 | 400 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Doc Gen | [53 empty] | 2088 | 2088 | 0 |  |  | 1190160 | 1190160 | 0 |  | 0 | 0 | 0 | 0
CTS Design | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2088 | 2088 | 0 |  | 120 | 250560 | 250560 | 0 |  | 63360 | 62400 | 62400 | 62400
CTS Build | 48 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 12528 | 12528 | 0 |  | 75 | 939600 | 939600 | 0 |  | 237600 | 234000 | 234000 | 234000
CTS SIT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
SIT | [53 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Design | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS Build | [53 empty] | 0 | 0 | 0 |  | 35 |  |  |  |  | 0 | 0 | 0 | 0
CTS SIT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS SIT test | 8 | 80 | 80 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 400 | 400 | 400 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 31688 | 31688 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT dev | [53 empty] | 0 | 0 | 0 |  | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CTS UAT test |  | 2016-10-22: 200; 2016-10-29: 200; 2016-11-05: 200; 2016-11-12: 200; 2016-11-19: 200; 2016-11-26: 200; 2016-12-03: 200; 2016-12-10: 200; 2016-12-17: 200; 2016-12-24: 200 | 2000 | 2000 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[63 empty] | 0 | 0 | 0 | 0
Migration Support | [53 empty] | 477 | 477 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
I. Chukhanov | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 477 | 477 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
M. Willingham | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 477 | 477 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
0
0
Resources | [54 empty] | TOTAL | [9 empty] | 0
J. Baldwin | 0 | 2016-01-02: 0; 2016-01-09: 0; 2016-01-16: 0; 2016-01-23: 0; 2016-01-30: 0; 2016-02-06: 0; 2016-02-13: 0; 2016-02-20: 0; 2016-02-27: 0; 2016-03-05: 0; 2016-03-12: 0 |  | 0 | [9 empty] | 0
J. Nord | 0 | 2016-01-02: 0; 2016-01-09: 0; 2016-01-16: 0; 2016-01-23: 0; 2016-01-30: 0; 2016-02-06: 0; 2016-02-13: 0; 2016-02-20: 0; 2016-02-27: 0; 2016-03-05: 0; 2016-03-12: 0 |  | 0 |  | 0 | [7 empty] | 0
K. Larison | 0 | 2016-01-02: 0; 2016-01-09: 0; 2016-01-16: 0; 2016-01-23: 0; 2016-01-30: 0; 2016-02-06: 0; 2016-02-13: 0; 2016-02-20: 0; 2016-02-27: 0; 2016-03-05: 0; 2016-03-12: 0 |  | 0 | [9 empty] | 0
A. Dubovik | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
V. Shmelev | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
A. Savich | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
K. Biziuk | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
A. Shmelev | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
I. Chukhanov | 9 | 2016-01-02: 9; 2016-01-09: 9; 2016-01-16: 9; 2016-01-23: 9; 2016-01-30: 9; 2016-02-06: 9; 2016-02-13: 9; 2016-02-20: 9; 2016-02-27: 9; 2016-03-05: 9; 2016-03-12: 9 |  | 108 | [9 empty] | 0
M. Willingham | 9 | 2016-01-02: 9; 2016-01-09: 9; 2016-01-16: 9; 2016-01-23: 9; 2016-01-30: 9; 2016-02-06: 9; 2016-02-13: 9; 2016-02-20: 9; 2016-02-27: 9; 2016-03-05: 9; 2016-03-12: 9 |  | 108 | [9 empty] | 0
D. Maiseyenka | 9 | 2016-01-02: 45; 2016-01-09: 45; 2016-01-16: 45; 2016-01-23: 45; 2016-01-30: 45; 2016-02-06: 45; 2016-02-13: 45; 2016-02-20: 45; 2016-02-27: 45; 2016-03-05: 45; 2016-03-12: 45 |  | 504 | [9 empty] | 0
0

## Master Plan
|  | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Week Start (Mon) |  | 2019-04-09 | 2019-04-16 | 2019-04-23 | 2019-04-30 | 2019-05-07 | 2019-05-14 | 2019-05-21 | 2019-05-28 | 2019-06-04 | 2019-06-11 | 2019-06-18 | 2019-06-25 | 2019-07-02 | 2019-07-09 | 2019-07-16 | 2019-07-23 | 2019-07-30 | 2019-08-06 | 2019-08-13 | 2019-08-20 | 2019-08-27 | 2019-09-03 | 2019-09-10 | 2019-09-17 | 2019-09-24 | 2019-10-01 | 2019-10-08 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17 | 2019-12-24 | 2019-12-31 | 2020-01-07 | 2020-01-14 | 2020-01-21 | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-06-30 | 2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-07-28 | 2020-08-04 | 2020-08-11 | 2020-08-18 | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | Who
|  | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Week End (Fri) | 2019-04-06 | 2019-04-13 | 2019-04-20 | 2019-04-27 | 2019-05-04 | 2019-05-11 | 2019-05-18 | 2019-05-25 | 2019-06-01 | 2019-06-08 | 2019-06-15 | 2019-06-22 | 2019-06-29 | 2019-07-06 | 2019-07-13 | 2019-07-20 | 2019-07-27 | 2019-08-03 | 2019-08-10 | 2019-08-17 | 2019-08-24 | 2019-08-31 | 2019-09-07 | 2019-09-14 | 2019-09-21 | 2019-09-28 | 2019-10-05 | 2019-10-12 | 2019-10-19 | 2019-10-26 | 2019-11-02 | 2019-11-09 | 2019-11-16 | 2019-11-23 | 2019-11-30 | 2019-12-07 | 2019-12-14 | 2019-12-21 | 2019-12-28 | 2020-01-04 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-02-29 | 2020-03-07 | 2020-03-14 | 2020-03-21 | 2020-03-28 | 2020-04-04 | 2020-04-11 | 2020-04-18 | 2020-04-25 | 2020-05-02 | 2020-05-09 | 2020-05-16 | 2020-05-23 | 2020-05-30 | 2020-06-06 | 2020-06-13 | 2020-06-20 | 2020-06-27 | 2020-07-04 | 2020-07-11 | 2020-07-18 | 2020-07-25 | 2020-08-01 | 2020-08-08 | 2020-08-15 | 2020-08-22 | 2020-08-29 | 2020-09-05 | 2020-09-12 | 2020-09-19 | 2020-09-26 | 2020-10-03 | 2020-10-10 | 2020-10-17 | 2020-10-24 | 2020-10-31 | 2020-11-07 | 2020-11-14 | Who
[52 empty] | 2018 Q2 | [12 empty] | 20 18 Q3 | [12 empty] | 2018 Q4 | [13 empty] | 2019 Q1 | [11 empty] | 2019 Q2
[52 empty] | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul | [5 empty] | Interfaces in Scope
| Drop 1 | [49 empty] | Philippines
| UAT | [49 empty] | Philippines
| Migration | [49 empty] | Philippines
| Go Live | [49 empty] | Philippines |  |  | GO LIVE: Philippines | [9 empty] | Soft Go Live of the Drop 2 code for Philipinnes
| Floor Walking | [49 empty] | Philippines
| Post Go Live support | [49 empty] | Philippines
| Drop 2 | [49 empty] | Singapore
| UAT - Migration | [49 empty] | Singapore
| UAT - Everything else | [49 empty] | Singapore
| Migration | [49 empty] | Singapore | [10 empty] | RN |  |  |  |  | Final
| Training | [49 empty] | Singapore
| Go Live | [49 empty] | Singapore | [20 empty] | Singapore
| Floor Walking | [49 empty] | Singapore
| Post Go Live support | [49 empty] | Singapore
| Drop 3 | [49 empty] | HongKong, Australia, New Zealand
| Development | [49 empty] | HongKong, Australia, New Zealand
| Data Config | [49 empty] | HongKong, Australia, New Zealand
| interfaces & Ingestion Config | [49 empty] | HongKong, Australia, New Zealand
| Others Config | [49 empty] | HongKong, Australia, New Zealand
MI Interim
MI Strategic
| New interfaces | [49 empty] | HongKong, Australia, New Zealand
| SIT | [49 empty] | HongKong, Australia, New Zealand
| Data Config | [49 empty] | HongKong, Australia, New Zealand
| Others Config | [49 empty] | HongKong, Australia, New Zealand
| SIT sample execution - Mig | [49 empty] | HongKong, Australia, New Zealand
| New interfaces - TBD | [49 empty] | HongKong, Australia, New Zealand
| SIT - Functional Testing | [49 empty] | HongKong, Australia, New Zealand
| SIT - Data Migration Testing on UAT Environment | [49 empty] | HongKong, Australia, New Zealand
| UAT Build team effort (Deployment & Config) | [49 empty] | HongKong, Australia, New Zealand
| Data Config | [49 empty] | HongKong, Australia, New Zealand
| Others Config | [49 empty] | HongKong, Australia, New Zealand
| Migration Run | [49 empty] | HongKong, Australia, New Zealand
| Interfaces & Ingestion Config | [49 empty] | HongKong, Australia, New Zealand
| UAT - Migration | [49 empty] | HongKong, Australia, New Zealand
| UAT - Everything else | [49 empty] | HongKong, Australia, New Zealand
| Migration - Content Transfer | [49 empty] | HongKong, Australia, New Zealand
| Migration - PROD | [49 empty] | HongKong, Australia, New Zealand | [22 empty] | RN | [5 empty] | Interim | Final
| Training | [49 empty] | HongKong, Australia, New Zealand
| Go Live | [49 empty] | HongKong, Australia, New Zealand | [27 empty] | Hong Kong, Australia, New Zealand
| Floor Walking | [49 empty] | HongKong, Australia, New Zealand
| Post Go Live support | [49 empty] | HongKong, Australia, New Zealand
| Drop 4 | [49 empty] | Vietnam, Thailand, Indonesia
| Development | [49 empty] | Vietnam, Thailand, Indonesia
| Data Config | [49 empty] | Vietnam, Thailand, Indonesia
| interfaces & Ingestion Config | [49 empty] | Vietnam, Thailand, Indonesia
| Others Config | [49 empty] | Vietnam, Thailand, Indonesia
| New interfaces | [49 empty] | Vietnam, Thailand, Indonesia
| SIT | [49 empty] | Vietnam, Thailand, Indonesia
| Data Config | [49 empty] | Vietnam, Thailand, Indonesia
| Others Config | [49 empty] | Vietnam, Thailand, Indonesia
| SIT sample execution - Mig in UAT | [49 empty] | Vietnam, Thailand, Indonesia
| New interfaces | [49 empty] | Vietnam, Thailand, Indonesia
| SIT - Functional Testing | [49 empty] | Vietnam, Thailand, Indonesia
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Vietnam, Thailand, Indonesia
| UAT Build team effort (Deployment & Config) | [49 empty] | Vietnam, Thailand, Indonesia
| Data Config | [49 empty] | Vietnam, Thailand, Indonesia
| Others Config | [49 empty] | Vietnam, Thailand, Indonesia
| Migration Run | [49 empty] | Vietnam, Thailand, Indonesia
| Interfaces & Ingestion Config | [49 empty] | Vietnam, Thailand, Indonesia
| UAT - Migration | [49 empty] | Vietnam, Thailand, Indonesia
| UAT - Everything else | [49 empty] | Vietnam, Thailand, Indonesia
| Migration - Content Transfer | [49 empty] | Vietnam, Thailand, Indonesia
| Migration | [49 empty] | Vietnam, Thailand, Indonesia | [34 empty] | RN | [5 empty] | Interim | Final
Vietnam, Thailand, Indonesia
| Go Live | [49 empty] | Vietnam, Thailand, Indonesia | [42 empty] | Vietnam, Thailand, Indonesia
| Floor Walking | [49 empty] | Vietnam, Thailand, Indonesia
| Post Go Live support | [49 empty] | Vietnam, Thailand, Indonesia
| Drop 5 | [49 empty] | Taiwan, Korea, Malaysia
| Development | [49 empty] | Taiwan, Korea, Malaysia
| Data Config | [49 empty] | Taiwan, Korea, Malaysia
| interfaces & Ingestion Config | [49 empty] | Taiwan, Korea, Malaysia
| Others Config | [49 empty] | Taiwan, Korea, Malaysia
| New interfaces | [49 empty] | Taiwan, Korea, Malaysia
| SIT | [49 empty] | Taiwan, Korea, Malaysia
| Data Config | [49 empty] | Taiwan, Korea, Malaysia
| Others Config | [49 empty] | Taiwan, Korea, Malaysia
| SIT sample execution - Mig in UAT | [49 empty] | Taiwan, Korea, Malaysia
| New interfaces | [49 empty] | Taiwan, Korea, Malaysia
| SIT - Functional Testing | [49 empty] | Taiwan, Korea, Malaysia
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Taiwan, Korea, Malaysia
| UAT Build team effort (Deployment & Config) | [49 empty] | Taiwan, Korea, Malaysia
| Data Config | [49 empty] | Taiwan, Korea, Malaysia
| Others Config | [49 empty] | Taiwan, Korea, Malaysia
| Migration Run | [49 empty] | Taiwan, Korea, Malaysia
| Interfaces & Ingestion Config | [49 empty] | Taiwan, Korea, Malaysia
| UAT - Migration | [49 empty] | Taiwan, Korea, Malaysia
| UAT - Everything else | [49 empty] | Taiwan, Korea, Malaysia
| Migration - Content Transfer | [49 empty] | Taiwan, Korea, Malaysia
| Migration | [49 empty] | Taiwan, Korea, Malaysia | [34 empty] | RN | [9 empty] | Interim |  |  | Final
Taiwan, Korea, Malaysia
| Go Live | [49 empty] | Taiwan, Korea, Malaysia | [48 empty] | Taiwan, Korea, Malaysia
| Floor Walking | [49 empty] | Taiwan, Korea, Malaysia
| Post Go Live support | [49 empty] | Taiwan, Korea, Malaysia
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
| UAT | [49 empty] | Poland, Hungary Czech, South Africa
| Migration | [49 empty] | Poland, Hungary Czech, South Africa
| Go Live | [49 empty] | Poland, Hungary Czech, South Africa |  |  | GO LIVE: Poland, Hungary Czech, South Africa
| Floor Walking | [49 empty] | Poland, Hungary Czech, South Africa
| Post Go Live support | [49 empty] | Poland, Hungary Czech, South Africa
| Drop 2 | [49 empty] | Benelux
| UAT - Migration | [49 empty] | Benelux
| UAT - Everything else | [49 empty] | Benelux
| Migration | [49 empty] | Benelux | [10 empty] | Final
| Training | [49 empty] | Benelux
| Go Live | [49 empty] | Benelux | [17 empty] | Benelux
| Floor Walking | [49 empty] | Benelux
| Post Go Live support | [49 empty] | Benelux
| Drop 3 | [49 empty] | UK&I
| Development | [49 empty] | UK&I
| Data Config | [49 empty] | UK&I
| interfaces & Ingestion Config | [49 empty] | UK&I
| Others Config | [49 empty] | UK&I
| New interfaces | [49 empty] | UK&I
| SIT | [49 empty] | UK&I
| Data Config | [49 empty] | UK&I
| Others Config | [49 empty] | UK&I
| SIT sample execution - Mig | [49 empty] | UK&I
| New interfaces | [49 empty] | UK&I
| SIT - Functional Testing | [49 empty] | UK&I
| SIT - Data Migration Testing on UAT Environment | [49 empty] | UK&I
| UAT Build team effort (Deployment & Config) | [49 empty] | UK&I
| Data Config | [49 empty] | UK&I
| Others Config | [49 empty] | UK&I
| Migration Run | [49 empty] | UK&I | [13 empty] | C1 |  | C2
| Interfaces & Ingestion Config | [49 empty] | UK&I
| UAT - Migration | [49 empty] | UK&I
| UAT - Everything else | [49 empty] | UK&I
| Migration - Content Transfer | [49 empty] | UK&I
| Migration | [49 empty] | UK&I | [23 empty] | RN | [9 empty] | Final
| Training | [49 empty] | UK&I
| Go Live | [49 empty] | UK&I | [32 empty] | UK&I
| Floor Walking | [49 empty] | UK&I
| Post Go Live support | [49 empty] | UK&I
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
| Development | [49 empty] | Germany, Austria, Switzerland, Italy
| Data Config | [49 empty] | Germany, Austria, Switzerland, Italy
| interfaces & Ingestion Config | [49 empty] | Germany, Austria, Switzerland, Italy
| Others Config | [49 empty] | Germany, Austria, Switzerland, Italy
| New interfaces | [49 empty] | Germany, Austria, Switzerland, Italy
| SIT | [49 empty] | Germany, Austria, Switzerland, Italy
| Data Config | [49 empty] | Germany, Austria, Switzerland, Italy
| Others Config | [49 empty] | Germany, Austria, Switzerland, Italy
| SIT sample execution - Mig in UAT | [49 empty] | Germany, Austria, Switzerland, Italy
| New interfaces | [49 empty] | Germany, Austria, Switzerland, Italy
| SIT - Functional Testing | [49 empty] | Germany, Austria, Switzerland, Italy
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Germany, Austria, Switzerland, Italy
| UAT Build team effort (Deployment & Config) | [49 empty] | Germany, Austria, Switzerland, Italy
| Data Config | [49 empty] | Germany, Austria, Switzerland, Italy
| Others Config | [49 empty] | Germany, Austria, Switzerland, Italy
| Migration Run | [49 empty] | Germany, Austria, Switzerland, Italy
| Interfaces & Ingestion Config | [49 empty] | Germany, Austria, Switzerland, Italy
| UAT - Migration | [49 empty] | Germany, Austria, Switzerland, Italy
| UAT - Everything else | [49 empty] | Germany, Austria, Switzerland, Italy
| Migration - Content Transfer | [49 empty] | Germany, Austria, Switzerland, Italy
| Migration | [49 empty] | Germany, Austria, Switzerland, Italy | [34 empty] | RN | [5 empty] | Interim | Final
| Training | [49 empty] | Germany, Austria, Switzerland, Italy
| Go Live | [49 empty] | Germany, Austria, Switzerland, Italy | [45 empty] | Germany, Austria, Switzerland, Italy
| Floor Walking | [49 empty] | Germany, Austria, Switzerland, Italy
| Post Go Live support | [49 empty] | Germany, Austria, Switzerland, Italy
| Drop 5 | [49 empty] | Spain, Portugal, France, Nordics
| Development | [49 empty] | Spain, Portugal, France, Nordics
| Data Config | [49 empty] | Spain, Portugal, France, Nordics
| interfaces & Ingestion Config | [49 empty] | Spain, Portugal, France, Nordics
| Others Config | [49 empty] | Spain, Portugal, France, Nordics
| New interfaces | [49 empty] | Spain, Portugal, France, Nordics
| SIT | [49 empty] | Spain, Portugal, France, Nordics
| Data Config | [49 empty] | Spain, Portugal, France, Nordics
| Others Config | [49 empty] | Spain, Portugal, France, Nordics
| SIT sample execution - Mig in UAT | [49 empty] | Spain, Portugal, France, Nordics
| New interfaces | [49 empty] | Spain, Portugal, France, Nordics
| SIT - Functional Testing | [49 empty] | Spain, Portugal, France, Nordics
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Spain, Portugal, France, Nordics
| UAT Build team effort (Deployment & Config) | [49 empty] | Spain, Portugal, France, Nordics
| Data Config | [49 empty] | Spain, Portugal, France, Nordics
| Others Config | [49 empty] | Spain, Portugal, France, Nordics
| Migration Run | [49 empty] | Spain, Portugal, France, Nordics
| Interfaces & Ingestion Config | [49 empty] | Spain, Portugal, France, Nordics
| UAT - Migration | [49 empty] | Spain, Portugal, France, Nordics
| UAT - Everything else | [49 empty] | Spain, Portugal, France, Nordics
| Migration - Content Transfer | [49 empty] | Spain, Portugal, France, Nordics
| Migration | [49 empty] | Spain, Portugal, France, Nordics | [34 empty] | RN | [5 empty] | Interim | Final | [5 empty] | Interim | Final
| Training | [49 empty] | Spain, Portugal, France, Nordics
| Go Live | [49 empty] | Spain, Portugal, France, Nordics | [42 empty] | Spain, Portugal | [6 empty] | France, Nordics | [21 empty] | SP + POR = Jan, FRA + NORD = Mar
| Floor Walking | [49 empty] | Spain, Portugal, France, Nordics
| Post Go Live support | [49 empty] | Spain, Portugal, France, Nordics
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Development | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Data Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| interfaces & Ingestion Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Others Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| New interfaces | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| SIT | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Data Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Others Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| SIT sample execution - Mig in UAT | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| New interfaces | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| SIT - Functional Testing | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| UAT Build team effort (Deployment & Config) | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Data Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Others Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Migration Run | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Interfaces & Ingestion Config | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| UAT - Migration | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| UAT - Everything else | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Migration - Content Transfer | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Migration | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | [48 empty] | RN |  |  |  | Interim | Final
| Training | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Go Live | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt | [57 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Floor Walking | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Post Go Live support | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
| Drop 1 | [49 empty] | Peru
| UAT | [49 empty] | Peru
| Migration | [49 empty] | Peru
| Go Live | [49 empty] | Peru
| Floor Walking | [49 empty] | Peru
| Post Go Live support | [49 empty] | Peru
| Drop 2 | [49 empty] | Ecuador
| UAT - Migration | [49 empty] | Ecuador
| UAT - Everything else | [49 empty] | Ecuador
| Migration | [49 empty] | Ecuador
| Training | [49 empty] | Ecuador
| Go Live | [49 empty] | Ecuador | [10 empty] | Ecuador
| Floor Walking | [49 empty] | Ecuador
| Post Go Live support | [49 empty] | Ecuador
| Drop 3 | [49 empty] | Colombia, Chile
| Development | [49 empty] | Colombia, Chile
| Data Config | [49 empty] | Colombia, Chile
| interfaces & Ingestion Config | [49 empty] | Colombia, Chile
| Others Config | [49 empty] | Colombia, Chile
| New interfaces | [49 empty] | Colombia, Chile
| SIT | [49 empty] | Colombia, Chile
| Data Config | [49 empty] | Colombia, Chile
| Others Config | [49 empty] | Colombia, Chile
| SIT sample execution - Mig in UAT | [49 empty] | Colombia, Chile
| New interfaces | [49 empty] | Colombia, Chile
| SIT - Functional Testing | [49 empty] | Colombia, Chile
SIT - Data Migration Testing on UAT Environment
| UAT Build team effort (Deployment & Config) | [49 empty] | Colombia, Chile
| Data Config | [49 empty] | Colombia, Chile
| Others Config | [49 empty] | Colombia, Chile
| Migration Run | [49 empty] | Colombia, Chile
| Interfaces & Ingestion Config | [49 empty] | Colombia, Chile
| UAT - Migration | [49 empty] | Colombia, Chile | [71 empty] | Includes ChubbNet interface (NEW)
| UAT - Everything else | [49 empty] | Colombia, Chile
| Migration | [49 empty] | Colombia, Chile | [14 empty] | RN |  |  |  | Final
| Training | [49 empty] | Colombia, Chile
| Go Live | [49 empty] | Colombia, Chile | [18 empty] | Colombia, Chile | [52 empty] | Chub Net
| Floor Walking | [49 empty] | Colombia, Chile
| Post Go Live support | [49 empty] | Colombia, Chile
| Drop 4 | [49 empty] | Argentina, Puerto Rico
| Development | [49 empty] | Argentina, Puerto Rico | [71 empty] | Config must be done by mid May (Argentina nearly complete)
| Data Config | [49 empty] | Argentina, Puerto Rico
| interfaces & Ingestion Config | [49 empty] | Argentina, Puerto Rico
| Others Config | [49 empty] | Argentina, Puerto Rico
| New interfaces | [49 empty] | Argentina, Puerto Rico
| SIT | [49 empty] | Argentina, Puerto Rico
| Data Config | [49 empty] | Argentina, Puerto Rico
| Others Config | [49 empty] | Argentina, Puerto Rico
| SIT sample execution - Mig in UAT | [49 empty] | Argentina, Puerto Rico
| New interfaces | [49 empty] | Argentina, Puerto Rico
| SIT - Functional Testing | [49 empty] | Argentina, Puerto Rico
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Argentina, Puerto Rico
| UAT Build team effort (Deployment & Config) | [49 empty] | Argentina, Puerto Rico
| Data Config | [49 empty] | Argentina, Puerto Rico
| Others Config | [49 empty] | Argentina, Puerto Rico
| Migration Run | [49 empty] | Argentina, Puerto Rico
| Interfaces & Ingestion Config | [49 empty] | Argentina, Puerto Rico
| UAT - Migration | [49 empty] | Argentina, Puerto Rico
| UAT - Everything else | [49 empty] | Argentina, Puerto Rico
| Migration - Content Transfer | [49 empty] | Argentina, Puerto Rico
| Migration | [49 empty] | Argentina, Puerto Rico | [22 empty] | RN |  |  |  | Final
| Training | [49 empty] | Argentina, Puerto Rico
| Go Live | [49 empty] | Argentina, Puerto Rico | [27 empty] | Argentina, Puerto Rico
| Floor Walking | [49 empty] | Argentina, Puerto Rico
| Post Go Live support | [49 empty] | Argentina, Puerto Rico
| Drop 5 | [49 empty] | Mexico, Panamá
| Development | [49 empty] | Mexico, Panamá | [71 empty] | Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| Data Config | [49 empty] | Mexico, Panamá
| interfaces & Ingestion Config | [49 empty] | Mexico, Panamá
| Others Config | [49 empty] | Mexico, Panamá
| New interfaces | [49 empty] | Mexico, Panamá
| SIT | [49 empty] | Mexico, Panamá
| Data Config | [49 empty] | Mexico, Panamá
| Others Config | [49 empty] | Mexico, Panamá
| SIT sample execution - Mig in UAT | [49 empty] | Mexico, Panamá
| New interfaces | [49 empty] | Mexico, Panamá
| SIT - Functional Testing | [49 empty] | Mexico, Panamá
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Mexico, Panamá
| UAT Build team effort (Deployment & Config) | [49 empty] | Mexico, Panamá
| Data Config | [49 empty] | Mexico, Panamá
| Others Config | [49 empty] | Mexico, Panamá
| Migration Run | [49 empty] | Mexico, Panamá
| Interfaces & Ingestion Config | [49 empty] | Mexico, Panamá
| UAT - Migration | [49 empty] | Mexico, Panamá
| UAT - Everything else | [49 empty] | Mexico, Panamá | [71 empty] | Includes Meridian Interface (re-worked from APAC interface)
| Migration - Content Transfer | [49 empty] | Mexico, Panamá
| Migration | [49 empty] | Mexico, Panamá | [22 empty] | RN |  |  | Final
| Training | [49 empty] | Mexico, Panamá
| Go Live | [49 empty] | Mexico, Panamá | [35 empty] | Mexico, Panamá
| Floor Walking | [49 empty] | Mexico, Panamá
| Post Go Live support | [49 empty] | Mexico, Panamá
| Drop 6 | [49 empty] | Brazil
| Development | [49 empty] | Brazil | [71 empty] | Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| Data Config | [49 empty] | Brazil
| interfaces & Ingestion Config | [49 empty] | Brazil
| Others Config | [49 empty] | Brazil
| New interfaces | [49 empty] | Brazil
| SIT | [49 empty] | Brazil
| Data Config | [49 empty] | Brazil
| Others Config | [49 empty] | Brazil
| SIT sample execution - Mig in UAT | [49 empty] | Brazil
| New interfaces | [49 empty] | Brazil
| SIT - Functional Testing | [49 empty] | Brazil
| SIT - Data Migration Testing on UAT Environment | [49 empty] | Brazil
| UAT Build team effort (Deployment & Config) | [49 empty] | Brazil
| Data Config | [49 empty] | Brazil
| Others Config | [49 empty] | Brazil
| Migration Run | [49 empty] | Brazil
| Interfaces & Ingestion Config | [49 empty] | Brazil
| UAT - Migration | [49 empty] | Brazil
| UAT - Everything else | [49 empty] | Brazil
Migration - Content Transfer
| Migration | [49 empty] | Brazil | [33 empty] | RN | [5 empty] | Interim | Final
| Training | [49 empty] | Brazil
| Go Live | [49 empty] | Brazil | [44 empty] | Brazil
| Floor Walking | [49 empty] | Brazil
| Post Go Live support | [49 empty] | Brazil
Assumptions
Based on LATAM plan with slip in Drop 2 factored in
Not reviewed by LATAM yet
Countries migration in parrallel
Improved migration timelines
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes can comnplete config for Drop 4, 5 & 6 by end of May
Assumes can run Brasil, Mexico and Puerto Rico UAT at same time
Note on BN34: Drop 1&2 Interfaces to be rolled out for New Region: New Zealand 1. Interfaces that were part of Drop 1&2 rollout where in it was specific to a particular region (country specific) are being leveraged to different region in Drop 2.E.g.: Genius Integration to be rolled out to APAC region. Hence we would required two weeks of SIT testing. 3. Build validations, defect retesting & adhoc reports
Note on BN35: 1. The Given Timeline will Cover Exhaustive Migration Testing for New Zealand country. 2. Three New General Files are added In-Scope for Australia. 3. File volume for six month data is high - henceforth we have to do extensive Coverage for all File Types Hence we require 2 weeks for Testing. 4. Build validations, defect retesting & adhoc reports
Note on BY60: Drop 1&2 Interfaces to be rolled out for New Region: Vietnam 1. Interfaces that were part of Drop 1&2 rollout where in it was specific to a particular region (country specific) are being leveraged to different region in Drop 3.E.g.: Genius Integration to be rolled out to APAC region. Hence we would required two weeks of SIT testing 4. Build validations, defect retesting & adhoc reports
Note on BZ61: 1. The Given Timeline will Cover Exhaustive Migration Testing for Vietnam country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BV86: 1. Regression testing for existing UI & interfaces 2. Build validations, defect retesting & adhoc reports
Note on BZ86: 1. Considering testing for korea country as 7 new interfaces getting implemented. 2. High level regression testing.
Note on BV87: 1. The Given Timeline will Cover Exhaustive Migration Testing for Korea country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BR127: 1. Considering UK country for testing which has all 11 new interfaces lined in drop 3 along with UI & existing interfaces regression testing. 2. Build validations, defect retesting & adhoc reports
Note on BN128: 1. The Given Timeline will Cover Exhaustive Migration Testing for UK and for Ireland only newly added File Types will be tested along with Regression Pack 2. Build validations, defect retesting & adhoc reports
Note on BO128: 1. The Given Timeline will Cover Exhaustive Migration Testing for UK and for Ireland only newly added File Types will be tested along with Regression Pack 2. Build validations, defect retesting & adhoc reports
Note on BZ154: 1. Considering Germany country for testing as it has 2 new interfaces bringing in and UI & existing interfaces validations. 2. Build validations, defect retesting & adhoc report
Note on BV155: 1. The Given Timeline will Cover Exhaustive Migration Testing for Germany country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. 1. The Given Timeline will Cover Exhaustive Migration Testing for UK and for Ireland only newly added File Types will be tested along with Regression Pack 2. Build validations, defect retesting & adhoc reports
Note on BZ179: 1. Considering Spain & France countries for testing as it has all the touch points for new interfaces. Approx 6 new interfaces are getting implemented, require confirmation on the same 2. Build validations, defect retesting & adhoc reports
Note on BX180: 1. The Given Timeline will Cover Exhaustive Migration Testing for Spain and France countries. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on CN205: 1. Considering Russia & Bahrain countries for testing as it has all the touch points in new interfaces. Approx 5 new interfaces are getting implemented, require confirmation on the same 2. Build validations, defect retesting & adhoc reports
Note on CN206: 1. The Given Timeline will Cover Exhaustive Migration Testing for Russia and Bahrain countries. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BL246: 1. Considering Columbia for testing as it has all the integration touch points and we have 2 new interfaces getting implemented. 2. Build validations, defect retesting & adhoc reports
Note on BL247: 1. The Given Timeline will Cover Exhaustive Migration Testing for Columbia country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BP271: 1. Considering Argentina for testing as it has all the integration touch points. 2. Build validations, defect retesting & adhoc reports
Note on BO272: 1. The Given Timeline will Cover Exhaustive Migration Testing for Argentina country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BP297: 1. Considering Mexico for testing as it has all the integration touch points and we have 1 new interface getting implemented 2. Build validations, defect retesting & adhoc reports
Note on BP298: 1. The Given Timeline will Cover Exhaustive Migration Testing for Mexico country. 2.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 3. In case New File Types are added, this Timeline may vary. 4. Build validations, defect retesting & adhoc reports
Note on BZ322: 1. we have 2 new interfaces getting implemented for Brazil country. 2. Build validations, defect retesting & adhoc reports
Note on CA323: 1.Configuration Sheet for the Countries are not available hence we are assuming this timeline which includes Only Regression Suite for already existing File Types. 2. In case New File Types are added, this Timeline may vary. 3. Build validations, defect retesting & adhoc reports

## Key Notes
Drop | Region | Summary | Impacted phase | Delay | Original Start Date | Revised Start Date
Drop 3 | APAC | Hong Kong, Australia, New Zealand | Go live | 2 Weeks | 2018-10-08 | 2018-10-22
Drop 3 | EMEA | UK&I | UAT | 4 Weeks | 2018-07-16 | 2018-08-13
Drop 3 | EMEA | UK&I | Go live | 2 Weeks | 2018-11-05 | 2018-11-19
Drop 3 | LATAM | Colombia, Chile | Go live | 1 Week | 2018-07-30 | 2018-08-06
Track | Key Items In Scope | Key Risks | Key Dependencies
Migration | No changes compared to Drop1 | Unavailability of LATAM informatica server will have an impact in the migration timeline. | This is needed before Drop2 production go live.
| Notes Redesign & Content transfer has been included | Master plan has got Parallel UAT migration for multiple Drops, within same region & countries. | Additional UAT environments to be procured
| For UAT, 3-4 weeks of Migration Execution is planned to meet the UAT timeline. The coverage of data for ~3-4 weeks would cover ~1 month of data | Parallel Migration Execution has not been tested in PTE/lower environment | Dependant on the Infrastructure scalability & PTE execution (this is part of Migration Accelration plan discussion)
|  | Not able to execute the LATAM Doc Migration and we are having only limited time daily for execution which is only 3 - 4 hours and this is not sufficient | Need support from LATAM ITSupport to execute the jobs during LATAM off hours to cover the Doc Migration for every UAT and PROD timelines
|  | Data volume has been picked up as of April'18 hence the timeline would based on the increased volume before Go live | N/A
QEA - Functional | Only changes on the UI/Interfaces /Migration(Content transfer/Notes redesign will be considered) | * The timelines also covers the testing of Adhoc build of earlier drop code which covers defects fixes that we have experienced in current drops. * Parallel SIT and UAT Execution: UAT Testing would commence along with the SIT Testing which may lead to the high defect leakage into UAT. | * SIT deployment should be done on the planned delivery date. Delay in code drops will affect quality of the applications & SIT execution window (regression defects).
QEA - Migration | Only Regression testing will be done | sample migration testing will be done in UAT as part of SIT | Any delays in the data load completion would affect the Migration testing timelines.
|  | * The timelines also covers the testing of Adhoc build of earlier drop code which covers defects fixes that we have experienced in current drops. * Parallel SIT and UAT Execution: UAT Testing would commence along with the SIT Testing which may lead to the high defect leakage into UAT. * Configuration sheet updates or CR's or any new file types added would affect the Migration Testing timeline. | Configuration Sheet for the Countries in Drop - 4, 5 & 6 are yet to be finalised and hence we are assuming this timeline which includes only Regression Suite for already existing File Types.

## QA Activites RunBook
QEA Activities Run Book Per Country
Region
# | Phase | Activity | APAC | EMEA | LATAM | Team | Dependency | Estimated Effort /Country (Days)
1 | SIT Functional | Updating the automation suite for Country Specific Config Data / Code Object Level Changes. | 1 | 1 | 1 | QEA Automation Team | Config data to be ready. | 2 days per country per region
2 | SIT Functional | Regression test validations(Manual & Automation execution) | 1 | 1 | 1 | QEA Manual/Automation Team | SIT build to be deployed as per the plan to proceed the testing. | 1 Day Per Country per region
3 | SIT Functional | Adhoc build validations for the previous drops to perform smoke testing & defect retesting. | 1 | 1 | 1 | QEA Manual/Automation Team |  | 2 Days for 3 Regions(one country per region)
4 | SIT Migration | Regression testing validation for the File types(~90 file count) which are in scope for Migration as per the Configuration documents. | 1 | 1 | 1 | QEA Data Migration Team | Data load has to be done as per the plan. | 4 days per country(excluding the Data Load activities)
5 | SIT Migration | Test Data Identification and Defect Retesting. | 1 | 1 | 1 | QEA Data Migration Team | Data load has to be done for the defect fixes. | 1 Day Per Country per region(excluding the Data Load activities)
6 | SIT Migration | Adhoc build validations for the previous drops to perform smoke testing. | 1 | 1 | 1 | QEA Data Migration Team | SIT build to be deployed as per the plan to proceed the testing. | 1 Day (3 Regions)

## QEA (hidden)
Functional Testing:
Assumptions:
· The SIT timelines highlighted is purely based on Capacity based testing( Functional – 5, Automation – 1 & Data Migration – 2) across all the future drops.
· The timelines also covers the testing of Adhoc build, Adhoc defects fixes retesting that we have experienced in current drops.
· SIT deploy should be done on the planned delivery date. Delay in code drops will affect quality of the applications (regression defects).
· Any planned / unplanned down time should be informed well in advance to re-plan the test execution and update the timelines.
· Any changes to the either of the below points in countries within the region, would impact the test execution time lines
o Change in Functionality
o Change to existing Interfaces or adding new interface
o New CR’s
· Any adhoc priority request for testing, would impact the testing timelines for the current Drop.
· Assuming Separate SIT environment will be provided for each drops.
· Assuming APAC, EMEA & LATAM Drops test execution will go in parallel.
In scope for testing:
· Will be selecting one country per region for the respective drops.
· If there is any specific new changes to the below points for any country within the region; then we would perform a full SIT coverage testing based on the requirement shared, then followed by regression testing.
Ø Change in Functionality
Ø Change to existing Interfaces
Ø New CR’s
Out of scope for testing:
· Remaining countries out of scope.
Risk Forecast
· Parallel SIT and UAT Execution: UAT Testing has been commenced along with the SIT Regression Testing. This would lead to the high defect leakage into UAT.
· Parallel SIT Execution will be happening in APAC and LATAM Drops.
· Stringent/Short Testing Window.
· Countries selected for SIT testing in respective drops, should not be pushed to later drops when testing is in progress.
Data Migration Testing:
Assumptions:
1. The SIT Timeline is highlighted only for the data migration validation it exclude the time required for data load.
2. Configuration Sheet for the Countries in Drop - 4, 5 & 6 are yet to be finalised and hence we are assuming this timeline which includes only Regression Suite for already existing File Types.
3. Assuming we will be migrating 6 months of data for UAT testing.
4. Only One Bulk and One Trickle Data Load will be done apart from Defect Fixes Data Loads.
In scope for testing:
1. Regression Testing will be done by selecting one country per region.
2. In the other Countries, only Newly added File Types will be Tested along with Regression Pack.
Risk Forecast
1. We do Risk-based testing and hence 100% coverage is not possible .i.e. Testing will be done for 6 month data only.
2. Due to this Issues can be identified in Higher Environments which is inevitable because of Stringent Timeline.
3. Requirement adding or CR’s or any Configuration sheet update or any New File Types are added would impact the testing timelines.

## Old Aggressive Plan (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | time axis 2017-12-04 to 2019-11-11
[56 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [13 empty] | Q1 | [11 empty] | Q2
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Philippines
| UAT | [50 empty] | 2017-12-11: Complete
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Philippines
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-14
| Drop 2 | [49 empty] | Singapore
UAT - Migration | bar: 2018-03-26 to 2018-05-28
UAT - Everything else | bar: 2018-02-26 to 2018-05-28
Migration
Training | bar: 2018-05-28 to 2018-06-18
| Go Live | [50 empty] | 2018-07-02: GO LIVE: Singapore
Floor Walking | bar: 2018-06-25 to 2018-07-02
Post Go Live support | bar: 2018-06-25 to 2018-08-06
| Drop 3 | [49 empty] | HongKong, Australia, NZ
| Development | [50 empty] | 2018-04-09: TBC
| SIT | [50 empty] | 2018-04-09: TBC
UAT - Migration | bar: 2018-06-11 to 2018-07-30
UAT - Everything else | bar: 2018-06-18 to 2018-08-06
Migration | bar: 2018-07-09 to 2018-08-20
| Go Live | [50 empty] | 2018-09-03: Go Live: Hong Kong, Australia, New Zealand
Floor Walking | bar: 2018-08-27 to 2018-09-03
Post Go Live support | bar: 2018-08-27 to 2018-10-15
| Drop 4 | [49 empty] | Malaysia, Vietnam, Thailand, Indonesia
| Development | [50 empty] | 2018-04-16: TBC
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-08-20 to 2018-09-17
UAT - Everything else | bar: 2018-08-27 to 2018-10-15
Migration | bar: 2018-09-24 to 2018-10-08
| Go Live | [50 empty] | 2018-11-05: Go Live: Malaysia, Vietnam, Thailand, Indonesia
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 5 | [49 empty] | Taiwan, Korea
| Development | [50 empty] | 2018-04-16: TBC
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-08-20 to 2018-09-17
UAT - Everything else | bar: 2018-08-27 to 2018-10-15
| Migration | [50 empty] | 2019-08-12: Unknown forecast for Korea migration (have assumed 2 weeks)
| Go Live | [50 empty] | 2018-12-03: Go Live: Taiwan, Korae
Floor Walking | bar: 2018-11-26 to 2018-12-03
Post Go Live support | bar: 2018-11-26 to 2019-01-14
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
UAT | bar: 2017-12-04 to 2018-03-12
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Poland, Hungary Czech, South Africa
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-28
| Drop 2 | [49 empty] | Benelux
UAT - Migration | bar: 2018-04-02 to 2018-05-28
UAT - Everything else | bar: 2018-04-09 to 2018-06-04
| Migration | [50 empty] | 2018-04-23: (TBC)
Training | bar: 2018-06-04 to 2018-06-18
| Go Live | [50 empty] | 2018-07-16: Go Live: Benelux
Floor Walking | bar: 2018-07-09 to 2018-07-16
Post Go Live support | bar: 2018-07-09 to 2018-09-03
| Drop 3 | [49 empty] | UK&I
Development
SIT
UAT - Migration | bar: 2018-06-18 to 2018-08-06
UAT - Everything else | bar: 2018-06-25 to 2018-08-13
Migration | bar: 2018-08-13 to 2018-09-17
Training | bar: 2018-09-03 to 2018-09-17
| Go Live | [50 empty] | 2018-10-08: Go Live: UK&I
Floor Walking | bar: 2018-10-01 to 2018-10-08
Post Go Live support | bar: 2018-10-01 to 2018-11-26
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
Development
SIT
UAT - Migration | bar: 2018-08-27 to 2018-09-24
UAT - Everything else | bar: 2018-09-03 to 2018-10-22
Migration | bar: 2018-10-08 to 2018-10-22
Training | bar: 2018-10-08 to 2018-10-22
| Go Live | [50 empty] | 2018-11-05: Go Live: Germany, Austria, Switzerland, Italy
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 5 | [49 empty] | France, Spain, Portugal, Nordics
Development
SIT
UAT - Migration | bar: 2018-09-24 to 2018-10-22
UAT - Everything else | bar: 2018-10-01 to 2018-11-19
Migration | bar: 2018-10-29 to 2018-11-19
Training | bar: 2018-11-05 to 2018-11-19
| Go Live | [50 empty] | 2018-12-03: Go Live: France, Spain, Portugal, Nordics
Floor Walking | bar: 2018-11-26 to 2018-12-03
Post Go Live support | bar: 2018-11-26 to 2019-01-14
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Development
SIT
UAT - Migration | bar: 2019-01-14 to 2019-02-11
UAT - Everything else | bar: 2019-01-21 to 2019-03-11
Migration | bar: 2019-03-04 to 2019-03-18
Training | bar: 2019-03-04 to 2019-03-18
| Go Live | [50 empty] | 2019-04-01: Go Live: Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Floor Walking | bar: 2019-03-25 to 2019-04-01
Post Go Live support | bar: 2019-03-25 to 2019-05-13
| Drop 1 | [49 empty] | Peru
| UAT | [50 empty] | 2017-12-11: Complete
| Migration | [50 empty] | 2017-12-11: Complete
| Go Live | [50 empty] | 2017-12-11: Complete
| Floor Walking | [50 empty] | 2017-12-11: Complete
| Post Go Live support | [50 empty] | 2017-12-11: Complete
| Drop 2 | [49 empty] | Ecuador
UAT - Migration | bar: 2018-02-26 to 2018-04-30
UAT - Everything else | bar: 2018-02-12 to 2018-04-16
Migration
Training | bar: 2018-05-07 to 2018-05-28
| Go Live | [50 empty] | 2018-06-11: Go Live: Ecuador
Floor Walking | bar: 2018-06-04 to 2018-06-11
Post Go Live support | bar: 2018-06-04 to 2018-07-23
| Drop 3 | [49 empty] | Colombia, Chile
| Development | [50 empty] | 2018-04-09: TBC
| SIT | [50 empty] | 2018-04-09: TBC
| UAT - Migration | [50 empty] | 2019-08-12: Includes ChubbNet interface (NEW)
UAT - Everything else | bar: 2018-05-21 to 2018-07-09
Migration | bar: 2018-07-09 to 2018-09-24
Training | bar: 2018-07-02 to 2018-07-23
| Go Live | [50 empty] | 2018-08-06: Go Live: Colombia, Chile; 2019-08-12: Chub Net
Floor Walking | bar: 2018-07-30 to 2018-08-06
Post Go Live support | bar: 2018-07-30 to 2018-09-17
| Drop 4 | [49 empty] | Argentina, Panamá
| Development | [50 empty] | 2018-04-16: TBC; 2019-08-12: Config must be done by mid May (Argentina nearly complete)
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-07-30 to 2018-08-27
UAT - Everything else | bar: 2018-08-06 to 2018-09-24
Migration | bar: 2018-09-03 to 2018-09-10; 2018-10-01 to 2018-10-29
Training | bar: 2018-09-03 to 2018-09-24
| Go Live | [50 empty] | 2018-10-08: Go Live: Argentina, Panamá
Floor Walking | bar: 2018-10-01 to 2018-10-08
Post Go Live support | bar: 2018-10-01 to 2018-11-19
| Drop 5 | [49 empty] | Mexico, Puerto Rico
| Development | [50 empty] | 2018-04-16: TBC; 2019-08-12: Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-07-30 to 2018-08-27
| UAT - Everything else | [50 empty] | 2019-08-12: Includes Meridian Interface (re-worked from APAC interface)
Migration | bar: 2018-09-10 to 2018-09-24; 2018-10-29 to 2018-11-05
Training | bar: 2018-10-01 to 2018-10-22
| Go Live | [50 empty] | 2018-11-05: Go Live: Mexico, Puerto Rico
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 6 | [49 empty] | Brazil
| Development | [50 empty] | 2018-04-16: TBC; 2019-08-12: Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-07-30 to 2018-08-27
UAT - Everything else | bar: 2018-08-06 to 2018-09-24
Migration | bar: 2018-09-10; 2018-10-01 to 2018-10-08
Training | bar: 2018-10-29 to 2018-11-19
| Go Live | [50 empty] | 2018-12-03: Go Live: Brazil
Floor Walking | bar: 2018-11-26 to 2018-12-03
Post Go Live support | bar: 2018-11-26 to 2019-01-14
Assumptions
Not reviewed/agreed with businss yet
Multiple countries migrating in parrallel
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes 1 week gap required from sign off of previous drop UAT to start of UAT for next drop (IT request)
Assumes Drop 4 & 5 config done by end of May

## APAC Summary fastest UAT (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | time axis 2017-12-04 to 2019-11-11
[56 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Philippines
| UAT | [50 empty] | 2017-12-11: Complete
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Philippines
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-14
| Drop 2 | [49 empty] | Singapore
UAT - Migration | bar: 2018-03-26 to 2018-05-28
UAT - Everything else | bar: 2018-02-26 to 2018-05-28
Migration
Training | bar: 2018-05-28 to 2018-06-18
| Go Live | [50 empty] | 2018-07-02: GO LIVE: Singapore
Floor Walking | bar: 2018-06-25 to 2018-07-02
Post Go Live support | bar: 2018-06-25 to 2018-08-06
| Drop 3 | [49 empty] | HongKong, Australia, NZ
| Development | [50 empty] | 2018-04-09: TBC
| SIT | [50 empty] | 2018-04-09: TBC
UAT - Migration | bar: 2018-06-11 to 2018-07-30
UAT - Everything else | bar: 2018-06-18 to 2018-08-06
Migration | bar: 2018-07-09 to 2018-08-20
Go Live | bar: 2018-08-27
Floor Walking | bar: 2018-08-27 to 2018-09-03
Post Go Live support | bar: 2018-08-27 to 2018-10-15
| Drop 4 | [49 empty] | Malaysia, Vietnam, Thailand, Indonesia
| Development | [50 empty] | 2018-04-16: TBC
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-08-20 to 2018-09-17
UAT - Everything else | bar: 2018-08-27 to 2018-10-15
Migration | bar: 2018-09-24 to 2018-10-08
Go Live | bar: 2018-10-29
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 5 | [49 empty] | Taiwan, Korea
| Development | [50 empty] | 2018-04-16: TBC
| SIT | [50 empty] | 2018-04-16: TBC
UAT - Migration | bar: 2018-08-20 to 2018-09-17
UAT - Everything else | bar: 2018-08-27 to 2018-10-15
| Migration | [50 empty] | 2019-08-12: Unknown forecast for Korea migration (have assumed 2 weeks)
Go Live | bar: 2018-11-26
Floor Walking | bar: 2018-11-26 to 2018-12-03
Post Go Live support | bar: 2018-11-26 to 2019-01-14
Drop 1 MI Signoff | bar: 2018-03-12
PCH, SA | Drop 1 GO LIVE | [50 empty] | 2018-04-09: 11th Opening
- Migration Signoff | bar: 2018-02-19
| Business Readiness - Training Team | [49 empty] | 2 | bar: 2018-03-05 to 2018-04-09
Business Readiness - SOP Creation | bar: 2018-02-19 to 2018-04-02
Business Readiness - SOP Review | bar: 2018-03-05 to 2018-04-02
Drop 1 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11 | 2018-04-09: 1; 2018-04-16: 2
| - BAU (AST) | [49 empty] | 6 | 2018-04-23: 3; 2018-04-30: 4; 2018-05-07: 5; 2018-05-14: 6; 2018-05-21: 7; 2018-05-28: 8
Drop 2 Pre-Development
- Business Engagement/ Comms | bar: 2018-02-26 to 2018-05-28
- UAT Team Selection | bar: 2018-02-26
- SME Team Selection | bar: 2018-02-26
| - Config & Interface W/S & Baseline | [49 empty] | Complete
- Review of Config/Interface (check for change) | bar: 2018-03-26
| Drop 2A & B Development | [49 empty] | Complete
| Drop 2A & B SIT | [49 empty] | Complete
Drop 2A & B Application + MI UAT (Benelux and Nordics)
UAT Training | bar: 2018-03-12 to 2018-03-19
- UAT Cycle 1 | bar: 2018-03-26 to 2018-04-02
- Fix Window
- UAT Cycle 2 | bar: 2018-04-16 to 2018-04-30
- Fix Window
- UAT Cycle 3 | bar: 2018-05-14 to 2018-05-21
Application + MI UAT sign off | bar: 2018-05-21
Drop 2A & B Migration UAT (Benelux and Nordics)
- Migration UAT Cycle 1 | bar: 2018-02-26 to 2018-03-05
- Fix Window
- Migration UAT Cycle 2 | bar: 2018-03-19 to 2018-03-26
- Fix Window
- Migration UAT Cycle 3 | bar: 2018-04-09 to 2018-04-23
- Migration Signoff | bar: 2018-04-23
2A Benelux, 2B Nordics | Drop 2A Bulk Migration (Benelux only)
- Bulk Migration Recon | bar: 2018-05-28
| Drop 2A & 2B Business Readiness - SOP Creation | [49 empty] | 1 | bar: 2018-04-23 to 2018-05-14
Drop 2A & 2B Business Readiness - SOP Review | bar: 2018-05-07 to 2018-05-14
| Drop 2A (Benelux) Business Readiness - Training | [49 empty] | 2 | bar: 2018-05-07 to 2018-05-28
Drop 2A Post Production Support
| - Go Live Activities + Floor Support (Benelux) | [49 empty] | 11 | bar: 2018-06-04 to 2018-06-11
| - BAU (AST) (Benelux) | [49 empty] | 6 | bar: 2018-06-18 to 2018-07-23
| Drop 2A GO LIVE (Benelux) | [50 empty] | 2018-06-04: 6th June go live
| Drop 2B (Nordics) Business Readiness - Training | [49 empty] | 2 | bar: 2018-07-02 to 2018-07-23
Drop 2B (Nordics) Post Production Support
| - Go Live Activities + Floor Support (Nordics) | [49 empty] | 11 | bar: 2018-07-30 to 2018-08-06
| - BAU (AST) (Nordics) | [49 empty] | 6 | bar: 2018-08-13 to 2018-09-17
| Drop 2B GO LIVE (Nordics) | [50 empty] | 2018-07-30: 1st Aug go live? (TBC)
Drop 3 and beyond Config Workshops | bar: 2018-03-05; 2018-03-26
| Drop 3 and beyond Config Completion | [49 empty] | 1 | bar: 2018-03-05 to 2018-04-09
UK & I | Drop 3 Config Completion | bar: 2018-04-16
Drop 3 Pre-development
- Business Engagement | bar: 2018-02-26 to 2018-10-22
- UAT Team Selection | bar: 2018-06-18 to 2018-07-02
- SME Team Selection | bar: 2018-06-18 to 2018-07-02
- Review of Config/Interface (check for change) | bar: 2018-07-02 to 2018-07-16
| Drop 3 Development | [50 empty] | 2018-03-19: 1; 2018-03-26: 2; 2018-04-02: 3; 2018-04-09: 4; 2018-04-16: 5; 2018-04-23: 6; 2018-04-30: 7
| Drop 3 SIT | [50 empty] | 2018-05-07: 1; 2018-05-14: 2; 2018-05-21: 3; 2018-05-28: 4
| Drop 3 Application UAT | [78 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - UAT Cycle 1 | [78 empty] | 1: 1; 2: 2
| - Fix Window | [78 empty] | 3: 3
| - UAT Cycle 2 | [78 empty] | 4: 4; 5: 5
| - Fix Window | [78 empty] | 6: 6
| - UAT Cycle 3 | [78 empty] | 7: 7; 8: 8
| Drop 3 Migration UAT | [78 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - Migration UAT Cycle 1 | [78 empty] | 1: 1; 2: 2
| - Fix Window | [78 empty] | 3: 3
| - Migration UAT Cycle 2 | [78 empty] | 4: 4; 5: 5
| - Fix Window | [78 empty] | 6: 6
| - UAT Cycle 3 | [78 empty] | 7: 7; 8: 8
Drop 3 Bulk Migration
- Bulk Migration Recon
| Drop 3 Business Readiness - Training | [49 empty] | 2
Drop 3 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11
| - BAU (AST) | [49 empty] | 6
| Drop 3 GO LIVE | [97 empty] | 31st Oct go live? (TBC)
Germany, Austria, Switzerland, Pakistan, Egypt
Drop 4 Pre-development
- Business Engagement
- UAT Team Selection | bar: 6 to 8
- SME Team Selection | bar: 6 to 8
- Review of Config/Interface
| Drop 4 Development | [70 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 4 SIT | [77 empty] | 1 | 1: 2; 2: 3; 3: 4; 4: 5
| Drop 4 Application UAT | [86 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - UAT Cycle 1 | [86 empty] | 1: 1; 2: 2
| - Fix Window | [86 empty] | 3: 3
| - UAT Cycle 2 | [86 empty] | 4: 4; 5: 5
| - Fix Window | [86 empty] | 6: 6
| - UAT Cycle 3 | [86 empty] | 7: 7; 8: 8
| Drop 4 Migration UAT | [86 empty] | 3: 1; 4: 2; 5: 3; 6: 4
| - Migration UAT Cycle 1 | [86 empty] | 3: 1; 4: 2
| - Fix Window | [86 empty] | 5: 3
| - Migration UAT Cycle 2 | [86 empty] | 6: 4
| Drop 4 Bulk Migration | [86 empty] | 7: 1; 8: 2 | 3 | 4
- Bulk Migration Recon
Drop 4 GO LIVE
| Drop 3 Business Readiness - Training | [49 empty] | 2
Drop 3 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11
| - BAU (AST) | [49 empty] | 6
Italy, Spain, Portugal
Drop 5 Pre-development
- Business Engagement
- UAT Team Selection
- SME Team Selection
- Review of Config/Interface
| Drop 5 Development | [69 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 5 SIT | [76 empty] | 1 | 2 | 3 | 4 | 5
| Drop 5 Application UAT | [103 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| - UAT Cycle 1 | [103 empty] | 1 | 2
| - Fix Window | [105 empty] | 3
| - UAT Cycle 2 | [106 empty] | 4 | 5
| - Fix Window | [108 empty] | 6
| - UAT Cycle 3 | [109 empty] | 7
| Drop 5 Migration UAT | [105 empty] | 1 | 2 | 3 | 4
| - Migration UAT Cycle 1 | [105 empty] | 1 | 2
| - Fix Window | [107 empty] | 3
| - Migration UAT Cycle 2 | [108 empty] | 4
| Drop 5 Bulk Migration | [109 empty] | 1
- Bulk Migration Recon
Drop 5 GO LIVE
Drop 5 Business Readiness - Training
Drop 5 Post Production Support
- Go Live Activities + Floor Support
- BAU (AST)
France, Pakistan, Egypt, Turkey, Dubai, Bahrain, Russia
Drop 6 Pre-development
- Business Engagement
- UAT Team Selection
- SME Team Selection
- Review of Config/Interface
| Drop 6 Development | [69 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 6 SIT | [76 empty] | 1 | 2 | 3 | 4 | 5
Drop 6 Application UAT
- UAT Cycle 1
- Fix Window
- UAT Cycle 2
- Fix Window
- UAT Cycle 3
Drop 6 Migration UAT
- Migration UAT Cycle 1
- Fix Window
- Migration UAT Cycle 2
| Drop 6 Bulk Migration | [119 empty] | 3 | 4 | 5 | 6 | 7
- Bulk Migration Recon
Drop 6 GO LIVE
Drop 6 Business Readiness - Training
Drop 6 Post Production Support
- Go Live Activities + Floor Support
- BAU (AST)
Assumptions
Not reviewed/agreed with businss yet
Multiple countries migrating in parrallel
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes 1 week gap required from sign off of previous drop UAT to start of UAT for next drop (IT request)
Assumes Drop 4 & 5 config done by end of May

## LATAM Summary fastest UAT (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | Who
[56 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul | [5 empty] | Interfaces in Scope
| Drop 1 | [49 empty] | Peru
| UAT | [51 empty] | Complete
| Migration | [51 empty] | Complete
| Go Live | [51 empty] | Complete
| Floor Walking | [51 empty] | Complete
| Post Go Live support | [51 empty] | Complete
| Drop 2 | [49 empty] | Ecuador and Ecuador Life
UAT - Migration
UAT - Everything else
Migration
Training
Go Live
Floor Walking
Post Go Live support
| Drop 3 | [49 empty] | Colombia, Chile, Chile Life
| Development | [68 empty] | TBC
| SIT | [68 empty] | TBC
| UAT - Migration | [138 empty] | Includes ChubbNet interface (NEW)
UAT - Everything else
| Migration | [81 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Training
| Go Live | [138 empty] | Chub Net
Floor Walking
Post Go Live support
| Drop 4 | [49 empty] | Argentina, Panamá
| Development | [69 empty] | TBC | [68 empty] | Config must be done by mid May (Argentina nearly complete)
| SIT | [69 empty] | TBC
UAT - Migration
UAT - Everything else
| Migration | [93 empty] | 1 | 1 | 1 | 1 | 1
Training
Go Live
Floor Walking
Post Go Live support
| Drop 5 | [49 empty] | Mexico, Puerto Rico
| Development | [69 empty] | TBC | [68 empty] | Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| SIT | [69 empty] | TBC
UAT - Migration
| UAT - Everything else | [138 empty] | Includes Meridian Interface (re-worked from APAC interface)
| Migration | [90 empty] | 1 | [6 empty] | 1 | 1
Training
Go Live
Floor Walking
Post Go Live support
Drop 1 MI Signoff
PCH, SA | Drop 1 GO LIVE | [68 empty] | 11th Opening
- Migration Signoff
| Business Readiness - Training Team | [49 empty] | 2
Business Readiness - SOP Creation
Business Readiness - SOP Review
Drop 1 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11 | [18 empty] | 1 | 2
| - BAU (AST) | [49 empty] | 6 | [20 empty] | 3 | 4 | 5 | 6 | 7 | 8
Drop 2 Pre-Development
- Business Engagement/ Comms
- UAT Team Selection
- SME Team Selection
| - Config & Interface W/S & Baseline | [49 empty] | Complete
- Review of Config/Interface (check for change)
| Drop 2A & B Development | [49 empty] | Complete
| Drop 2A & B SIT | [49 empty] | Complete
Drop 2A & B Application + MI UAT (Benelux and Nordics)
UAT Training
- UAT Cycle 1
- Fix Window
- UAT Cycle 2
- Fix Window
- UAT Cycle 3
Application + MI UAT sign off
Drop 2A & B Migration UAT (Benelux and Nordics)
- Migration UAT Cycle 1
- Fix Window
- Migration UAT Cycle 2
- Fix Window
- Migration UAT Cycle 3
- Migration Signoff
2A Benelux, 2B Nordics | Drop 2A Bulk Migration (Benelux only)
- Bulk Migration Recon
| Drop 2A & 2B Business Readiness - SOP Creation | [49 empty] | 1
Drop 2A & 2B Business Readiness - SOP Review
| Drop 2A (Benelux) Business Readiness - Training | [49 empty] | 2
Drop 2A Post Production Support
| - Go Live Activities + Floor Support (Benelux) | [49 empty] | 11
| - BAU (AST) (Benelux) | [49 empty] | 6
| Drop 2A GO LIVE (Benelux) | [76 empty] | 6th June go live
| Drop 2B (Nordics) Business Readiness - Training | [49 empty] | 2
Drop 2B (Nordics) Post Production Support
| - Go Live Activities + Floor Support (Nordics) | [49 empty] | 11
| - BAU (AST) (Nordics) | [49 empty] | 6
| Drop 2B GO LIVE (Nordics) | [84 empty] | 1st Aug go live? (TBC)
Drop 3 and beyond Config Workshops
| Drop 3 and beyond Config Completion | [49 empty] | 1
UK & I | Drop 3 Config Completion
Drop 3 Pre-development
- Business Engagement
- UAT Team Selection
- SME Team Selection
- Review of Config/Interface (check for change)
| Drop 3 Development | [65 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 3 SIT | [72 empty] | 1 | 2 | 3 | 4
| Drop 3 Application UAT | [78 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - UAT Cycle 1 | [78 empty] | 1: 1; 2: 2
| - Fix Window | [78 empty] | 3: 3
| - UAT Cycle 2 | [78 empty] | 4: 4; 5: 5
| - Fix Window | [78 empty] | 6: 6
| - UAT Cycle 3 | [78 empty] | 7: 7; 8: 8
| Drop 3 Migration UAT | [78 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - Migration UAT Cycle 1 | [78 empty] | 1: 1; 2: 2
| - Fix Window | [78 empty] | 3: 3
| - Migration UAT Cycle 2 | [78 empty] | 4: 4; 5: 5
| - Fix Window | [78 empty] | 6: 6
| - UAT Cycle 3 | [78 empty] | 7: 7; 8: 8
Drop 3 Bulk Migration
- Bulk Migration Recon
| Drop 3 Business Readiness - Training | [49 empty] | 2
Drop 3 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11
| - BAU (AST) | [49 empty] | 6
| Drop 3 GO LIVE | [96 empty] | 31st Oct go live? (TBC)
Germany, Austria, Switzerland, Pakistan, Egypt
Drop 4 Pre-development
- Business Engagement
- UAT Team Selection | bar: 6 to 8
- SME Team Selection | bar: 6 to 8
- Review of Config/Interface
| Drop 4 Development | [70 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 4 SIT | [77 empty] | 1 | 1: 2; 2: 3; 3: 4; 4: 5
| Drop 4 Application UAT | [86 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8
| - UAT Cycle 1 | [86 empty] | 2
| - Fix Window | [87 empty] | 3
| - UAT Cycle 2 | [88 empty] | 4 | 5
| - Fix Window | [90 empty] | 6
| - UAT Cycle 3 | [91 empty] | 7 | 8
| Drop 4 Migration UAT | [87 empty] | 1 | 2 | 3 | 4
| - Migration UAT Cycle 1 | [87 empty] | 1 | 2
| - Fix Window | [89 empty] | 3
| - Migration UAT Cycle 2 | [90 empty] | 4
| Drop 4 Bulk Migration | [91 empty] | 1 | 2 | 3 | 4
- Bulk Migration Recon
| Drop 4 GO LIVE | [100 empty] | 28th Nov go live
| Drop 3 Business Readiness - Training | [49 empty] | 2
Drop 3 Post Production Support
| - Go Live Activities + Floor Support | [49 empty] | 11
| - BAU (AST) | [49 empty] | 6
Italy, Spain, Portugal
Drop 5 Pre-development
- Business Engagement
- UAT Team Selection
- SME Team Selection
- Review of Config/Interface
| Drop 5 Development | [69 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 5 SIT | [76 empty] | 1 | 2 | 1: 3; 2: 4; 3: 5
| Drop 5 Application UAT | [103 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| - UAT Cycle 1 | [103 empty] | 1 | 2
| - Fix Window | [105 empty] | 3
| - UAT Cycle 2 | [106 empty] | 4 | 5
| - Fix Window | [108 empty] | 6
| - UAT Cycle 3 | [109 empty] | 7
| Drop 5 Migration UAT | [105 empty] | 1 | 2 | 3 | 4
| - Migration UAT Cycle 1 | [105 empty] | 1 | 2
| - Fix Window | [107 empty] | 3
| - Migration UAT Cycle 2 | [108 empty] | 4
| Drop 5 Bulk Migration | [109 empty] | 1
- Bulk Migration Recon
Drop 5 GO LIVE
Drop 5 Business Readiness - Training
Drop 5 Post Production Support
- Go Live Activities + Floor Support
- BAU (AST)
France, Pakistan, Egypt, Turkey, Dubai, Bahrain, Russia
Drop 6 Pre-development
- Business Engagement
- UAT Team Selection
- SME Team Selection
- Review of Config/Interface
| Drop 6 Development | [69 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Drop 6 SIT | [76 empty] | 1 | 2 | 1: 3; 2: 4; 3: 5
Drop 6 Application UAT
- UAT Cycle 1
- Fix Window
- UAT Cycle 2
- Fix Window
- UAT Cycle 3
Drop 6 Migration UAT
- Migration UAT Cycle 1
- Fix Window
- Migration UAT Cycle 2
| Drop 6 Bulk Migration | [119 empty] | 3 | 4 | 5 | 6 | 7
- Bulk Migration Recon
Drop 6 GO LIVE
Drop 6 Business Readiness - Training
Drop 6 Post Production Support
- Go Live Activities + Floor Support
- BAU (AST)
| Drop 6 | [49 empty] | Brasil
| Development | [69 empty] | TBC | [68 empty] | Config done by mid May (do dev of Drop 4, 5 & 6 together?)
| SIT | [69 empty] | TBC
UAT - Migration | bar: 7 to 8
UAT - Everything else | bar: 8
| Migration | [90 empty] | 1
Training
Go Live
Floor Walking
Post Go Live support
| Drop 1 | [49 empty] | Philippines
| UAT | [51 empty] | Complete
| Migration | [65 empty] | (TBC)
| Go Live | [69 empty] | GO LIVE: Philippines
Floor Walking
Post Go Live support
| Drop 2 | [49 empty] | Singapore
UAT - Migration
UAT - Everything else
Migration
Training | bar: 1
| Go Live | [78 empty] | 3: GO LIVE: Singapore
Floor Walking | bar: 2 to 3
Post Go Live support | bar: 2 to 8
| Drop 3 | [49 empty] | HongKong, Australia, NZ
| Development | [68 empty] | TBC
| SIT | [68 empty] | TBC
UAT - Migration | bar: 1 to 7
UAT - Everything else
| Migration | [86 empty] | 1 | 1 | bar: 4 to 8
Go Live
Floor Walking
Post Go Live support
| Drop 4 | [49 empty] | Malaysia, Vietnam, Thailand, Indonesia
| Development | [69 empty] | TBC
| SIT | [69 empty] | TBC
UAT - Migration
UAT - Everything else
Migration
Go Live
Floor Walking
Post Go Live support
| Drop 5 | [49 empty] | Taiwan, Korea
| Development | [69 empty] | TBC
| SIT | [69 empty] | TBC
UAT - Migration
UAT - Everything else
| Migration | [138 empty] | Unknown forecast for Korea migration (have assumed 2 weeks)
Go Live
Floor Walking
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
UAT
| Migration | [65 empty] | (TBC)
| Go Live | [69 empty] | GO LIVE: Poland, Hungary Czech, South Africa
Floor Walking
Post Go Live support
| Drop 2 | [49 empty] | Benelux
UAT - Migration
UAT - Everything else
| Migration | [70 empty] | (TBC)
Training | bar: 1
Go Live | bar: 4
Floor Walking | bar: 4 to 5
Post Go Live support | bar: 4 to 8
| Drop 3 | [49 empty] | UK&I
Development
SIT
UAT - Migration
UAT - Everything else | bar: 2 to 8
Migration
Training
Go Live
Floor Walking
Post Go Live support
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
Development
SIT
UAT - Migration
UAT - Everything else
Migration
Training
Go Live
Floor Walking
Post Go Live support
| Drop 5 | [49 empty] | France, Spain, Portugal, Nordics
Development
SIT
UAT - Migration
UAT - Everything else
Migration
Training
Go Live
Floor Walking
Post Go Live support
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Development
SIT
UAT - Migration
UAT - Everything else
Migration
Training
Go Live
Floor Walking
Post Go Live support
Assumptions
Based on LATAM plan with slip in Drop 2 factored in
Not reviewed by LATAM yet
Countries migration in parrallel
Improved migration timelines
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes can comnplete config for Drop 4, 5 & 6 by end of May
Assumes can run Brasil, Mexico and Puerto Rico UAT at same time

## EMEA Summary fastest UAT (2) (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | time axis 2017-12-04 to 2019-11-11
[56 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
UAT | bar: 2017-12-04 to 2018-03-12
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Poland, Hungary Czech, South Africa
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-28
| Drop 2 | [49 empty] | Benelux
UAT - Migration | bar: 2018-04-02 to 2018-06-04
UAT - Everything else | bar: 2018-04-09 to 2018-06-04
| Migration | [50 empty] | 2018-04-23: (TBC)
Training | bar: 2018-06-04 to 2018-06-18
Go Live | bar: 2018-06-25
Floor Walking | bar: 2018-06-25 to 2018-07-02
Post Go Live support | bar: 2018-06-25 to 2018-08-13
| Drop 3 | [49 empty] | UK&I
Development
SIT
UAT - Migration | bar: 2018-06-18 to 2018-08-06
UAT - Everything else | bar: 2018-06-25 to 2018-08-13
Migration | bar: 2018-08-13 to 2018-09-17
Training | bar: 2018-09-03 to 2018-09-17
Go Live | bar: 2018-09-24
Floor Walking | bar: 2018-09-24 to 2018-10-01
Post Go Live support | bar: 2018-09-24 to 2018-11-12
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
Development
SIT
UAT - Migration | bar: 2018-07-30 to 2018-08-27
UAT - Everything else | bar: 2018-08-06 to 2018-09-24
Migration | bar: 2018-09-10 to 2018-09-24
Training | bar: 2018-09-10 to 2018-09-24
Go Live | bar: 2018-10-01
Floor Walking | bar: 2018-10-01 to 2018-10-08
Post Go Live support | bar: 2018-10-01 to 2018-11-19
| Drop 5 | [49 empty] | France, Spain, Portugal, Nordics
Development
SIT
UAT - Migration | bar: 2018-08-27 to 2018-09-24
UAT - Everything else | bar: 2018-09-03 to 2018-10-22
Migration | bar: 2018-10-01 to 2018-10-22
Training | bar: 2018-10-08 to 2018-10-22
Go Live | bar: 2018-10-29
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Development
SIT
UAT - Migration | bar: 2019-01-14 to 2019-02-11
UAT - Everything else | bar: 2019-01-21 to 2019-03-11
Migration | bar: 2019-03-04 to 2019-03-18
Training | bar: 2019-03-04 to 2019-03-18
Go Live | bar: 2019-03-25
Floor Walking | bar: 2019-03-25 to 2019-04-01
Post Go Live support | bar: 2019-03-25 to 2019-05-13
Overlapping activities
| Migration UAT | [50 empty] | 2018-07-30: 2; 2018-08-06: 2; 2018-08-27: 2
| Functional UAT | [50 empty] | 2018-08-06: 2; 2018-09-03: 2; 2018-09-10: 2; 2018-09-17: 2; 2018-09-24: 2
| Training | [50 empty] | 2018-09-10: 2; 2018-09-17: 2
| Floor walking | [50 empty] | 2018-10-01: 2
| Post Go Live Support | [50 empty] | 2018-10-01: 2; 2018-10-08: 2; 2018-10-15: 2; 2018-10-22: 2; 2018-10-29: 3; 2018-11-05: 3; 2018-11-12: 3; 2018-11-19: 2
Assumptions
Assumes IT can supply a second UAT environment for Drop 4 UAT
Not reviewed/agreed with business yet
Multiple countries migrating in parallel
Periods of overlap of UAT, Training, Floorwalking and Post go live support
After drop 3 migration UAT drops to 5 weeks
Assumes 1 week gap required from sign off of previous drop UAT to start of UAT for next drop (IT request)
Assumes Drop 4,5&6 config done by end of May
Needs workshop approach for Config for drops 4-6

## EMEA Summary fastest UAT (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | time axis 2017-12-04 to 2019-11-11
[56 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
UAT | bar: 2017-12-04 to 2018-03-12
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Poland, Hungary Czech, South Africa
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-28
| Drop 2a | [49 empty] | Benelux
UAT - Migration | bar: 2018-04-02 to 2018-06-04
UAT - Everything else | bar: 2018-04-09 to 2018-06-04
| Migration | [50 empty] | 2018-04-23: (TBC)
Go Live
Floor Walking
Post Go Live support
| Drop 2b | [49 empty] | Nordics
UAT - Migration | bar: 2018-04-02 to 2018-06-04
UAT - Everything else | bar: 2018-04-09 to 2018-06-04
| Migration | [50 empty] | 2018-04-23: (TBC)
Go Live
Floor Walking
Post Go Live support
| Drop 3 | [49 empty] | UK&I
Development
SIT
UAT - Migration | bar: 2018-06-18 to 2018-08-06
UAT - Everything else | bar: 2018-06-25 to 2018-08-13
Migration | bar: 2018-07-09 to 2018-09-24
Go Live | bar: 2018-09-24
Floor Walking | bar: 2018-09-24
Post Go Live support | bar: 2018-09-24
| Drop 4 | [49 empty] | Germany, Austria, Switzerland,
Development
SIT
UAT - Migration | bar: 2018-07-30 to 2018-08-27
UAT - Everything else | bar: 2018-08-06 to 2018-09-03
Migration | bar: 2018-10-01 to 2018-10-29
| Go Live | [50 empty] | 2018-10-29: 2
| Floor Walking | [50 empty] | 2018-10-29: 3
| Post Go Live support | [50 empty] | 2018-10-29: 4
| Drop 5 | [49 empty] | France, Italy, Spain, Portugal
Development
SIT
UAT - Migration | bar: 2018-08-27 to 2018-09-24
UAT - Everything else | bar: 2018-09-03 to 2018-10-22
Migration | bar: 2018-09-17 to 2018-11-12
Go Live
Floor Walking
Post Go Live support
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Development
SIT
UAT - Migration | bar: 2019-01-14 to 2019-02-11
UAT - Everything else | bar: 2019-01-21 to 2019-03-11
Migration
Go Live
Floor Walking
Post Go Live support
Assumptions
Not reviewed/agreed with businss yet
Multiple countries migrating in parrallel
3 business project teams (1 team running UAT, 2 teams leapfrogging supporting the go live activities)
Migration UAT is primarily performed by in ountry SMEs
After drop 3 migration UAT drops to 5 weeks
Assumes 1 week gap required from sign off of previous drop UAT to start of UAT for next drop (IT request)
Assumes Drop 4 config done by end of May for Drop 4
Assumes Drop 4 config done by end of June for Drop 5&6
Needs workshop approach for Config for drops 4-6
Assumes can do UAT for drop 5 & 6 at same time (but not necessarily go liveat same time)

## EMEA Summary fastest UAT - v1.2 (hidden)
| Milestone | Resource | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | Countries | time axis 2017-12-04 to 2019-11-11
| Revised plan based on Nick's feedback | [50 empty] | 2018-01-01: Q1; 2018-04-02: Q2; 2018-07-02: Q3; 2018-10-01: Q4
[52 empty] | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| Drop 1 | [49 empty] | Poland, Hungary Czech, South Africa
UAT | bar: 2017-12-04 to 2018-03-12
| Migration | [50 empty] | 2018-03-19: (TBC)
| Go Live | [50 empty] | 2018-04-16: GO LIVE: Poland, Hungary Czech, South Africa
Floor Walking | bar: 2018-04-09 to 2018-04-16
Post Go Live support | bar: 2018-04-09 to 2018-05-28
| Drop 2 | [49 empty] | Benelux
UAT - Migration | bar: 2018-04-02 to 2018-05-28
UAT - Everything else | bar: 2018-04-09 to 2018-06-04
| Migration | [50 empty] | 2018-04-23: (TBC)
Training | bar: 2018-06-04 to 2018-06-18
Go Live | bar: 2018-07-09
Floor Walking | bar: 2018-07-09 to 2018-07-16
Post Go Live support | bar: 2018-07-09 to 2018-09-03
| Drop 3 | [49 empty] | UK&I
Development
SIT
UAT - Migration | bar: 2018-06-18 to 2018-08-06
UAT - Everything else | bar: 2018-06-25 to 2018-08-13
Migration | bar: 2018-08-13 to 2018-09-17
Training | bar: 2018-09-03 to 2018-09-17
Go Live | bar: 2018-10-01
Floor Walking | bar: 2018-10-01 to 2018-10-08
Post Go Live support | bar: 2018-10-01 to 2018-11-26
| Drop 4 | [49 empty] | Germany, Austria, Switzerland, Italy
Development
SIT
UAT - Migration | bar: 2018-08-27 to 2018-09-24
UAT - Everything else | bar: 2018-09-03 to 2018-10-22
Migration | bar: 2018-10-08 to 2018-10-22
Training | bar: 2018-10-08 to 2018-10-22
Go Live | bar: 2018-10-29
Floor Walking | bar: 2018-10-29 to 2018-11-05
Post Go Live support | bar: 2018-10-29 to 2018-12-17
| Drop 5 | [49 empty] | France, Spain, Portugal, Nordics
Development
SIT
UAT - Migration | bar: 2018-09-24 to 2018-10-22
UAT - Everything else | bar: 2018-10-01 to 2018-11-19
Migration | bar: 2018-10-29 to 2018-11-19
Training | bar: 2018-11-05 to 2018-11-19
Go Live | bar: 2018-11-26
Floor Walking | bar: 2018-11-26 to 2018-12-03
Post Go Live support | bar: 2018-11-26 to 2019-01-14
| Drop 6 | [49 empty] | Turkey, Dubai, Bahrain, Russia, Pakistan, Egypt
Development
SIT
UAT - Migration | bar: 2019-01-14 to 2019-02-11
UAT - Everything else | bar: 2019-01-21 to 2019-03-11
Migration | bar: 2019-03-04 to 2019-03-18
Training | bar: 2019-03-04 to 2019-03-18
Go Live | bar: 2019-03-25
Floor Walking | bar: 2019-03-25 to 2019-04-01
Post Go Live support | bar: 2019-03-25 to 2019-05-13
Overlapping activities
| Migration UAT | [50 empty] | 2018-07-30: 2; 2018-08-06: 2; 2018-08-27: 2
| Functional UAT | [50 empty] | 2018-08-06: 2; 2018-09-03: 2; 2018-09-10: 2; 2018-09-17: 2; 2018-09-24: 2
| Training | [50 empty] | 2018-09-10: 2; 2018-09-17: 2
| Floor walking | [50 empty] | 2018-10-01: 2
| Post Go Live Support | [50 empty] | 2018-10-01: 2; 2018-10-08: 2; 2018-10-15: 2; 2018-10-22: 2; 2018-10-29: 3; 2018-11-05: 3; 2018-11-12: 3; 2018-11-19: 2
Assumptions
Assumes IT can supply a second UAT environment for Drop 4 UAT
Not reviewed/agreed with business yet
Multiple countries migrating in parallel
Periods of overlap of UAT, Training, Floorwalking and Post go live support
After drop 3 migration UAT drops to 5 weeks
Assumes 1 week gap required from sign off of previous drop UAT to start of UAT for next drop (IT request)
Assumes Drop 4,5&6 config done by end of May
Needs workshop approach for Config for drops 4-6

## Migration forecasts (hidden)
|  | Original View | 20% performance improvement | 20% improvement + 3 years | 20% improvement + 5 years | 20% improvement + 7 years | Region | Country | Entities Count | No. of Days (Approx.) | All Data | 3 years only | 5 years only | 7 years only
Region | Country | Weeks | 0.8 | 0.7 | 0.75 | 0.8 | [5 empty] | 0.7 | 0.75 | 0.8
EMEA | UK | 13.67 | 10.93 | 7.65 | 8.2 | 8.75 | LATAM | Chile | 7279108 | 8 | 1.07 | 0.75 | 0.8 | 0.85
EMEA | Ireland | 1.17 | 0.93 | 0.65 | 0.7 | 0.75 | LATAM | Chile Life | 270373 | 0.5 | 0.07 | 0.05 | 0.05 | 0.05
EMEA | Austria | 0.33 | 0.27 | 0.19 | 0.2 | 0.21 | LATAM | Argentina | 14822819 | 15 | 2 | 1.4 | 1.5 | 1.6
EMEA | Germany | 4.33 | 3.47 | 2.43 | 2.6 | 2.77 | LATAM | Colombia | 15412055 | 16 | 2.13 | 1.49 | 1.6 | 1.71
EMEA | Switzerland | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 | LATAM | Mexico | 21312163 | 22 | 2.93 | 2.05 | 2.2 | 2.35
EMEA | Pakistan | 0.08 | 0.07 | 0.05 | 0.05 | 0.05 | LATAM | Puerto Rico | 11032712 | 12 | 1.6 | 1.12 | 1.2 | 1.28
EMEA | Egypt | 0.08 | 0.07 | 0.05 | 0.05 | 0.05 | LATAM | Brazil | 35835500 | 37 | 4.93 | 3.45 | 3.7 | 3.95
EMEA | Italy | 5.67 | 4.53 | 3.17 | 3.4 | 3.63 | LATAM | Brazil Life | 255320 | 0.5 | 0.07 | 0.05 | 0.05 | 0.05
EMEA | Spain | 4 | 3.2 | 2.24 | 2.4 | 2.56 |  | Ecuador
EMEA | Portugal | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 |  | Ecuador Life
EMEA | France | 9.17 | 7.33 | 5.13 | 5.5 | 5.87
EMEA | Russia | 0.33 | 0.27 | 0.19 | 0.2 | 0.21
EMEA | Turkey | 0.33 | 0.27 | 0.19 | 0.2 | 0.21
EMEA | Bahrain | 0.5 | 0.4 | 0.28 | 0.3 | 0.32 | Region | Country | Entities Count | No. of Days (Approx.) | Weeks | 0.8 | 0.7 | 0.75 | 0.8
[7 empty] | APAC | Australia | 44071459 | 45 | 7.5 | 6 | 4.2 | 4.5 | 4.8
[7 empty] | APAC | New Zealand | 10312178 | 11 | 1.8 | 1.47 | 1.03 | 1.1 | 1.17
[7 empty] | APAC | Hong Kong | 15953449 | 16 | 2.7 | 2.13 | 1.49 | 1.6 | 1.71
[7 empty] | APAC | Vietnam | 9962614 | 10 | 1.7 | 1.33 | 0.93 | 1 | 1.07
[7 empty] | APAC | Malaysia | 34803393 | 35 | 5.8 | 4.67 | 3.27 | 3.5 | 3.73
[7 empty] | APAC | Indonesia | 25932879 | 26 | 4.3 | 3.47 | 2.43 | 2.6 | 2.77
|  | 4.335 |  |  |  |  | APAC | Thailand | 37274170 | 38 | 6.3 | 5.07 | 3.55 | 3.8 | 4.05
[7 empty] | APAC | Taiwan | 10128924 | 11 | 1.8 | 1.47 | 1.03 | 1.1 | 1.17
[7 empty] | APAC | Korea | ??? | ??? | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Data Activites Runbook
Data Services - Run Book Per Country
Region
# | Phase | Activity | APAC | EMEA | LATAM | Team | Dependency | Estimated Effort /Country (Days) | Can be automated? | Automation Status? | After Automation
1 | Init | Clean test data from Dev | 1 | 1 | 1 | Data Services Team |  | 0.5 | No
2 | Init | Load from Classic Apollo to WV | 1 | 1 | 1 | Data Services Team |  | 3 | Yes | Completed - team are using it | 1
3 | Init | BA config sheet load | 1 | 1 | 1 | Data Services Team | BA sheet to be ready | 7 | Yes | Dev in progress. | 1
4 | Init | Translation code - English | 1 | 1 | 1 | Data Services Team |  | 1 | Yes | Dev in progress. | 0.25
5 | Init | Mapping tables | 1 | 1 | 1 | Data Services Team |  | 2 | Yes | Dev in progress. | 0.25
| Init | Identity Column check | 1 | 1 | 1 | Data Services Team |  | 0.5 | No
6 | Init | Translations for other languages | 1 | 1 | 1 | Data Services Team | Translations should be ready | 1 | No
7 | Init | Load data from Genius | 0 | 1 | 0 | Data Services Team | Genius Data should be available | 0.5 | No
8 | Init | Add changes or missing data from BA in the config sheet if any | 1 | 1 | 1 | Data Services Team |  | 3 | No
9 | SIT | Prepare consolidated script and RN to load data in SIT | 1 | 1 | 1 | Data Services Team |  | 1
10 | SIT | Add changes or missing data from BA in the config sheet if any | 1 | 1 | 1 | Data Services Team |  | 1
11 | SIT | Collect all the data changes as part of SIT which is done by Data team, Security Team, Ingestion Team, Integration Team. | 1 | 1 | 1 | Data Services Team |  | 1
12 | UAT | Prepare consolidated script and RN to load data in SIT | 1 | 1 | 1 | Data Services Team |  | 1
13 | UAT | Collect all the data changes as part of SIT which is done by Data team, Security Team, Ingestion Team, Integration Team. | 1 | 1 | 1 | Data Services Team |  | 1
14 | UAT | Add changes or missing data from BA in the config sheet if any | 1 | 1 | 1 | Data Services Team |  | 1
15 | PRD | Sign-off from migration team and Integration team (MI) | 1 | 1 | 1 | Data Services Team |  | 0
16 | PRD | Compare Classic Apollo DB and prepare delta script | 1 | 1 | 1 | Data Services Team |  | 2
17 | PRD | Consolidate all the SIT and UAT phase changes | 1 | 1 | 1 | Data Services Team |  | 0.5
18 | PRD | DDL Changes made as part of any CR | 1 | 1 | 1 | Data Services Team |  | 0.5
19 | PRD | Provide classic Delta data to BA to update config sheet in case mapping is required. | 1 | 1 | 1 | Data Services Team |  | 0.5
20 | PRD | Load data from the updated config sheet, if any. | 1 | 1 | 1 | Data Services Team |  | 0.5
21 | PRD | Prepare RN for prod | 1 | 1 | 1 | Data Services Team |  | 1
22 | PRD | Load the scripts to Pre-Prod DB | 1 | 1 | 1 | Data Services Team |  | 1
23 | PRD | Compare loaded data with UAT Database | 1 | 1 | 1 | Data Services Team |  | 1
24 | PRD | Review RN and scripts | 1 | 1 | 1 | Data Services Team |  | 1

## Ingestion Activites Runbook
Ingestion Run Book Per Country
Ingestion Interfaces APAC: Email, PBE, ACRS, Scanning (Datacap)
Ingestion EMEA: ACL , Ignite, PBE,Scanning (DataCap)
Ingestion LATAM: Formspath ,Email,Scanning (DataCap)
Region
# | Phase | Activity | APAC | EMEA | LATAM | Team | Dependency | Estimated Effort/Country (Days)
1 | Dev | Configure/deploy the new instance of ICC,BR,PP,Datacap for every Drop | 1 | 1 | 1 | Ingestion Team |  | 1
2 | Init | Prepare script and Load EmailBroker Routing table data based on BA configuration data | 1 | 1 | 1 | Ingestion Team | BA sheet to be ready and dependancy on data team(for LOB,team and public WB ) | 2
3 | SIT | Configure/deploy the new instance of ICC,BR,PP,Datacap for new drops | 1 | 1 | 1 | Ingestion Team |  | 1
4 | SIT | Prepare consolidated script(Email Broker) and RN to load data in SIT | 1 | 1 | 1 | Ingestion Team |  | 2
5 | SIT | Create SIT mail boxes for new countries and SMTP routing for the drop | 1 | 1 | 1 | Ingestion Team | Messaging Team has to create new email boxes and do te SMTP routing | 1
6 | UAT | Redeploy the ICC,BR,PP,Datacap to promote SIT changes UAT | 1 | 1 | 1 | Ingestion Team |  | 1
7 | UAT | Prepare consolidated script(Email Broker) and RN to load data in UAT | 1 | 1 | 1 | Ingestion Team |  | 2
8 | UAT | Datacap- Get list of UAT Scan Stations and Scan users, provide access to datacap application. Support for UAT Scanning Workstation set up. | 1 | 1 | 1 | Ingestion Team |  | 2
9 | UAT | Create UAT mail boxes for new countries and SMTP routing for the drop | 1 | 1 | 1 | Ingestion Team | Messaging Team has to create new email boxes and do te SMTP routing | 1
10 | PRD | Consolidate all the SIT and UAT phase changes | 1 | 1 | 1 | Ingestion Team |  | 2
11 | PRD | Prepare RN for prod for all ingestion components | 1 | 1 | 1 | Ingestion Team |  | 3
12 | PRD | Review RN and Build for all ingestion components | 1 | 1 | 1 | Ingestion Team |  | 2
13 | PRD | Datacap- Get list of Prod Scan Stations and Scan users, provide access to datacap application. Support for Prod Scanning Workstation set up. | 1 | 1 | 1 | Ingestion Team |  | 1
14 | PRD | Datacap EMEA CLUW Scanning - Initial Prod Deployment (Only for Drop2) | 0 | 1 | 0 | Ingestion Team |  | 1
15 | PRD | SMTP routing for the Production mail boxes has to be done during blockout before stopping the Classic Apollo | 1 | 1 | 1 | Ingestion Team | Messaging Team has to do the SMTP routing | 1
16 | SIT | deploy PBE config files for new countries - Prepare RN and Build | 1 | 1 | 0 | Ingestion Team |  | 0.5
17 | UAT | deploy PBE config files for new countries - Prepare RN and Build | 1 | 1 | 0 | Ingestion Team |  | 0.5
18 | PRD | deploy PBE config files for new countries - Prepare RN and Build | 1 | 1 | 0 | Ingestion Team |  | 0.5
19 | SIT | Setup Country Specific Robot jobs for PBE, ACL , FormsPath | 1 | 1 | 1 | Ingestion Team |  | 0.5
20 | UAT | Setup Country Specific Robot jobs for PBE, ACL , FormsPath | 1 | 1 | 1 | Ingestion Team |  | 0.5
21 | PRD | Setup Country Specific Robot jobs for PBE, ACL , FormsPath | 1 | 1 | 1 | Ingestion Team |  | 0.5
22 | SIT | Create/Update Robot job to run the new instance of PP(for every Drop) | 1 | 1 | 1 | Ingestion Team |  | 0.5

## Integration Activites Runbook
Ingestion Run Book
Run Book Applicable for APAC : Meridian, ACRS, S6, ACC |  |  | * Genius not included, as the reference and config and functionality needs to be merged from EMEA to APAC as new
Run Book Applicable for EMEA : Genius, IGNITE, S6, ACC, GenNext
Run Book Applicable for LATAM : SIS, PEGA |  |  | * Meridian not included, as the reference and config and functionality needs to be Merged from APAC to LATAM as new
New interfaces are not included : GenNext2, ChubbNet, KORAH
Region
# | Phase | Activity | APAC | EMEA | LATAM | Team | Dependency | Estimated Effort/Country (Days) | Dependencies
1 | Init | Create new Genius/Meridian environment for Dev/SIT/ UAT to Environment team. | 1 | 1 | 1 | Integration Team | Genius team | 5 | Other team dependency
2 | SIT | Raise request to create country specific directory in UNIX server. The request needs to be raised to RS600 team. | 1 | 1 | 1 | RS6000 |  | 3 | Other team dependency
3 | SIT | Genius/Meridian team has to share the SFTP key to RS600 team to enable SFTP transfer between AS400 server and UNIX server | 1 | 1 | 1 | Genius/Meridian team |  | 3 | Other team dependency
4 | SIT | Raise the request to set up robot jobs | 1 | 1 | 1 | AS400 team |  | 2
5 | SIT | Prepare the RN to deploy the Directories and BAT scripts to UNIX server and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 6
6 | SIT | Work with Genius team to setup Genius / Meridian data area | 1 | 1 | 1 | Integration Team |  | 2
7 | SIT | Get the mapping between Loss Group/Casue of Loss from Genisu team for the country and share to data team to populate it. | 1 | 1 | 1 | Data Team |  | 3
8 | SIT | Get the Policy Period for the migrated policies and load those in Workview DB. | 1 | 1 | 1 | Integration Team |  | 2
9 | SIT | prepare RN to deploy web service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 3
10 | SIT | prepare RN to deploy Routing service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 2
11 | SIT | Share the Web servcies URL, File share details with end systems | 1 | 1 | 1 | Integartion team, End system team |  | 2
12 | UAT | Raise request to create country specific directory in UNIX server. The request needs to be raised to RS600 team. | 1 | 1 | 1 | RS6000 |  | 5
13 | UAT | Genius/Meridian team has to share the SFTP key to RS600 team to enable SFTP transfer between AS400 server and UNIX server | 1 | 1 | 1 | Genius/Meridian team |  | 3
14 | UAT | Raise the request to set up robot jobs | 1 | 1 | 1 | AS400 team |  | 3
15 | UAT | Prepare the RN to deploy the Directories and BAT scripts to UNIX server and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 2
16 | UAT | Work with Genius team to setup Genius / Meridian data area | 1 | 1 | 1 | Integration Team |  | 6
17 | UAT | Get the mapping between Loss Group/Casue of Loss from Genisu team for the country and share to data team to populate it. | 1 | 1 | 1 | Data Team |  | 2
18 | UAT | Get the Policy Period for the migrated policies and load those in Workview DB. | 0 | 1 | 1 | Integration Team |  | 3
19 | UAT | prepare RN to deploy web service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 2
20 | UAT | prepare RN to deploy Routing service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 3
21 | UAT | Share the Web servcies URL, File share details with end systems | 1 | 1 | 1 | Integartion team, End system team |  | 2
22 | PRD | Raise request to create country specific directory in UNIX server. The request needs to be raised to RS600 team. | 1 | 1 | 1 | RS6000 |  | 5
23 | PRD | Genius/Meridian team has to share the SFTP key to RS600 team to enable SFTP transfer between AS400 server and UNIX server | 1 | 1 | 1 | Genius/Meridian team |  | 3
24 | PRD | Raise the request to set up robot jobs | 1 | 1 | 1 | AS400 team |  | 3
25 | PRD | Prepare the RN to deploy the Directories and BAT scripts to UNIX server and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 2
26 | PRD | Work with Genius team to setup Genius /Meridian data area | 1 | 1 | 1 | Integration Team |  | 6
27 | PRD | Get the mapping between Loss Group/Casue of Loss from Genisu team for the country and share to data team to populate it. | 1 | 1 | 1 | Data Team |  | 2
28 | PRD | Get the Policy Period for the migrated policies and load those in Workview DB. | 1 | 1 | 1 | Integration Team |  | 3
29 | PRD | prepare RN to deploy web service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 2
30 | PRD | prepare RN to deploy Routing service for new drops and share with Shared servcie team to deploy it. | 1 | 1 | 1 | Integration Team |  | 3
31 | PRD | Share the Web servcies URL, File share details with end systems | 1 | 1 | 1 | Integartion team, End system team |  | 2

## Interfaces Inventory
|  |  | INTEGRATION | [19 empty] | INGESTION
Country | Region | DROP | ACC | Underwriting Portal | Pega (LATAM) | Genius (PBE) | Meridian (PBE) | System 6 (ACL) | SIS (FORMSPATH) | Sanction Check | ACRS | Ignite | GenNext | GenNext2 | eAbs | MNB | GeniusLIFE | CHUBBNET | S6 Life | French Extract | KORAH | Arima | Email Broker | IGNITE | ACL | Forms Path | PBE | DataCap | Business Rules
Philippines | APAC | 1 | Y |  |  |  | Y | Y |  | Y | Y |  |  |  |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Czech Republic | EMEA | 1 |  | Y |  | Y |  |  |  | Y |  |  | Y |  |  | Y | [6 empty] | Y |  |  |  | Y |  | Y
Poland | EMEA | 1 |  | Y |  | Y |  | Y |  | Y |  |  | Y |  |  | Y | [6 empty] | Y |  | Y |  | Y |  | Y
Hungary | EMEA | 1 |  | Y |  | Y |  |  |  | Y |  |  | Y |  |  | Y | [6 empty] | Y |  |  |  | Y |  | Y
South Africa | EMEA | 1 |  | Y |  | Y |  |  |  | Y |  | Y | Y |  |  | Y | [6 empty] | Y | Y |  |  | Y |  | Y
Peru | LATAM | 1 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y | [6 empty] | Y |  |  | Y |  | Y | Y
Singapore | APAC | 2 | Y | Y |  |  | Y | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Belgium | EMEA | 2 | Y | Y |  | Y |  | Y |  | Y |  |  | Y |  |  | Y |  |  | Y |  |  |  | Y |  | Y |  | Y | Y | Y
Netherlands | EMEA | 2 | Y | Y |  | Y |  | Y |  | Y |  | Y | Y |  | Y | Y | Y |  | Y |  |  |  | Y | Y | Y |  | Y | Y | Y
Ecuador | LATAM | 2 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y | [9 empty] | Y |  | Y | Y
Ecuador Life | LATAM | 2 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y | [9 empty] | Y |  | Y | Y
Australia | APAC | 3 | Y | Y |  |  | Y | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Hong Kong | APAC | 3 | Y | Y |  |  | Y | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
New Zealand | APAC | 3 | Y | Y |  | Y |  | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Chile | LATAM | 3 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  | Y |  | Y | Y
Chile Life | LATAM | 3 |  |  | Y |  |  |  | Y | Y | [5 empty] | Y | [6 empty] | Y |  |  | Y |  | Y | Y
Colombia | LATAM | 3 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  | Y |  | Y | Y
Ireland | EMEA | 3 | Y | Y |  | Y |  |  |  | Y |  | Y | Y |  |  | Y | Y |  | Y |  |  |  | Y | Y | Y |  | Y | Y | Y
UK | EMEA | 3 | Y | Y |  | Y |  |  |  | Y |  | Y | Y |  |  | Y | Y |  | Y |  |  |  | Y | Y | Y |  | Y | Y | Y
Switzerland | EMEA | 4 |  | Y |  | Y |  | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Switzerland Temp Re | EMEA | 4 |  |  |  |  | Y |  |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Germany | EMEA | 4 | Y | Y |  | Y |  | Y |  | Y |  | Y |  |  |  | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Italy | EMEA | 4 |  | Y |  | Y |  | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Austria | EMEA | 4 | Y | Y |  | Y |  | Y |  | Y |  | Y |  |  |  | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Vietnam | APAC | 4 |  | Y |  | Y |  | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Thailand | APAC | 4 |  | Y |  |  | Y | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Indonesia | APAC | 4 |  | Y | Y |  | Y | Y |  | Y | Y |  |  | Y |  | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Argentina | LATAM | 4 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  | Y |  | Y | Y
Puerto Rico | LATAM | 4 |  | Y | Y |  | Y |  |  | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  |  | Y | Y | Y
Spain | EMEA | 5 | Y | Y |  | Y |  | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Portugal | EMEA | 5 | Y | Y |  | Y |  | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
France | EMEA | 5 | Y | Y |  | Y |  | Y |  | Y |  | Y |  |  |  | Y |  |  |  | Y |  |  | Y | Y | Y |  | Y | Y | Y
Norway | EMEA | 5 | Y | Y |  | Y | [16 empty] | Y |  |  |  | Y | Y | Y
Finland | EMEA | 5 | Y | Y |  | Y | [16 empty] | Y |  |  |  | Y | Y | Y
Sweden | EMEA | 5 | Y | Y |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Denmark | EMEA | 5 | Y | Y |  | Y | [16 empty] | Y |  |  |  | Y | Y | Y
Taiwan | APAC | 5 | Y | Y |  |  | Y | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Korea | APAC | 5 |  | Y |  |  | Y | Y |  | Y | [5 empty] | Y |  |  |  |  | Y |  | Y |  |  |  | Y | Y | Y
Malaysia | APAC | 5 | Y | Y |  |  | Y | Y |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Turkey | EMEA | 6 |  |  |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  | Y |  | Y | Y | Y
Dubai | EMEA | 6 |  |  |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Bahrain | EMEA | 6 | [7 empty] | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Russia | EMEA | 6 |  |  |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Pakistan | EMEA | 6 |  |  |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Egypt | EMEA | 6 |  |  |  | Y |  |  |  | Y | [5 empty] | Y | [6 empty] | Y |  |  |  | Y | Y | Y
Mexico | LATAM | 5 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  | Y |  | Y | Y
Panama | LATAM | 5 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y | [7 empty] | Y |  | Y | Y
Brazil | LATAM | 6 |  | Y | Y |  |  |  | Y | Y | [5 empty] | Y |  | Y |  |  |  |  | Y |  |  | Y |  | Y | Y
Note on G2: Blackmore, Rachel: Genius (GENeral Insurance Underwriting System) is a fully integrated insurance and reinsurance system. Handles the full business process lifecycle for commercial Property and Casualty Underwriting companies. This includes name clearance, the recording of submission and quotation information, policy and premium registration, document processing, loss processing, transaction and cash processing, finance and reinsurance. There is a two way feed for policies details from APOLLO and fed to GENIUS using GGI (Generic GENIUS Interface). Currently, Claims feed is one way from GENIUS to Apollo.
Note on H2: Blackmore, Rachel: Implemented in countries ASPAC region other than Vietnam, Puerto Rico in Latin Am There is two way feed for policy details from Apollo to Genius. Merdian Claims feed is two way from Genius to Apollo only in ASPAC region. Meridian is an older system being supplanted by GENIUS and SIS is a similar system for Latin America. A financial application used by ACE. This shall provide payment information such as payee, payment method, and amount.
Note on I2: Blackmore, Rachel: System 6 provides A&H Certificate details to Apollo. It is a direct to database feed. Apollo has a one-way link with System 6. Currently the System 6 feed is a VB program, which pipe data (A&H Certificate details) from System 6 to Apollo. Used in UK, Europe, ASPAC. Database for Direct Marketing accounts. This shall provide information on the specific benefits covered and if the policy is still active.
Note on K2: Blackmore, Rachel: Company rating information is updated on a monthly basis via an external service provided by D&B and it exists in UK, Europe, US. The D&B provides a monthly file of rating changes to Apollo via FTP Server. This is a batch process.
Note on N2: Phil Ryan: Used in Europe Updates the Policy/Quote details into Apollo DB using a database call

## Migration Activites RunBook
Applicable for All Regions - APAC, EMEA & LATAM
S.No | Dependencies | # of Days | Comments
1 | Doc Migration | Daily Task | Doc Migration on daily basis will running across countries. Based on the roll out plan a priority call will be taken for the countries nearing PROD. Currently for LATAM we are facing licensing issue and only for 3 hrs of document migration is permitted on a week day and on weekends we are able to execute for LATAM. This is has to be addressed enabling us to run document migration for LATAM as in for other regions. Need to look for the automated way for starting and stopping doc migration services without support of ITOPs.
2 | Security data | 1 | Ready before ETL Kick off. Based on planned UAT Sign-off date it should be intimated atleast 1 week before to progress on this task.
3 | Configuration and reference data | 7 | Ready before ETL Kick off. Based on planned UAT Sign-off date it should be intimated atleast 2 weeks before to progress on this task.
4 | Apollo Staging Db creation | 1 | Apollo Staging DB will be created with the DB backup of Apollo baselined on a specific date (2 to 3 days before planned start of Bulk migration. Case Migration table creation/User access/Read only access/Runstats/Reorg will be covered in this step.
5 | Staging Db/ FileNet DB/ APP DB readiness | 3 | Scripts will be ready as part of 2 & 3 will be promoted to APP DB. Data model changes based on UI build version ( Prod) will be promoted. Migration tables changes and Migration config data scripts will be executed in Migration DB.
6 | Counts of Bulk to determine the actual execution | 1 | Scripts to be executed in Apollo DB to know the entities counts and Classic documents backlog yet to be migrated to Source object store.
7 | ETL Code Deployment/Catalogue creation/Param file changes | 1
8 | ECM Code deployment/Adaptor access/ Smoke testing | 1
9 | ETL Checklist validation which are required before triggering jobs | 2 | Need to validate if the deployment is done, Cataloging is done, required space is there informatica box, DB2 Cache is cleared, Informatica box cache is cleared
Migration Execution
10 | Content Transfer Service | Daily Task | Once moved to PROD, based on the PRODUCTION Rollout plan, this Doc Migration from Source Object Filestore to Target Object Filestore will be planned. 30% of the actual migration will be planned ahead
11 | ETL Execution | 1 | One country requires 16 Hrs at the max and this timing is derived based on Drop 1 Execution. But if the volumes are higher than Drop 1 countries this execution might extend more than 16 hrs or 1 day We can call this execution time with the mock run execution which we do it in PTE provided if we get a chance to load PTE.
12 | ETL Team Data Validation and Counts sharing with ECM | 4 to 6 hrs | It may require 4 to 6 hrs based on the query execution time
13 | SME/ETL Team will start preparing the Reconciliation Report at this point and raise if there is any discrepancy in Classic and in ETL staging dta | 0.6 | This will go in parallel with ECM Migration
14 | Data Fix - On need basis | 0.6 | Scripts needs to be prepared with CR Change and needs to be shared with IT ops
15 | ECM - Jobs Preparation | 0.5 | Based on the volume team will decide how to prepare the ECM Execution. This needs to be planned very well because on daily basis and weekly basis we have DB and FileNet maintenance planned. During Interim run and Final trickle run- ECM will be in 2 fold (for new files and file updates). Trickle update requires more manual effort in job creation.
16 | ECM Execution | 90K Per hour | Based on the volume only the executiong time will be decided. Note: Though the volume of Doc migration is calculated highly for ECM Migration. But only after ETL Migration, we will be knowing the actual migration count which will define the actual migration. During Interim run and Final trickle run- ECM will be in 2 fold (for new files and file updates). Trickle update run time includes the effort on job creation as well as the exeution time
17 | ECM Count Validation against ETL Validation | 0.5 | It may require 2 to 4 hrs based on the query execution time
18 | ETL App DB Load | 0.8 | One country requires 4 - 8 Hrs at the max and this timing is derived based on Drop 1 Execution. But if the volumes are higher than Drop 1 countries this execution might extend more than 8 hrs or 1 day or even more than that. Note: Notes Redesign will be effective in place from Drop 3 for EMEA and APAC and for Drop 4 LATAM. Based on the volume of notes the execution APP DB jobs can take longer.
19 | Offline Backup/ Snapshot to be taken for Staging/FileNet/APP Db and Filestore | 0.3 | To be planned after each of the completion of Bulk/Interim and Final Go-live migration
20 | Runstats execution in FileNet and APP DB | 0.8
21 | ETL Reconciliation Report Generation | 0.8 | One country requires 4 - 8 Hrs at the maxand this timing is derived based on Drop 1 Execution. But if the volumes are higher than Drop 1 countries this execution might extend more than 8 hrs or 1 day or even more than that.
22 | Reconciliation Report Validation by SME | 0.2 | For Each country this Report validation with SME is required and if we have more than one country, the validation will go in parallel while ETL Reconciliation Report extration or in place.
23 | Once the final trickle is run, APP DB sequence will have to be reset | 0.4

## Migration Counts
| ECM Througput Per Hr | 90000 |  | Projected Increase from Apr | 10% |  | Hrs Per Day execution | 20 |  | ELT Through put per Hr | 1681306.3231
[7 empty] | Batch Job/ Co-ordination and Email Updates | 4
APAC | Country | Document_Count | File_Count | Workitem_Count | Notes_Count | Count As on 15 Apr 2018 | Count + 10% Increase | Projected ETL Execution in Hrs | Projected ETL Execution in Days | Projected ECM Execution in Days | ETL & ECM Weeks of Execution | Content Service (30% Assumed Doc Mig) | Migration & FileIn Dependencies (30% We assumed) | Drop 0
APAC | Philippines | 10269992 | 8382634 | 159193 | 16273978 | 24455364.7 | 26900901.17 | 16 |  | 14.9449 | 2.135 |  |  | Drop 1
APAC | Singapore | 13903223 | 4515772 | 359212 | 66915734 | 24411669.1 | 26852836.01 | 15.9714 | 0.66548 | 14.9182 | 2.2262 |  |  | Drop 2
APAC | Australia | 20969045 | 4705013 | 504320 | 69280386 | 34031891.4 | 37435080.54 | 22.2655 | 0.92773 | 20.7973 | 3.1036 | 0.89131 | 2.2123 | Drop 3
APAC | Hong Kong | 6987808 | 1749575 | 182391 | 23733461 | 11595706.2 | 12755276.82 | 15.5865 | 0.64944 | 7.0863 | 1.1051 | 0.3037 | 0.8014 | Drop 3
APAC | New Zealand | 3963746 | 930908 | 117768 | 17479376 | 6516148.6 | 7167763.46 | 12.2632 | 0.51097 | 3.9821 | 0.64187 | 0.17066 | 0.4712 | Drop 3
APAC | Vietnam | 6051325 | 632999 | 4377 | 6511054 | 8695311.3 | 9564842.43 | 13.6889 | 0.57037 | 5.3138 | 0.8406 | 0.22773 | 0.61286 | Drop 4
APAC | Indonesia | 12423994 | 5866982 | 57525 | 16646394 | 23853051.3 | 26238356.43 | 15.6059 | 0.65025 | 14.5769 | 2.1753 | 0.62472 | 1.5506 | Drop 4
APAC | Thailand | 11186199 | 8787713 | 239650 | 33583457 | 26277630.6 | 28905393.66 | 17.1922 | 0.71634 | 16.0586 | 2.3964 | 0.68822 | 1.7082 | Drop 4
APAC | Taiwan | 8913154 | 1595248 | 40013 | 14277157 | 13712939.5 | 15084233.45 | 8.9717 | 0.37382 | 8.3801 | 1.2506 | 0.35915 | 0.89142 | Drop 5
APAC | Malaysia | 12423341 | 8432518 | 77701 | 27619323 | 27213628 | 29934990.8 | 17.8046 | 0.74186 | 16.6306 | 2.4818 | 0.71274 | 1.769 | Drop 5
APAC | Korea | 18679243 | 23068479 | 23908 | 84509551 | 54303119 | 59733430.9 | 35.528 | 1.4803 | 33.1852 | 4.9522 | 1.4222 | 3.53 | Drop 5
EMEA | Country | Document_Count | File_Count | Workitem_Count | Notes_Count | As on 15 Apr 2018 | As on 15 Apr 2018 | Projected ETL Execution in Hrs | Projected ETL Execution in Days | Projected ECM Execution in Days | ETL & ECM Weeks of Execution | Content Service (30% Assumed Doc Mig) | Migration & FileIn Dependencies (30% We assumed) | Drop 0
EMEA | Poland | 1076763 | 156810 | 67348 | 3398554 | 1691197.3 | 1860317.03 | Done |  | 1.0335 | 0.14764 |  |  | Drop 1
EMEA | Czech Republic | 112684 | 42318 | 11412 | 1048430 | 216338.2 | 237972.02 | Done |  | 0.13221 | 0.018887 |  |  | Drop 1
EMEA | South Africa | 1674276 | 148831 | 64562 | 7977111 | 2453969.7 | 2699366.67 | Done |  | 1.4996 | 0.21424 |  |  | Drop 1
EMEA | Hungary | 24031 | 4559 | 2625 | 170638 | 40579.5 | 44637.45 | Done |  | 0.024799 | 0.0035427 |  |  | Drop 1
EMEA | Belgium | 2282122 | 638031 | 85157 | 9682956 | 3906903 | 4297593.3 | 10.5561 | 0.43984 | 2.3876 | 0.40391 |  |  | Drop 2
EMEA | Netherlands | 5201351 | 2433535 | 135779 | 14923011 | 10101864.5 | 11112050.95 | 14.6092 | 0.60872 | 6.1734 | 0.96887 |  |  | Drop 2
EMEA | United Kingdom | 42019127 | 9890137 | 1614816 | 229853146 | 69581304 | 76539434.4 | 45.5238 | 1.8968 | 42.5219 | 6.3455 | 1.8224 | 4.5232 | Drop 3
EMEA | Ireland | 2526965 | 909487 | 129477 | 12887406 | 4635707.7 | 5099278.47 | 11.0329 | 0.45971 | 2.8329 | 0.47038 | 0.12141 | 0.34897 | Drop 3
EMEA | Italy | 16537869 | 2328943 | 406323 | 70285854 | 25055075.5 | 27560583.05 | 16.3924 | 0.68302 | 15.3114 | 2.2849 | 0.6562 | 1.6287 | Drop 4
EMEA | Germany | 9330465 | 2928426 | 447921 | 53145927 | 16518855.6 | 18170741.16 | 10.8075 | 0.45031 | 10.0949 | 1.5065 | 0.43264 | 1.0738 | Drop 4
EMEA | Austria | 976339 | 122008 | 42625 | 5032595 | 1483263.6 | 1631589.96 | 8.9704 | 0.37377 | 0.90644 | 0.18289 | 0.038847 | 0.14404 | Drop 4
EMEA | Swiss | 1545217 | 157591 | 38961 | 7367973 | 2264299.7 | 2490729.67 | 9.4814 | 0.39506 | 1.3837 | 0.25411 | 0.059303 | 0.19481 | Drop 4
EMEA | Swiss tempest | 27227 | 9747 | 5850 | 1931675 | 55671.2 | 61238.32 | 8.0364 | 0.33485 | 0.034021 | 0.052696 | 0.0014581 | 0.051238 | Drop 4
EMEA | France | 18495820 | 5982468 | 1624424 | 97395910 | 33933525.6 | 37326878.16 | 22.2011 | 0.92505 | 20.7372 | 3.0946 | 0.88874 | 2.2059 | Drop 5
EMEA | Sweden | 2866989 | 1062957 | 75516 | 7219519 | 5207100.6 | 5727810.66 | 11.4068 | 0.47528 | 3.1821 | 0.52249 | 0.13638 | 0.38611 | Drop 5
EMEA | Norway | 860152 | 187938 | 19266 | 2181827 | 1387562.8 | 1526319.08 | 8.9078 | 0.37116 | 0.84796 | 0.17416 | 0.036341 | 0.13782 | Drop 5
EMEA | Finland | 2521367 | 464927 | 24662 | 3088704 | 3914242.8 | 4305667.08 | 10.5609 | 0.44004 | 2.392 | 0.40458 | 0.10252 | 0.30207 | Drop 5
EMEA | Spain | 7122874 | 5740170 | 347468 | 32044812 | 17173665.6 | 18891032.16 | 11.2359 | 0.46816 | 10.495 | 1.5662 | 0.44979 | 1.1164 | Drop 5
EMEA | Portugal | 1032567 | 388918 | 23881 | 2609019 | 1878975.8 | 2066873.38 | 9.2293 | 0.38456 | 1.1483 | 0.21897 | 0.049211 | 0.16976 | Drop 5
EMEA | Denmark | 404700 | 224005 | 26735 | 2104363 | 852072 | 937279.2 | 8.5575 | 0.35656 | 0.52071 | 0.12532 | 0.022316 | 0.10301 | Drop 5
EMEA | Bermuda | 315977 | 22624 | 3685 | 1954206 | 444971.8 | 489468.98 | 8.2911 | 0.34546 | 0.27193 | 0.088199 | 0.011654 | 0.076545 | Drop 6
EMEA | Global Treaty | 161390 | 27000 | 5 | 488476 | 244913.5 | 269404.85 | 8.1602 | 0.34001 | 0.14967 | 0.069954 | 0.0064144 | 0.06354 | Drop 6
EMEA | Turkey | 587994 | 113448 | 44804 | 2329288 | 970119.8 | 1067131.78 | 8.6347 | 0.35978 | 0.59285 | 0.13609 | 0.025408 | 0.11068 | Drop 6
EMEA | Russia | 419739 | 60666 | 32300 | 2859869 | 666516.5 | 733168.15 | 8.4361 | 0.3515 | 0.40732 | 0.1084 | 0.017456 | 0.090946 | Drop 6
EMEA | Egypt | 28826 | 14934 | 145 | 78071 | 57076.5 | 62784.15 | 8.0373 | 0.33489 | 0.03488 | 0.052824 | 0.0014949 | 0.051329 | Drop 6
EMEA | Bahrain | 456781 | 283049 | 15929 | 3262161 | 982486.7 | 1080735.37 | 8.6428 | 0.36012 | 0.60041 | 0.13722 | 0.025732 | 0.11149 | Drop 6
EMEA | Pakistan | 2416 | 77463 | 160 | 12149 | 104050.7 | 114455.77 | 8.0681 | 0.33617 | 0.063587 | 0.057108 | 0.0027251 | 0.054383 | Drop 6
LATAM | Country | Document_Count | File_Count | Workitem_Count | Notes_Count | As on Dec 2017 | As on Dec 2017 | Projected ETL Execution in Hrs | Projected ETL Execution in Days | Projected ECM Execution in Days | ETL & ECM Weeks of Execution | Content Service (30% Assumed Doc Mig) | Migration & FileIn Dependencies (30% We assumed) | Drop 0
LATAM | Ecuador | 15211207 |  |  |  | 19774569.1 | 21752026.01 | 12.9376 | 0.53907 | 12.0845 | 1.8034 |  |  | Drop 2
LATAM | Ecuador Life | 1296750 |  |  |  | 1685775 | 1854352.5 | 9.1029 | 0.37929 | 1.0302 | 0.20135 |  |  | Drop 2
LATAM | Chile | 7279108 |  |  |  | 9462840.4 | 10409124.44 | 14.1911 | 0.5913 | 5.7828 | 0.91059 |  |  | Drop 3
LATAM | Chile Life | 270373 |  |  |  | 351484.9 | 386633.39 | 8.23 | 0.34292 | 0.2148 | 0.079673 |  |  | Drop 3
LATAM | Colombia | 15412055 |  |  |  | 20035671.5 | 22039238.65 | 13.1084 | 0.54618 | 12.244 | 1.8272 |  |  | Drop 3
LATAM | Argentina | 14822819 |  |  |  | 19269664.7 | 21196631.17 | 12.6072 | 0.5253 | 11.7759 | 1.7573 | 0.50468 | 1.2526 | Drop 4
LATAM | Puerto Rico | 11032712 |  |  |  | 14342525.6 | 15776778.16 | 9.3836 | 0.39099 | 8.7649 | 1.308 | 0.37564 | 0.93234 | Drop 4
LATAM | Mexico | 21312163 |  |  |  | 27705811.9 | 30476393.09 | 18.1266 | 0.75528 | 16.9313 | 2.5267 | 0.72563 | 1.801 | Drop 5
LATAM | Panama | 523096 |  |  |  | 680024.8 | 748027.28 | 8.4449 | 0.35187 | 0.41557 | 0.10963 | 0.01781 | 0.091824 | Drop 5
LATAM | Brazil | 35835500 |  |  |  | 46586150 | 51244765 | 30.4791 | 1.27 | 28.4693 | 4.2485 | 1.2201 | 3.0284 | Drop 6
LATAM | Brazil Life | 255320 |  |  |  | 331916 | 365107.6 | 8.2172 | 0.34238 | 0.20284 | 0.077888 | 0.008693 | 0.069195 | Drop 6