## Most Likely Plan
SIT End Date |  | 30-Jun-2015
SIT Testing Cycles | Current Status | New Timelines |  | TestCases | Resource Count | Through Put/Day | Dependencies | Exit Criteria
|  | Start Date | End Date
1A - Cycle 1 | Completed | 26-Jan-2015 | 11-Feb-2015 |  |  |  | N/A | Completed.
1A - Cycle 2 | Completed | 16-Feb-2015 | 20-Feb-2015 |  |  |  | N/A | Completed.
1B - Cycle 1 | Completed | 25-Feb-2015 | 16-Mar-2015 |  |  |  | N/A | Completed.
1B - Cycle 2 | Completed | 17-Mar-2015 | 20-Mar-2015 |  |  |  | N/A | Completed.
ETL Regression | WIP | 09-Apr-2015 | 13-Apr-2015 |  |  |  | N/A | Completed.
Peoplesoft Integration Cycle 1 | WIP | 13-Apr-2015 | 16-Apr-2015 |  |  |  | N/A | In Progress.
Peoplesoft Integration Cycle 2 |  | 21-Apr-2015 | 23-Apr-2015
1C - Cycle 1 (Including Carry Forward Test Cases) | WIP | 30-Mar-2015 | 08-May-2015 | 797 | 7 | 91 | Current Backlog (Prioritized): 78 Predicted Defect from the remaining scope: 40 Total Defect: 118 Expected Fix Rate: 80% (94 Critical & High Defects) | Execution Percentage: 100% Pass Percentage: 80%
1C - Cycle 2 (280 Test Cases) |  | 11-May-2015 | 22-May-2015 | 280 | 7 |  | Carry over: 24 Predicted Open Defects: 25 Expected Fix Rate: 100% (49 Critical & High Defects) | Execution Percentage: 100% Pass Percentage: 85%
Failed Test Cases & Defect Retesting |  | 30-Apr-2015 | 05-May-2015 | 170 | 6 | 78 | Backlog from CR & 1C Cycle 2: 17; Predicted Open Defects (Critical & High): 5; Total Defects: 22 Expected Fix Rate: 100% (22 Defects) Targeted Date: 05-May-2015
CR Builds (107 Test Cases) Daeja Viewer 4.1.3 Testing (55 Test Cases) Search Template & SSO (130 Test Cases) |  | 15-Apr-2015 | 29-Apr-2015 | 292 | 7 | 91 | Predicted Open Defects (Critical & High): 45 Expected Fix Rate: 80% (36 Defects) | Execution Percentage: 100% Pass Percentage: 85% No high and critical defect opened WITHOUT workaround
E2E - Cycle 1 PeopleSoft Integration Testing - Cycle 1 |  | 25-May-2015 | 10-Jun-2015 | 350 | 6 | 30 | Predicted Open Defects (Critical & High): 70 Expected Fix Rate: 80% (56 Defects) | Execution Percentage: 100% Pass Percentage: 80% Able to perform E2E Business process flow No New CRs will be approved/deployed into SIT beyond this point
E2E - Cycle 2 PeopleSoft Integration Testing - Cycle 2 Defect Retesting |  | 11-Jun-2015 | 24-Jun-2015 | 180 | 6 | 36 | Backlog from E2E Cycle 1: 14 Predicted Open Defects (Critical & High): 35 Total Defects: 49 Expected Fix Rate: 100% (49 Defects) | Execution Percentage: 100% Pass Percentage: 95% Able to perform E2E Business process flow
MI Testing Cycle 1 |  | 27-Apr-2015 | 20-May-2015 | 350 | 2 | 20 | MI build should be available before 24th April 2015.
MI Testing Cycle 2 |  | 21-May-2015 | 03-Jun-2015 | 180 | 2 | 20
Freeze/Final Regression Cycle |  | 18-Jun-2015 | 30-Jun-2015 | 350 | 6 | 20 | Expected Fix Rate: 100% | Execution Percentage: 100% Pass Percentage: 95% No high and critical defect opened WITHOUT workaround

## Defect ETA
Defect ID | Fix Priority | Summary | Severity | Component Name | Assigned To | Must Have Date | Planned Fix Date | Impacted System | Defect Owner | Defect Status
119 | 2 - High | Document Generation_ Generated document in document panel does not contain Folder type, Document type and Filename details | 2 - High | Document Generation | yxkhom | 2015-04-23 | 2015-04-23 | ACEView | Vega | Re-opened
140 | 2 - High | Document properties should be read only but they are editable in ACEView application. | 2 - High | Drag and Drop | kxbizi | 2015-04-16 | 2015-04-16 | ACEView | Vega | Fixed
174 | 2 - High | ACEView : The fields are not present in the expected format in the Vendor Search page. | 2 - High | ASPAC Workflow | axsavi | 2015-04-27 | 2015-04-27 | ACEView | Vega | Re-opened
192 | 2 - High | Manage Notes: "Type" filter functionality for Notes is not displayed as Expected. | 2 - High | Notes | kxbizi | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
193 | 2 - High | Diary – Filter icon is not present in status field to sort “Expired” & “Active”. | 2 - High | Diary | kxbizi | 2015-04-16 | 2015-04-16 | ACEView | Vega | Fixed
201 | 2 - High | ASPAC Workflow_Ok button is enabled in the comment pop up even when the comment box is left blank - decline order action | 2 - High | ASPAC Workflow | jwbald | 2015-04-27 | 2015-04-27 | ACEView | Vega | Open
225 | 2 - High | ASPAC: New PO record(a row) is created even when no data is entered and not Saved.No file number is displayed | 2 - High | ASPAC Workflow | yxkhom | 2015-04-16 | 2015-04-16 | ACEView | Vega | In Progress
242 | 2 - High | ASPAC: Title of the tab is displayed as ARASP_POInvoicing_undefined. It should be displayed as PO Invoice number, once saved | 2 - High | ASPAC Workflow | yxkhom | 2015-04-23 | 2015-04-23 | ACEView | Vega | Re-opened
245 | 2 - High | Read only rules on Properties - This is a catch all defect for all instances where Read Only rules on properties are not correct. The desciption can be used as these are found | 2 - High | ASPAC Workflow | axdubo | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
250 | 2 - High | ASPAC Workflow : Pop up dialog box is not displayed as expected. , when we try to perform "Send for Higher Approval" in Action tab . | 2 - High | ASPAC Workflow | axdubo | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
251 | 2 - High | ASPAC_Workflow_T&E: T&E File Number field is not editable | 2 - High | ASPAC Workflow | yxkhom | 2015-04-23 | 2015-04-23 | ACEView | Vega | Open
254 | 2 - High | ASPAC Workflow : File number is not getting displayed as expected , when New T & E expenses is created. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-23 | 2015-04-23 | ACEView | Vega | Open
262 | 2 - High | FileNet annotation table: Field should be populated with Status Code rather than Status description | 2 - High | ACEView | axsavi | 2015-04-23 | 2015-04-23 | Filenet | Vega | Re-opened
289 | 2 - High | ASPAC-Correspondents_ bold red font message that states "Vendor Locked to PeopleSoft" is not displayed after selecting a ‘vendor’ in PO Invoice tab | 2 - High | Correspondents | axdubo | 2015-04-30 | 2015-04-30 | ACEView | Vega | Open
296 | 2 - High | ASPAC-Correspondents_ system does not display the appropriate message to the user when no search results have been found for the given search criteria | 2 - High | Correspondents | axsavi | 2015-05-05 | 2015-05-05 | ACEView | Vega | Open
299 | 2 - High | ASPAC-flow_Wrong actions are displayed for a "New" status PO workitem | 2 - High | ASPAC Workflow | yxkhom | 2015-04-27 | 2015-04-27 | ACEView | Vega | Open
300 | 2 - High | ASPAC – PS Voucher number is editable in “Posted in peoplesoft” status. | 2 - High | ASPAC Workflow | axdubo | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
305 | 2 - High | ASPAC Workflow: System allows to edit the field values, after the payment is approved in PeopleSoft | 2 - High | ASPAC Workflow | axdubo | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
320 | 2 - High | ASPAC – Quotation amount field is not reflecting as mandatory field in invoice awaiting coding status. | 2 - High | ASPAC Workflow | dzmais | 2015-04-23 | 2015-04-23 | ACEView | Vega | Fixed
321 | 2 - High | Flags & Milestones - A milestone is created in the ACE View application UI, it is not being stored in the File_Miestone table inthe App DB. | 2 - High | Flags and Milestones | dzmais | 2015-04-16 | 2015-04-16 | ACEView | Vega | Fixed
340 | 2 - High | Manage User Preference: When user preference of Notes and Diary is set to alert in Settings, but it’s not reflecting in any of the work items. | 2 - High | Manage User Preference | kxbizi | 2015-04-16 | 2015-04-16 | ACEView | Vega | Open
347 | 2 - High | Search Template : Status of the workitem is not getting Displayed as "New" after performing PO Invoicing - Quick Search from Search template dropdown. | 2 - High | Search Template | axsavi | 2015-04-27 | 2015-04-27 | ACEView | Vega | New
353 | 2 - High | Send Email – Document is not getting attached in Email, while performing Send Email functionality in a work item. | 2 - High | Send Email | dzmais | 2015-04-16 | 2015-04-16 | ACEView | Vega | Open
381 | 2 - High | ASPAC-Workflow: Mismatch in the Field displayed in the T&E Expense tab and the Fields mentioned in the Config sheet (Wave_1_WorkflowConfiguration_ASPAC_Finance_TE_1.0) . | 2 - High | ASPAC Workflow | j9norb | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
382 | 2 - High | ASPAC-Workflow: Mismatch in the Field displayed in the T&E Expense tab and the Fields mentioned in the Config sheet (Wave_1_WorkflowConfiguration_ASPAC_Finance_TE_1.0) . | 2 - High | ASPAC Workflow | j9norb | 2015-04-20 | 2015-04-20 | ACEView | Vega | Open
383 | 2 - High | ASPAC Workflow: A new PO invoice is created even without entering the few mandatory fields such as Purchase Type & purchase Category. | 2 - High | ASPAC Workflow | axplac | 2015-04-16 | 2015-04-16 | ACEView | Vega | Put On Hold
385 | 2 - High | Open File & Open Case – System not prompting/warning with a message, when user close the work item without saving. | 2 - High | Open File and Open Case | kxbizi | 2015-04-16 | 2015-04-16 | ACEView | Vega | Put On Hold
389 | 2 - High | Notes :Audit Notes displays Status as "27" instead of "New" in the history of "Notes/audit trails" tab | 2 - High | Notes | axdubo | 2015-04-16 | 2015-04-16 | ACEView | Vega | In Progress
392 | 2 - High | ACE View – While saving the work item by using the shortcut key (Alt+Shift+C), system displays the dialog box. | 2 - High | ACEView | yxkhom | 2015-04-30 | 2015-04-30 | ACEView | Vega | Open
398 | 2 - High | Workbasket_Mega Filter: System deletes the Saved filter even when user does not select any filter record to delete | 2 - High | Workbasket | yxkhom | 2015-04-30 | 2015-04-30 | ACEView | Vega | New
402 | 2 - High | All the workitems are getting exported from the application to the Excel instead the selected workitems. | 2 - High | Search Template | axsavi | 2015-04-27 | 2015-04-27 | ACEView | Vega | New
421 | 2 - High | Workbasket_Reassign: Error message is not displayed when reassigning a workbasket without selecting any User value. | 2 - High | Workbasket | yxkhom | 2015-04-30 | 2015-04-30 | ACEView | Vega | New
437 | 2 - High | pend icon not removed after expiring pend time and the item colour is not changed automatically | 2 - High | Workflow Design | yxkhom | 2015-04-30 | 2015-04-30 | ACEView | Vega | New
440 | 2 - High | Pend time in “Pend” action is not being saved as expected | 2 - High | Workflow Design | kxbizi | 2015-04-30 | 2015-04-30 | ACEView | Vega | Open
444 | 2 - High | ASPAC Workflow – Right side reading pane is editable for the work items. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-30 | 2015-04-30 | ACEView | Vega | Open
445 | 2 - High | Open File and Open Case: Options Permanent Link – One Way Link, Permanent Link – Two Way Link are not displayed after clicking on Attach button to attach the selected file. | 2 - High | Open File and Open Case | kxbizi | 2015-04-27 | 2015-04-27 | ACEView | Vega | New
450 | 2 - High | AceView: AceView screen Screen displayed is not showing the entire full screen | 2 - High | ACEView | yxkhom | 2015-05-05 | 2015-05-05 | ACEView | Vega | Open
395 | 2 - High | Workbasket_Mega Filter: There are duplicate values available in 'Status' drop down of Mega Filter section | 2 - High | Workbasket | yxkhom | 2015-04-14 | 2015-04-14 | ACEView | Vega | Open
196 | 1 - Critical | ACEView_SendFax : Sent fax is not ingested back into ACEView when the "Save generated email/fax to ACEView" checkbox is Checked. | 2 - High | Send Fax | kanixd | 2015-04-20 | 2015-04-20 | ACEView | Cognizant | In Progress
469 | 2 - High | Security Policy on the Create forms for PO, T&E and CD should be re-labelled File Level Security Groups AND should require mandatory entry ie either Finance Restricted or None from the Choice List | 2 - High | ACEView | axdubo | 2015-04-16 | 2015-04-16 | ACEView | Vega | Open
25 | 2 - High | Email: Mails are available in (Inbox , Error and Processed ) all the folders. | 2 - High | Email | kxkaru | 2015-04-20 |  | ACEView | Cognizant | In Progress
167 | 2 - High | File Type should not be selectable in Documents Tab (should be inherited from the File) | 2 - High | ASPAC Workflow | axdubo | 2015-04-20 |  | ACEView | Vega | Re-opened
200 | 2 - High | ASPAC flow_System prompts a comment box when peforming approve order action, but the comment box is not mandatory. | 2 - High | ASPAC Workflow | axplac | 2015-04-20 |  | ACEView | Vega | Re-opened
316 | 2 - High | ASPAC – VAT Rate should be changed as “Optional” field in cost allocation tab. | 2 - High | ASPAC Workflow | axplac | 2015-04-20 |  | ACEView | Vega | New
317 | 2 - High | ASPAC-Workflow: Mismatch in the dropdown Values of Payment Method Field displayed in the PO Invoice tab and the Values mentioned in the Choice List document. | 2 - High | ASPAC Workflow | j9norb | 2015-04-20 |  | ACEView | Vega | In Progress
319 | 2 - High | ASPAC-Workflow: "Null" values getting displayed in the dropdown values of the Alt Account field in the Cost Allocation tab. | 2 - High | ASPAC Workflow | cxturl | 2015-04-20 |  | ACEView | MDS | In Progress
329 | 2 - High | Security – PEP integration - This is a master defect for early security related issues. | 2 - High | Security_ACEView Integration | yxkhom | 2015-04-20 |  | ACEView | Vega | Re-opened
390 | 2 - High | On Pending a workitem the Comment option should be Mandatory in the Pend dialog box. | 2 - High | Workflow Design | axplac | 2015-04-20 |  | ACEView | Vega | Open
408 | 2 - High | Workbasket_Bulk Action: 'Action' menu is enabled when records are selected with different statuses | 2 - High | ACEView | bybull | 2015-04-20 |  | ACEView | Vega | New
413 | 2 - High | ACEView_Cost Allocation: Values displayed in 'Alt Account' is displaye wrongly when compared with ASPAC Choice list value | 2 - High | ACEView | cxturl | 2015-04-20 |  | ACEView | MDS | Open
449 | 2 - High | ASPAC Workflow – File number is generating incorrectly for BU – AIOIC Branch Thailand. | 2 - High | ASPAC Workflow | kanixd | 2015-04-23 |  | ACEView | Cognizant | In Progress
451 | 2 - High | ASPAC Work Flow : Error message is not displayed by clicking on save button with value entered only for Business unit while creating a New T&E Expense. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
457 | 2 - High | Security_ACEView Integration: System displays all the PO work baskets, when a user is assigned to only “PO invoicing processing work basket” in Manage Role. | 2 - High | Security_ACEView Integration | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
460 | 2 - High | ASPAC Workflow: A newly created work item is not getting displayed in any of the work baskets, when a work item created with the security policy field given as “None”. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
461 | 2 - High | Send Email: Unable to perform Send Email functionality for a work item in Finance indexing work basket. | 2 - High | Send Email | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
463 | 2 - High | ACE View: A newly created finance indexing work item is getting invisible (with the white color font) in finance indexing work basket, when documents are ingested through upload option. | 2 - High | Upload Document | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
464 | 2 - High | ACE View: File count of “Total/Unread/Priority/Pended/Locked” for Finance indexing work basket is getting mismatched. | 2 - High | ACEView | yxkhom | 2015-04-23 |  | ACEView | Vega | New
465 | 2 - High | Send Fax: Unable to perform Send Fax functionality for a work item in Finance indexing work basket. | 2 - High | Send Fax | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
466 | 2 - High | Send Fax: System is not performing Send Fax functionality properly in PO invoicing work basket. | 2 - High | Send Fax | yxkhom | 2015-04-23 |  | ACEView | Vega | Open
468 | 2 - High | ACE View: ACE View system requires frequent cache clearance for the functionalities to reflect in the system. | 2 - High | ACEView | yxkhom | 2015-04-23 |  | ACEView | Vega | New
470 | 2 - High | Correspondents : Vendor Correspondence Name and Address not getting populated correctly in Correspondent tab. | 2 - High | Correspondents | yxkhom | 2015-04-27 |  | ACEView | Vega | Open
471 | 2 - High | ASPAC Workflow – System throws an error message, after uploading the data sheet in cost allocation tab. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-27 |  | ACEView | Vega | New
473 | 2 - High | ASPAC Workflow – A newly created work item (POAU100061) which is proceeded to “invoice awaiting coding” status is not getting displayed in any of the work baskets. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-27 |  | ACEView | Vega | Open
475 | 2 - High | Open File and Open Case: System is not allowing to link different files via tree view by right clicking Attach File option. | 2 - High | Open File and Open Case | yxkhom | 2015-04-27 |  | ACEView | Vega | New
478 | 2 - High | System is not displaying the Vendor Short name column details in Vendor Search screen when creating PO. | 2 - High | ACEView | j9norb | 2015-04-27 |  | ACEView | Vega | Open
479 | 2 - High | <DaejaViewer_ACEView_Integration> : Annotations toolbar is enabled for attachments present in the email. | 2 - High | Daeja_Viewer ACEView Integration | kxkana | 2015-04-27 |  | Daeja Viewer | Cognizant | In Progress
480 | 2 - High | Security_ACEView Integration: System displays PO Invoice Checking workbasket, when a user is assigned to only “PO invoicing processing work basket” in Manage Role. | 2 - High | Security_ACEView Integration | bybull | 2015-04-27 |  | ACEView | Vega | Open
482 | 2 - High | Security_ACE View Integration : System displays PO Invoice Coding workbasket, when a user is assigned the role of "Purchase Order Approval" in Manage Role screen. | 2 - High | Security_ACEView Integration | bybull | 2015-04-27 |  | ACEView | Vega | Open
483 | 2 - High | Prompt message is not asked while drag and drop from one queue to another | 2 - High | Drag and Drop | yxkhom | 2015-04-27 |  | ACEView | Vega | New
486 | 2 - High | Focus not moving to another tab when drag and drop from one open work item to another open work item | 2 - High | Drag and Drop | yxkhom | 2015-04-27 |  | ACEView | Vega | Open
487 | 2 - High | Prompt message is not displayed when dragging documents within the work item | 2 - High | Drag and Drop | yxkhom | 2015-04-30 |  | ACEView | Vega | Open
490 | 2 - High | The application is not behaving as expected after keeping it inactive for long time | 2 - High | ASPAC Workflow | yxkhom | 2015-04-30 |  | ACEView | Vega | Put On Hold
491 | 2 - High | MQ(Message Queue) Failed | 2 - High | ACEView | aykhan | 2015-04-30 |  | PeopleSoft | ACE | Open
493 | 2 - High | Security: Mismatch in “Security Policies” values displayed in ACEView Application and the values displayed in Use Case. | 2 - High | Security | bybull | 2015-04-30 |  | ACEView | ACE | New
494 | 2 - High | Security_ACE View Integration: Work basket Email notification in Settings icon is not working as expected for personal work basket. | 2 - High | Scanning_ACEView Integration | yxkhom | 2015-04-30 |  | ACEView | Vega | Open
495 | 2 - High | Security: System displays User Administration and System Administration tab, when a user is assigned to only "Purchase Order Processor" in Assigned Roles. | 2 - High | Security | stsure | 2015-04-30 |  | ACEView | Cognizant | In Progress
496 | 2 - High | ASPAC Workflow : On an Indexing Work Item, Transaction Type values is not displayed based on Transaction File Type selected. | 2 - High | ASPAC Workflow | yxkhom | 2015-04-30 |  | ACEView | Vega | New
497 | 2 - High | Security_ACEView Integration: System displays PO Invoice Approvals workbasket, when a user is assigned with the "PO Invoice Checking" workbasket and the Manage Role as "Finance Indexer". | 2 - High | Security_ACEView Integration | yxkhom | 2015-04-30 |  | ACEView | Vega | New

## Metrics
Down Time
Overall DownTime | 430 Hrs ($ 11,180)
1C Downtime | 380 Hrs ($ 9,880)
Build Rejection on First Deployment
Overall Build Rejection Count | 7 Build (Send Email, Send Fax, Security_PEP Integration, Manage User Preference, Workflow Design - Pend & Indexing, Flags & Milestones, Open File and Open Case)
1C Build Rejection Count | 5 Build (Security_PEP Integration, Manage User Preference, Workflow Design - Pend & Indexing, Flags & Milestones, Open File and Open Case)
Build Delay
1C Build Delay | 3 Business Days (Planned Start Date: 25/03 - Actual Start Date: 30/03)
Application Stability
Concern Areas | 1. ETL run doesn’t have a permanent fix, manually the tables are updated for last 3 builds 2. PeopleSoft Integration Testing
Component Stability
Components Tested & dusted in the past, having lot of issues now – which needs re-testing as an whole | 1. ASPAC Workflow - Create PO (Data Issues) 2. Cost allocation tab in PO file creation 3. Send Email & Send Fax 4. Drag & Drop 5. Notes, Alerts and Notification 6. Manage User Preference 7. Security ACEView PEP Configuration
Vulnerable Defects (Going Back & Forth like Environment Defects), Ageing Defects | 25 - Email broker, 157 - Drag and Drop, 213 - Cost allocation in PO file creation,
Components with large open defects | ASPAC workflow - 46, ACEView - 32, Workbasket - 26, Workflow design - 12, Security_Integration - 12
Defects Re-open Trend (Last 11 Week)
Overall Re-opened Defect Count | 71
Avg Defect Fix Per Week | 14
Avg Defect Re-Open Per Week | 6
Avg Defect Aging - all defects | 16 days
Avg Defect Aging - Critical & High defects | 14 days
Avg Defect Aging - Medium & Low | 17 Days

## ACE_Action_Items
S. No | Facilitation Required on Defects
1 | All critical & high defects to have ETA (Fix date column to be updated in HP ALM).
2 | Expected Defect Fix / Week is Minimum 24 Defects.
3 | Defect Prioritisation should be discussed & confirmed with Barry in defect triage and this to be shared with Annie.
4 | Build / Environment team should confirm on the successful smoke test results before handing over to SIT to avoid build rejection at the initial test stage.
5 | Suggestion: Dev teams to give build on once in 2 days basis, to expedite the testing.
6 | Half day defect workshop to discuss on the medium & low defects as it was not considered for the discussion in the defect triage.
S. No | Focus Area | Expectations
1 | Peoplesoft Integration Testing is not working even with workaround (Scenario tested last time - is not working consistently) | 1. We need War Room set-up involving all stakeholders to resolve the basic issues 2. We need VEGA/CTS/Peoplesoft/Accenture teams available, with SPOC's in each team till testing is complete
2 | ETL related Downtime - Affecting QA testing | 1. Need Permanent Fix to resolve the issue( Currently Manual Intervention is required)
Financial
Current QA team planned rampdown from 8 to 3 in May end, Since timelines are getting pushed out, we need coverage for min 5 (3+2) for month of June

## Options to Expedite
Vega Ramp-up Possible ?
Hot house session to expedite defect turnaround
QA Team can spare 1-2 functional QA - for Validating defect fixes in Dev Environment, once the fix is ready