## DR Dashboard
R2 COG - Document Revision Dashboard

## DR Report
| Total Reworked Test Scenarios | Total Reworked Test Cases | Rework Effort (in Hrs.) | Rework Cost (in $)
| 134 | 445 | 123.95 | 3222.7
Documents Revised | Version Revised | Revised Version | Test Design Update | Test Design Updation % | Requirement Stability Index
Policy | Yes | v1.1_WIP | In-Progress | 80% | 0.68
Claims | Yes | v1.1_Update | In-Progress | 90% | 0.91
BIRI | Yes | v1.0_Baseline | Completed | 100% | 0.83
CI | Yes | v1.0 - Customization | Completed | 100% | 0.85
Complaints | Yes | v1.0_Baseline | Completed | 100% | 0.88
Overview | Yes | v0.81 | Yet to Start | 0% | TBU
Security | Yes | v0.81 | In-Progress | 90% | 0.75
Ingestion | Yes | Ingestion Documents Updated | Yet to Start | 0% | TBU
Indexing | Yes | UC028 | Completed | 100% | 0.75
Integration Overview | Yes | v0.8 | In-Progress | 20% | 0.92
Correspondent | Yes | v.0.7- Customization | In-Progress | 20% | 0.89
Document Generation | Yes | v0.72 | Completed | 100% | 0.5
Total |  |  | In-Progress | 63.64% | NA
Documents Revised | Test Scenarios |  |  | Test Cases |  |  | Rework Effort (in Hrs.) | Rework Cost (in $)
| Updated | Added | Deleted | Updated | Added | Deleted
Policy | 20 | 9 | 4 | 10 | 104 | 21 | 42.0833 | 1094.1667
Claims | 1 | 12 | 27 | 27 | 14 | 10 | 13.85 | 360.1
BIRI | 0 | 0 | 0 | 6 | 8 | 0 | 3.6667 | 95.3333
CI | 0 | 0 | 0 | 4 | 2 | 0 | 1.3333 | 34.6667
Complaints | 30 | 2 | 0 | 0 | 0 | 0 | 3.4 | 88.4
Overview | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security | 1 | 8 | 7 | 58 | 105 | 15 | 47.4667 | 1234.1333
Ingestion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indexing | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 26
Integration Overview | 0 | 0 | 0 | 40 | 0 | 0 | 6.6667 | 173.3333
Correspondent | 0 | 0 | 0 | 4 | 1 | 0 | 1 | 26
Document Generation | 10 | 0 | 3 | 0 | 5 | 8 | 3.4833 | 90.5667
Total | 62 | 31 | 41 | 149 | 242 | 54 | 123.95 | 3222.7

## RSI
S. No | Document Name | Document Type | Total No Original Requirements | No of Requirements Changed | No of Requirements added | No of Requirements deleted | Requirement Stability % | Requirement Stability Index | Tracked Date (DD/MM/YYYY)
1 | Claims | Functional Specification | 21 | 3 | 0 | 0 | 85.7143 | 0.85714 | 2016-11-07
2 | Claims | Customization Sheet | 34 | 0 | 2 | 0 | 94.1176 | 0.94118 | 2016-11-07
3 | Complaints | Functional Specification | 8 | 1 | 0 | 0 | 87.5 | 0.875 | 2016-11-07
4 | Indexing | Use case | 4 | 1 | 0 | 0 | 75 | 0.75 | 2016-11-07
5 | Policy | Functional Specification | 25 | 8 | 0 | 0 | 68 | 0.68 | 2016-11-07
6 | Security | Functional Specification | 4 | 1 | 0 | 0 | 75 | 0.75 | 2016-11-07
S. No | Document Name | Document Type | Total No Original Requirements | No of Requirements Changed | No of Requirements added | No of Requirements deleted | Requirement Stability % | Requirement Stability Index | Tracked Date (DD/MM/YYYY)
1 | Claims | Functional Specification | 55 | 3 | 2 | 0 | 90.9091 | 0.90909 | 2016-11-07
2 | Complaints | Functional Specification | 8 | 1 | 0 | 0 | 87.5 | 0.875 | 2016-11-07
3 | Indexing | Use case | 4 | 1 | 0 | 0 | 75 | 0.75 | 2016-11-07
4 | Policy | Functional Specification | 25 | 8 | 0 | 0 | 68 | 0.68 | 2016-11-07
5 | Security | Functional Specification | 4 | 1 | 0 | 0 | 75 | 0.75 | 2016-11-07
6 | Integration Overview | Functional Specification | 12 | 1 | 0 | 0 | 91.6667 | 0.91667 | 2016-11-07
7 | BIRI | Customization Sheet | 23 | 4 | 0 | 0 | 82.6087 | 0.82609 | 2016-11-07
8 | CI | Customization Sheet | 13 | 2 | 0 | 0 | 84.6154 | 0.84615 | 2016-11-07
9 | Correspondent | Customization Sheet | 2 | 1 | 0 | 0 | 50 | 0.5 | 2016-11-07
10 | Document Generation | Functional Specification | 9 | 1 | 0 | 0 | 88.8889 | 0.88889 | 2016-11-07

## Revision Entry
S. No | Document Name | Document Type | Revisied Version | Module Impacted | Test Scenario Revision | Test Case Revision | Test Scenario Revised | Test Cases Revised | Tracked By | Tracked Date (MM/DD/YYYY) | Impacted hours (in hr) | Impacted Cost (in $)
1 | Claims | Functional Specification | 1.1 | Module 2.0 | Deleted | NA | 19 |  | Lincy J | 2016-06-06 | 0.95 | 24.7
2 | Claims | Functional Specification | 1.1 | Module 3.0 | Updated | NA | 1 |  | Lincy J | 2016-06-06 | 0.1 | 2.6
3 | Claims | Functional Specification | 1.1 | Module 3.0 | Deleted | NA | 3 |  | Lincy J | 2016-06-06 | 0.15 | 3.9
4 | Claims | Functional Specification | 1.1 | Module 12.0 | Deleted | NA | 5 |  | Lincy J | 2016-06-06 | 0.25 | 6.5
5 | Policy | Functional Specification | 1.1 | Module 3.0 | Updated | Updated | 3 | 10 | Dharshan | 2016-05-20 | 1.9667 | 51.1333
6 | Policy | Functional Specification | 1.1 | Module 3.0 | Updated | Added | 13 | 40 | Dharshan | 2016-05-20 | 14.6333 | 380.4667
7 | Policy | Functional Specification | 1.1 | Module 6.0 | Added | Added | 4 | 12 | Shyam | 2016-05-20 | 4.8 | 124.8
8 | Policy | Functional Specification | 1.1 | Module 7.0 | Updated | Added | 4 | 10 | Shyam | 2016-05-20 | 3.73 | 96.98
9 | Policy | Functional Specification | 1.1 | Module 9.0 | Deleted | Deleted | 4 | 9 | Prashanth Radhakrishnan | 2016-05-20 | 0.95 | 24.7
10 | Policy | Functional Specification | 1.1 | Module 14.0 | Added | Added | 2 | 6 | Prashanth Radhakrishnan | 2016-05-20 | 2.4 | 62.4
11 | Policy | Functional Specification | 1.1 | Module 20.0 | Added | Added | 3 | 17 | Dhanwandhi P | 2016-05-20 | 6.27 | 163.02
12 | Policy | Functional Specification | 1.1 WIP | Module 17.0 | NA | Deleted |  | 12 | Lincy J | 2016-06-08 | 1 | 26
13 | Policy | Functional Specification | 1.1 WIP | Module 18.0 | NA | Added |  | 19 | Lincy J | 2016-06-08 | 6.3333 | 164.6667
14 | Indexing | Use case | UC028 |  | NA | Added |  | 3 | Lincy J | 2016-06-13 | 1 | 26
15 | Claims | Customization Sheet | 1.03 |  | Added | Added | 12 | 12 | Rishabh Karn | 2016-06-14 | 6.4 | 166.4
16 | Complaints | Functional Specification | 1 | Module 2.0 | Added | NA | 2 |  | Rashi Dhama | 2016-06-17 | 0.4 | 10.4
17 | Complaints | Functional Specification | 1 | Module 2.0 | Updated | NA | 30 |  | Rashi Dhama | 2016-06-17 | 3 | 78
18 | Security | Functional Specification | 0.81 | Module 2.0 | Added | Added | 2 | 8 | Sivakumar V | 2016-06-21 | 3.0667 | 79.7333
19 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Updated |  | 49 | Sivakumar V | 2016-06-21 | 8.1667 | 212.3333
20 | Security | Functional Specification | 0.81 | Module 2.0 | Added | Added | 3 | 10 | Lincy J | 2016-06-22 | 3.9333 | 102.2667
23 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 6 | Sivakumar V | 2016-06-22 | 2 | 52
25 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 6 | Sivakumar V | 2016-06-23 | 2 | 52
26 | Security | Functional Specification | 0.81 | Module 2.0 | Added | Added | 3 | 24 | Lincy J | 2016-06-23 | 8.6 | 223.6
27 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Updated |  | 3 | Lincy J | 2016-06-23 | 0.5 | 13
28 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 8 | Sivakumar V | 2016-06-24 | 2.6667 | 69.3333
29 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Deleted |  | 2 | Sivakumar V | 2016-06-24 | 0.16667 | 4.3333
30 | Security | Functional Specification | 0.81 | Module 2.0 | Updated | Deleted | 1 | 6 | Lincy J | 2016-06-28 | 0.6 | 15.6
31 | Security | Functional Specification | 0.81 | Module 2.0 | Deleted | Added | 7 | 11 | Lincy J | 2016-06-28 | 4.0167 | 104.4333
32 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Updated |  | 3 | Lincy J | 2016-06-28 | 0.5 | 13
33 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Deleted |  | 7 | Lincy J | 2016-06-29 | 0.58333 | 15.1667
34 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 10 | Lincy J | 2016-06-29 | 3.3333 | 86.6667
35 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 4 | Lincy J | 2016-06-30 | 1.3333 | 34.6667
36 | Integration Overview | Functional Specification | 0.8 |  | NA | Updated |  | 40 | Vishak | 2016-06-30 | 6.6667 | 173.3333
37 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 9 | Lincy J | 2016-07-01 | 3 | 78
38 | Security | Functional Specification | 0.81 | Module 2.0 | NA | Added |  | 9 | Lincy J | 2016-07-04 | 3 | 78
39 | BIRI | Customization Sheet | 0.5 |  | NA | Added |  | 8 | Vishnu Sundara Rajan | 2016-07-04 | 2.6667 | 69.3333
40 | BIRI | Customization Sheet | 0.5 |  | NA | Updated |  | 6 | Vishnu Sundara Rajan | 2016-07-04 | 1 | 26
41 | CI | Customization Sheet | 1 |  | NA | Added |  | 2 | Vishnu Sundara Rajan | 2016-07-04 | 0.66667 | 17.3333
42 | CI | Customization Sheet | 1 |  | NA | Updated |  | 4 | Vishnu Sundara Rajan | 2016-07-04 | 0.66667 | 17.3333
43 | Correspondent | Customization Sheet | 0.7 |  | NA | Added |  | 1 | Lipsita | 2016-07-05 | 0.33333 | 8.6667
44 | Correspondent | Customization Sheet | 0.7 |  | NA | Updated |  | 4 | Lipsita | 2016-07-05 | 0.66667 | 17.3333
45 | Document Generation | Functional Specification | 0.72 | Module 2.0 | Updated | NA | 10 |  | Banu Priya S | 2016-07-06 | 1 | 26
46 | Document Generation | Functional Specification | 0.72 | Module 2.0 | Deleted | NA | 3 |  | Banu Priya S | 2016-07-06 | 0.15 | 3.9
47 | Document Generation | Functional Specification | 0.72 | Module 2.0 | NA | Deleted |  | 8 | Banu Priya S | 2016-07-08 | 0.66667 | 17.3333
48 | Document Generation | Functional Specification | 0.72 | Module 2.0 | NA | Added |  | 5 | Banu Priya S | 2016-07-08 | 1.6667 | 43.3333
49 | Claims | Customization Sheet | 1.04 |  |  | Updated |  | 27 | Shyam | 2016-07-14 | 4.5 | 117
50 | Claims | Customization Sheet | 1.04 |  |  | Deleted |  | 10 | Shyam | 2016-07-14 | 0.83333 | 21.6667
51 | Claims | Customization Sheet | 1.04 |  |  | Added |  | 2 | Shyam | 2016-07-14 | 0.66667 | 17.3333
52 | [10 empty] | 0 | 0
53 | [10 empty] | 0 | 0
54 | [10 empty] | 0 | 0
55 | [10 empty] | 0 | 0
56 | [10 empty] | 0 | 0
57 | [10 empty] | 0 | 0
58 | [10 empty] | 0 | 0
59 | [10 empty] | 0 | 0
60 | [10 empty] | 0 | 0
61 | [10 empty] | 0 | 0
62 | [10 empty] | 0 | 0
63 | [10 empty] | 0 | 0
64 | [10 empty] | 0 | 0
65 | [10 empty] | 0 | 0
66 | [10 empty] | 0 | 0
67 | [10 empty] | 0 | 0
68 | [10 empty] | 0 | 0
69 | [10 empty] | 0 | 0
70 | [10 empty] | 0 | 0
71 | [10 empty] | 0 | 0
72 | [10 empty] | 0 | 0
73 | [10 empty] | 0 | 0
74 | [10 empty] | 0 | 0
75 | [10 empty] | 0 | 0
76 | [10 empty] | 0 | 0
77 | [10 empty] | 0 | 0
78 | [10 empty] | 0 | 0
79 | [10 empty] | 0 | 0
80 | [10 empty] | 0 | 0
81 | [10 empty] | 0 | 0
82 | [10 empty] | 0 | 0
83 | [10 empty] | 0 | 0
84 | [10 empty] | 0 | 0
85 | [10 empty] | 0 | 0
86 | [10 empty] | 0 | 0
87 | [10 empty] | 0 | 0
88 | [10 empty] | 0 | 0
89 | [10 empty] | 0 | 0
90 | [10 empty] | 0 | 0
91 | [10 empty] | 0 | 0
92 | [10 empty] | 0 | 0
93 | [10 empty] | 0 | 0
94 | [10 empty] | 0 | 0
95
96
97
98
99
100
| Security | Functional Specification | 0.81 | Module 2.0 | NA | Updated |  | 3 | Lincy J | 2016-06-28

## Input
S. No | Document Name | S. No | Document Type | S. No | Revisied Version | S. No | Module Impacted | S. No | TS Revision | Efforts in Hrs | S. No | TC Revision | Efforts in Hrs | S. No | Tracked By
1 | Policy | 1 | Functional Specification | 1 | V0.5 | 1 | Module 1.0 | 1 | NA | 0 | 1 | NA | 0 | 1 | Balaji Sivarajan
2 | Claims | 2 | Customization Sheet | 2 | V0.6 | 2 | Module 2.0 | 2 | Updated | 0.1 | 2 | Updated | 0.16667 | 2 | Kesiya T R
3 | BIRI | 3 | ASPAC_Customization Sheet | 3 | V0.7 | 3 | Module 3.0 | 3 | Added | 0.2 | 3 | Added | 0.33333 | 3 | Terasa Santhi M
4 | CI | 4 | LATAM_Customization Sheet | 4 | V0.8 | 4 | Module 4.0 | 4 | Deleted | 0.05 | 4 | Deleted | 0.083333 | 4 | Bargavi R
5 | Complaints | 5 | EMEA_Customization Sheet | 5 | V0.9 | 5 | Module 5.0 | [6 empty] | 5 | Manoj Sharma
6 | Overview | 6 | Use case | 6 | V1.0 | 6 | Module 6.0 | [6 empty] | 6 | Banu Priya S
7 | Security |  |  | 7 | V1.1 | 7 | Module 7.0 | [6 empty] | 7 | Lincy J
8 | Ingestion |  |  | 8 | V1.2 | 8 | Module 8.0 | [6 empty] | 8 | Rashi Dhama
9 | Indexing |  |  | 9 | V1.3 | 9 | Module 9.0 | [6 empty] | 9 | Sivakumar V
10 | Integration Overview |  |  | 10 | V1.4 | 10 | Module 10.0 | [6 empty] | 10 | Vishnu Sundara Rajan
11 | Correspondent |  |  | 11 | V1.5 | 11 | Module 11.0 | [6 empty] | 11 | Prashanth Radhakrishnan
12 | Document Generation |  |  | 12 | V1.6 | 12 | Module 12.0 | [6 empty] | 12 | Dhanwandhi P
|  |  |  | 13 | V1.7 | 13 | Module 13.0 | [6 empty] | 13 | Rishabh Karn
|  |  |  | 14 | V1.8 | 14 | Module 14.0 | [6 empty] | 14 | Dharshan
|  |  |  | 15 | V1.9 | 15 | Module 15.0 | [6 empty] | 15 | Shyam
|  |  |  | 16 | V0.10 | 16 | Module 16.0 | [6 empty] | 16 | Vishak
|  |  |  | 17 | V0.11 | 17 | Module 17.0 | [6 empty] | 17 | Lipsita
|  |  |  | 18 | V0.12 | 18 | Module 18.0
|  |  |  | 19 | V0.13 | 19 | Module 19.0
|  |  |  | 20 | V0.14 | 20 | Module 20.0
|  |  |  | 21 | V0.15 | 21 | Module 21.0
|  |  |  | 22 | V0.16 | 22 | Module 22.0
|  |  |  | 23 | V0.17 | 23 | Module 23.0
|  |  |  | 24 | V0.18 | 24 | Module 24.0
|  |  |  | 25 | V0.19 | 25 | Module 25.0
|  |  |  | 26 | V0.20 | 26 | Module 26.0
|  |  |  | 27 | V0.21 | 27 | Module 27.0
|  |  |  | 28 | V0.22 | 28 | Module 28.0
|  |  |  | 29 | V0.23 | 29 | Module 29.0
|  |  |  | 30 | V0.24 | 30 | Module 30.0
|  |  |  | 31 | V0.25
|  |  |  | 32 | V0.26
|  |  |  | 33 | V0.27
|  |  |  | 34 | V0.28
|  |  |  | 35 | V0.29
|  |  |  | 36 | V0.30

## Annexure (hidden)
S. No | Component Name | Environment Name | Environment Owner / PoC