## Slide 1: Apollo Refresh Testing - Status
30th August 2014

## Slide 2
Week of: 24th Aug to 30th Aug | Project Manager | Annie Schmetzer | Onsite Test Manager | Aravind Ravichandar | RAG Status Last week |  | RAG Status This week | 
Progress Headlines |  |  |  | 
Understanding of Peoplesoft & Mercury Integration was completed. Understanding on Bookmarks functional area completed. Clarification logs and Observation logs for Notes, Flags &Milestones, PeopleSoft Integration, Indexing, Search templates and Correspondents updates are in –progress NFT-Understanding application landscape, Biz talk , Integration Environment and system documentation for the performance testing use case was completed. |  |  |  | 
Focus for Next Period |  |  |  | 
Wireframe Design – Understanding of Workflow, In -baskets and User Asynchronous Document Import use cases. Ingestion Methods – Understanding of all Use cases File Net –(Redaction/Split & Merge ) Understanding the Environments and Test regions. |  |  |  | 
Key Deliverable Milestones |  |  |  | 
SCOPE | Key Activity | FORECAST | RAG | STATUS SUMMARY
Vega Unity Design- Use case | Overview of Use cases and Core cuss | 15th Aug | COMPLETE | Discussions completed with Simon.
 | Drag and Drop –Use cases | 15th Aug | COMPLETE | Discussion with John completed. Requested for access to the Proof of concept URL for more understanding and understanding the performance testing requirements. Separate meeting to be scheduled for non functional requirements around drap and drop use cases.
 | Wireframe Demo | 30th Aug | G | Discussions with Garima in progress. Planned to be part of the walkthrough sessions for Vega.
Core Platform and Application | Use cases – Mercury and PeopleSoft Integration | 30th Aug | G | Discussion in progress with John
 | Mercury and PeopleSoft Integration- BIZ Talk | 07th Sep | G | Discussion in progress with Abdul. Further meetings planned to discuss on the non functional requirement around BizTalk for mercury and people soft integrations. Performance test lead is being on boarded at offshore from 08/28 and will join these sessions to understand the non functional requirement for BIZ Talk.
 | Expressions Interface Design-PO template | 20th Aug | COMPLETE | Session with Sangari completed. Additional information on other templates were provided by John (PO,T&E)
Track – Testing Updates
Status Headlines:
  Devised a plan to gather knowledge towards building a develop a comprehensive test strategy for functional and non functional testing. Had initial round of meetings with BA’s and SME’s to understand the business objectives of the program and the Use case structuring /documentations/ folder structures.
Notes: 2

## Slide 3
Track – Testing Updates
Key Deliverable Milestones |  |  |  | 
 | Key Activity | FORECAST | RAG | STATUS SUMMARY /Remarks
File Net | Document Bookmarks Design | Aug-27th | G | Knowledge Gathering session scheduled with Pradeep
 | Redaction/Split & Merge Document | Aug-28th | G | Knowledge Gathering session scheduled with Pradeep
 | Replacement of Vignette Web service Toolkit | Aug-29th | G | Knowledge Gathering session scheduled with Pradeep
Global/ Core | Enterprise Search | Sep 04th | G | Meetings to be scheduled
 | Security Features and Roles setup | Sep 08th | G | Meetings to Scheduled.
Key Functions | Performance Test Requirements | Sep 13th | G | Performance Test lead is on boarded at offshore from 28th Aug to define the plan for the non functional Requirements.
 | Test environment and environment requirements | Sep13th | G | 
 | Build Plan- Code Drop Delivery Dates | Sep 10th | G | This is needed to come up with the test design plan and the execution plan based on the dependencies.
 | Test Data Requirements | Sep 9th | G | Identification of the Unique Test data requirements for functional coverage through data will be collected during the functional KT sessions.
 | Test Process | Sep 13th | G | Understand the current processes and procedures followed for various QA activities
Define Test Strategy | Identify major milestones in the implementation plan- Test Plan | Sep 19th | G | 
 | Determine anticipated QA budget /Effort for the Test design Phase and high level resource plan for testing for 2014 | Sep 22th | G | 
 | Construct an overall Program implementation plan blending the current state activities and Program goals for: Master test strategy | Sep 27th | G | 
Sign of Test Strategy | Master Test Strategy-Review and Sign off QA strategy | Oct-01 | G | 
Notes: 3

## Slide 4
Track – Testing Updates
Risks & Dependencies / Items Not considered
Following Requirements were not considered for Planning Wave 2 –NA requirements( Would be tracked outside of this) Track 3 – Document Migration Data Migration –Not covered for this planning
Notes: 4

## Slide 5: Appendices
5

## Slide 6: Release 1 Work Breakdown – version 1.4