## AR-ASPAC-Relase 1 - Test cases
Components Stability Matrix - Heat Map | Test Execution % | Pass % | Overall Open Defects | Open P1 and P2 | Component Stability | Status | Test Cases | Build - 1A |  |  | Build - 1B |  |  | Build - 1C |  |  | Overall Status |  |  | Stability Stats |  | Defects Trend - Priority Defects
[6 empty] | Status | Test Cases | Pass | Fail | NA | Pass | Fail | NA | Pass | Fail | NA | Pass | Fail | NA | Completion % | Pass % | Overall Defects | Effective Open Defects | Open - P1 and P2 Defects
Bar Code Generation | 100% | 100% | 4 | 0 |  | Completed | 91 | 67 | 24 | 0 | 2 | 22 | 0 | 22 | 0 | 0 | 91 | 0 | 0 | 100% | 100% | 33 | 4 | 0
Email Broker | 100% | 97.96% | 0 | 0 |  | Completed | 98 | 86 | 12 | 0 | 8 | 4 | 0 | 2 | 1 | 1 | 96 | 1 | 1 | 100% | 97.96% | 7 | 0 | 0
Datacap Scanning | 100% | 100% | 2 | 0 |  | Completed | 267 | 259 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 267 | 0 | 0 | 100% | 100% | 14 | 2 | 0
Viewer Configuration | 100% | 100% | 0 | 0 |  | Completed | 88 | 87 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 100% | 100% | 27 | 0 | 0
Document Generation | 100% | 100% | 5 | 0 |  | Completed | 33 | 23 | 10 | 0 | 3 | 7 | 0 | 7 | 0 | 0 | 33 | 0 | 0 | 100% | 100% | 30 | 5 | 0
Send Email Build | 100% | 100% | 0 | 0 |  | Completed | 15 | 8 | 7 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 15 | 0 | 0 | 100% | 100% | 10 | 0 | 0
1A - Final | [6 empty] | 592 | 530 | 62 | 0 | 22 | 41 | 0 | 39 | 1 | 1 | 590 | 1 | 1
ACEView Print | 100% | 93.75% | 1 | 0 |  | Completed | 16 | NA |  |  | 15 | 1 | 0 | 0 | 1 | 0 | 15 | 1 | 0 | 100% | 93.75% | 3 | 1 | 0
Upload Documents | 100% | 100% | 6 | 1 |  | Completed | 33 |  |  |  | 27 | 3 | 3 | 6 | 0 | 0 | 33 | 0 | 0 | 100% | 100% | 11 | 6 | 1
Drag & Drop | 100% | 97.65% | 3 | 1 |  | Completed | 85 |  |  |  | 46 | 14 | 25 | 37 | 2 | 0 | 83 | 2 | 0 | 100% | 97.65% | 20 | 3 | 1
Diary | 100% | 97.06% | 8 | 1 |  | Completed | 34 |  |  |  | 33 | 1 | 0 | 0 | 1 | 0 | 33 | 1 | 0 | 100% | 97.06% | 21 | 8 | 1
Daeja - Security - Integration | 100% | 100% | 3 | 1 |  | Completed | 34 |  |  |  | 33 | 1 | 0 | 1 | 0 | 0 | 34 | 0 | 0 | 100% | 100% | 8 | 3 | 1
Alerts & Notification | 100% | 95.24% | 3 | 0 |  | Completed | 21 |  |  |  | 20 | 1 | 0 | 0 | 1 | 0 | 20 | 1 | 0 | 100% | 95.24% | 6 | 3 | 0
Workbasket | 100% | 95.24% | 29 | 3 |  | Completed | 42 |  |  |  | 29 | 11 | 2 | 11 | 2 | 0 | 40 | 2 | 0 | 100% | 95.24% | 57 | 29 | 3
Notes | 100% | 95.77% | 4 | 0 |  | Completed | 71 |  |  |  | 59 | 10 | 2 | 9 | 3 | 0 | 68 | 3 | 0 | 100% | 95.77% | 16 | 4 | 0
ASPAC workflow | 100% | 94.58% | 23 | 3 |  | Completed | 295 |  |  |  | 178 | 69 | 48 | 101 | 16 | 0 | 279 | 16 | 0 | 100% | 94.58% | 165 | 23 | 3
Send Fax | 100% | 100% | 0 | 0 |  | Completed | 21 |  |  |  | 14 | 3 | 4 | 7 | 0 | 0 | 21 | 0 | 0 | 100% | 100% | 11 | 0 | 0
Security | 100% | 100% | 0 | 0 |  | Completed | 139 |  |  |  | 86 | 0 | 53 | 53 | 0 | 0 | 139 | 0 | 0 | 100% | 100% | 24 | 0 | 0
1B - Final | [6 empty] | 791 | 0 | 0 | 0 | 540 | 114 | 137 | 225 | 26 | 0 | 765 | 26 | 0
Flags and Milestone | 100% | 100% | 3 | 2 |  | Completed | 32 | NA | [5 empty] | 32 | 0 | 0 | 32 | 0 | 0 | 100% | 100% | 10 | 3 | 2
Correspondents | 100% | 80.95% | 3 | 0 |  | Completed | 21 | [6 empty] | 17 | 4 | 0 | 17 | 4 | 0 | 100% | 80.95% | 12 | 3 | 0
Manage User Preference | 100% | 97.53% | 2 | 3 |  | Completed | 81 | [6 empty] | 79 | 2 | 0 | 79 | 2 | 0 | 100% | 97.53% | 23 | 2 | 3
Email_ACEView Integration | 100% | 95% | 2 | 0 |  | Completed | 40 | [6 empty] | 38 | 2 | 0 | 38 | 2 | 0 | 100% | 95% | 3 | 2 | 0
Open File and Open Case | 100% | 86.07% | 56 | 1 |  | Completed | 201 | [6 empty] | 173 | 22 | 6 | 173 | 22 | 6 | 100% | 86.07% | 85 | 56 | 1
Workflow Design | 100% | 90.7% | 6 | 1 |  | Completed | 43 | [6 empty] | 39 | 4 | 0 | 39 | 4 | 0 | 100% | 90.7% | 21 | 6 | 1
Security_ACEView Integration | 100% | 97.5% | 3 | 0 |  | Completed | 40 | [6 empty] | 39 | 1 | 0 | 39 | 1 | 0 | 100% | 97.5% | 30 | 3 | 0
Scanning_ACEView Integration | 100% | 95% | 0 | 0 |  | Completed | 60 | [6 empty] | 57 | 3 | 0 | 57 | 3 | 0 | 100% | 95% | 3 | 0 | 0
Search Template | 100% | 81.9% | 32 | 1 |  | Completed | 116 | [6 empty] | 95 | 21 | 0 | 95 | 21 | 0 | 100% | 81.9% | 85 | 32 | 1
1C - Final | [6 empty] | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 569 | 59 | 6 | 569 | 59 | 6
Legends | > 90% | > 90% | < 10 | 0 | Stable | Total | 2017 | 530 | 62 | 0 | 562 | 155 | 137 | 833 | 86 | 7 | 1924 | 86 | 7 |  | 95.39% | 735 | 198 | 18
| < 90% & >70% | < 90% & >70% | > 10 & < 20 | > 0 & < 5 | Partially Stable
| > 70% | > 70% | > 20 | > 5 | Need Immediate Attention

## For Deck
Stable Components:
Components Stability Matrix - Heat Map | Test Execution % | Pass % | Overall Open Defects | Open P1 and P2 | Component Stability
Bar Code Generation | 100% | 100% | 4 | 0
Email Broker | 100% | 98% | 0 | 0
Datacap Scanning | 100% | 100% | 0 | 0
Viewer Configuration | 100% | 100% | 0 | 0
Document Generation | 100% | 97% | 1 | 0
Send Email Build | 100% | 100% | 0 | 0
ACEView Print | 100% | 94% | 0 | 0
Upload Documents | 100% | 100% | 3 | 1
Diary | 100% | 97% | 9 | 1
Daeja - Security - Integration | 100% | 100% | 1 | 1
Alerts & Notification | 100% | 95% | 3 | 0
Notes | 100% | 96% | 1 | 0
Send Fax | 100% | 100% | 0 | 0
Security | 100% | 100% | 0 | 0
Flags and Milestone | 100% | 100% | 3 | 2
Correspondents | 100% | 76% | 3 | 0
Manage User Preference | 100% | 75% | 5 | 3
Email_ACEView Integration | 100% | 95% | 3 | 1
Workflow Design | 100% | 91% | 6 | 1
Security_ACEView Integration | 100% | 95% | 5 | 2
Scanning_ACEView Integration | 100% | 95% | 1 | 0
Nearing Stable - Components:
Drag & Drop | 100% | 95% | 5 | 3
Needs Attention / Unstable - Components:
ASPAC workflow | 100% | 95% | 30 | 6
Workbasket | 100% | 95% | 31 | 4
Open File and Open Case | 100% | 84% | 54 | 7
Search Template | 100% | 49% | 41 | 7
Legends | > 90% | > 90% | < 10 | 0 | Stable
| < 90% & >70% | < 90% & >70% | > 10 & < 20 | > 0 & < 5 | Partially Stable
| <70% & > 50% | <70% & > 50% | > 20 & < 30 | > 5 & < 10 | Need Immediate Attention
| <50% | <50% | > 30 | > 10 | UnStable