## Executive Summary
ACEView Programme - Testing Dashboard
|  | Report Date : | 2015-05-28 |  | Execution Progress (%) |  | 92.31% |  |  | Planned Completion - 1C Cycle 1 |  | 2015-05-23 | Quality RAG
[10 empty] | Expected Completion -1C - Cycle 1 |  | 2015-05-29 | Schedule RAG
[10 empty] | Error Discovery Rate |  | 0.83333
Key Highlights
| Updates for the Day: * Po files were created and posted into Peoplesoft today. The batch results will be analysed and results will be shared tomorrow. * 92% execution progress and 90% Pass percentage were observed * 2 Critical and 24 High Priority defects are Open | [9 empty] | Low Lights of the day: * The failed testcases of 1A, 1B and 1C are being executed in End to End cycle 1, as per the defect fixes
| Items that need Immediate Attention: * 1 Critical Defect need to be addressed immediately * P1 and P2 defects without planned fix date need to be updated with appropriate fix date | [9 empty] | Task for Tomorrow: * PeopleSoft Integration testing
| Road To Green: * All the P1 and P2 defects need to be fixed before the final build in SIT(June 08th) | [9 empty] | Defect Build Status for (26 Open)P1 and P2 Defects: No Planned Fix Date - 6 29/05/2015 - 13 02/06/2015 - 5 04/06/2015 - 2 08/06/2015 - 0
Test Execution Progress - End to End - Cycle 1
Failed Testcases + Defect Retesting
1A+1B+1C Failed Testcases Execution Progress
| Components |  | Total TC | Passed | Failed | Not Completed | No Run | N/A | Blocked | Execution % | Pass % | Defect Retesting Contigency
| Failed testcases 1A |  | 10 | 8 | 1 | 0 | 0 | 1 | 0 | 90% | 88.89% | Components | Total Defects Contigency | Closed | Re-opened
| Failed testcases 1B |  | 32 | 15 | 1 | 0 | 16 | 0 | 0 | 50% | 93.75% | Defect Retesting | 38 | 29 | 8
| Failed testcases 1C |  | 171 | 111 | 59 | 1 | 0 | 0 | 0 | 100% | 65.29% | Total | 38 | 29 | 8
| Total |  | 213 | 134 | 61 | 1 | 16 | 1 | 0 | 92.02% | 68.72%
Defect Summary Status - ASPAC
Overall Open Defects - Severity
[14 empty] | 1 - Critical | 2 - High | 3 - Medium | 4 - Low
[14 empty] | 0 | 16 | 167 | 79
Overall Open Defects - Priority
[14 empty] | 1 - Critical | 2 - High | 3 - Medium | 4 - Low
[14 empty] | 2 | 24 | 155 | 81
Defects Key Inference

## Executive Summary Data (hidden)
Component wise Execution report
Release | Release - Cycle | Components | Total TC | Passed | Failed | Not Completed | No Run | N/A | Blocked | Passed% | Failed% | Not Completed% | No Run% | N/A% | Blocked%
Release 1_ASPAC | End to End - Cycle 1 | E2E PO | 148 | 129 | 19 | 0 | 0 | 0 | 0 | 87.16% | 12.84% | 0% | 0% | 0% | 0%
|  | E2E TE | 152 | 141 | 11 | 0 | 0 | 0 | 0 | 92.76% | 7.237% | 0% | 0% | 0% | 0%
|  | PeopleSoft Integration | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
|  | Total | 330 | 270 | 30 | 0 | 30 | 0 | 0 | 81.82% | 9.091% | 0% | 9.091% | 0% | 0%
Release | Release - Cycle | Components | Total TC | Passed | Failed | Not Completed | No Run | N/A | Blocked | Passed% | Failed% | Not Completed% | No Run% | N/A% | Blocked%
Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | 10 | 8 | 1 | 0 | 0 | 1 | 0 | 80% | 10% | 0% | 0% | 10% | 0%
|  | Failed testcases 1B | 32 | 15 | 1 | 0 | 16 | 0 | 0 | 46.88% | 3.125% | 0% | 50% | 0% | 0%
|  | Failed testcases 1C | 171 | 111 | 59 | 1 | 0 | 0 | 0 | 64.91% | 34.5% | 0.5848% | 0% | 0% | 0%
| Total |  | 213 | 8 | 1 | 0 | 0 | 1 | 0 | 3.756% | 0.4695% | 0% | 0% | 0.4695% | 0%
Component wise Defect report
Release Name | Cycle Name | Component Name | New | Open | Active | In Progress | Fixed | Ready for System Test | Retest Dependency | Failed Retest | Ready for Business Test | Re-Opened | Put On Hold | Total | Deferred | Rejected | Closed | Total
Release 1_ASPAC | End to End - Cycle 1 | ACEView | 25 | 19 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 3 | 2 | 57 | 3 | 0 | 80 | 140
|  | ACEViewPrint | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 3
|  | Alerts & Notification | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 6
|  | ASPAC Peoplesoft Integration | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 16 | 17
|  | ASPAC Workflow | 7 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 20 | 0 | 0 | 145 | 165
|  | Barcode Generation | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 29 | 33
|  | Daeja_Viewer ACEView Integration | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 5 | 8
|  | Diary | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 13 | 21
|  | Datacap Scanning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
|  | Document Generation | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 25 | 31
|  | Drag and Drop | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 17 | 20
|  | Email | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
|  | Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
|  | Notes | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 12 | 16
|  | Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24
|  | Send Email | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 12
|  | Send Fax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11
|  | Upload Document | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 5 | 11
|  | Viewer Configuration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 25 | 27
|  | Open File and Open Case | 24 | 29 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 0 | 29 | 86
|  | Flags and Milestones | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 6 | 10
|  | Correspondents | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 9 | 12
|  | Search Template | 19 | 11 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 36 | 1 | 0 | 51 | 88
|  | Workflow Design | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 15 | 21
|  | Manage User Preference | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 24 | 25
|  | Look Ups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Security_ACEView Integration | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 26 | 30
|  | Email_ACEView Integration | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 3
|  | Scanning_ACEView Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
|  | Workbasket | 8 | 12 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 5 | 0 | 30 | 0 | 0 | 28 | 58
| Total |  | 105 | 101 | 0 | 10 | 18 | 3 | 1 | 0 | 0 | 19 | 5 | 262 | 7 | 0 | 646 | 915
Component wise Open Defects
Release wise Open defects |  |  |  | Defect Severity |  |  |  | Defect Priority
Release Name | Cycle Name | Component Name | Open Defects | 1 - Critical | 2 - High | 3 - Medium | 4 - Low | 1 - Critical | 2 - High | 3 - Medium | 4 - Low
Release 1_ASPAC | End to End - Cycle 1 | ACEView | 57 | 0 | 3 | 30 | 24 | 1 | 7 | 24 | 25
|  | ACEViewPrint | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
|  | Alerts & Notification | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 2
|  | ASPAC Peoplesoft Integration | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
|  | ASPAC Workflow | 20 | 0 | 1 | 14 | 5 | 0 | 1 | 13 | 6
|  | Barcode Generation | 4 | 0 | 0 | 3 | 1 | 0 | 0 | 3 | 1
|  | Daeja_Viewer ACEView Integration | 3 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1
|  | Diary | 8 | 0 | 1 | 4 | 3 | 0 | 1 | 4 | 3
|  | Datacap Scanning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Document Generation | 6 | 0 | 0 | 4 | 2 | 0 | 0 | 4 | 2
|  | Drag and Drop | 3 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1
|  | Email | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Notes | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
|  | Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Send Email | 4 | 0 | 3 | 1 | 0 | 1 | 2 | 1 | 0
|  | Send Fax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Upload Document | 6 | 0 | 0 | 4 | 2 | 0 | 1 | 3 | 2
|  | Viewer Configuration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Open File and Open Case | 56 | 0 | 0 | 42 | 14 | 0 | 0 | 42 | 14
|  | Flags and Milestones | 4 | 0 | 3 | 1 | 0 | 0 | 3 | 1 | 0
|  | Correspondents | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 1
|  | Search Template | 36 | 0 | 2 | 22 | 12 | 0 | 2 | 22 | 12
|  | Workflow Design | 6 | 0 | 0 | 5 | 1 | 0 | 1 | 4 | 1
|  | Manage User Preference | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
|  | Look Ups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Security_ACEView Integration | 4 | 0 | 1 | 1 | 2 | 0 | 1 | 1 | 2
|  | Email_ACEView Integration | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
|  | Scanning_ACEView Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Workbasket | 30 | 0 | 0 | 22 | 8 | 0 | 3 | 19 | 8
| Total |  | 262 | 0 | 16 | 167 | 79 | 2 | 24 | 155 | 81
Defect/Test Quality
Inflow Vs Out Flow - P1 and P2 Priority Defects
|  |  | Date | Open Defects on given day | Defects detected on given day | Defects closed on given day
|  |  | 08/05/2015 | 60 | 2 | 17
|  |  | 11/05/2015 | 67 | 9 | 2
|  |  | 12/05/2015 | 67 | 5 | 4
|  |  | 13/05/2015 | 59 | 6 | 16
|  |  | 14/05/2015 | 62 | 5 | 2
|  |  | 15/05/2015 | 56 | 6 | 12
|  |  | 18/05/2015 | 26 | 6 | 2
|  |  | 19/05/2015 | 54 | 5 | 12
|  |  | 20/05/2015 | 53 | 6 | 3
|  |  | 21/05/2015 | 57 | 1 | 0
|  |  | 22/05/2015 | 43 | 2 | 20
|  |  | 25/05/2015 | 32 | 0 | 0
|  |  | 26/05/2015 | 32 | 2 | 4
|  |  | 27/05/2015 | 26 | 2 | 9
|  |  | 28/05/2015 | 26 | 1 | 3

## Execution Report
Apollo Refresh - Release 1 - Test Execution Report |  |  | Test Execution - Planned Vs. Actual | [7 empty] | Test Execution - Status | [5 empty] | Test Execution - Eared Value |  |  |  | Test Execution - Defects
Planned Date | Release Name | Cycle Name | Planned Test Case | Actual Test Case | Daily TC Variance | Planned Cumulative Test Case | Actual Cumulative Test Case | Cumulative TC Variance | Planned Burndown | Actual Burndown | Passed | Failed | Blocked | No Run | N/A | Not Completed | % Passed | % Failed | % Executed | % Not Executed | Defects Logged | 1 - Critical | 2 - High | 3 - Medium | 4 - Low
08/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 20 | 15 | 5 | 20 | 15 | 5 | 325 | 325 | 14 | 1 | 0 | 0 | 0 | 0 | 93.33% | 6.667% | 75% | 25% | 12 | 0 | 1 | 7 | 7
09/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 20 | 0 | 20 | 305 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
10/05//2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 20 | 0 | 20 | 305 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
11/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 25 | 5 | 50 | 25 | 25 | 305 | 310 | 22 | 3 | 0 | 0 | 0 | 0 | 88% | 12% | 83.33% | 16.67% | 18 | 1 | 6 | 8 | 8
12/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 25 | 5 | 80 | 25 | 55 | 275 | 285 | 22 | 3 | 0 | 0 | 0 | 0 | 88% | 12% | 83.33% | 16.67% | 12 | 1 | 3 | 6 | 6
13/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 42 | -12 | 110 | 42 | 68 | 245 | 260 | 38 | 4 | 0 | 0 | 0 | 0 | 90.48% | 9.524% | 140% | -40% | 10 | 2 | 3 | 2 | 2
14/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 29 | 1 | 140 | 29 | 111 | 215 | 218 | 25 | 4 | 0 | 0 | 0 | 0 | 86.21% | 13.79% | 96.67% | 3.333% | 23 | 0 | 4 | 18 | 18
15/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 25 | 5 | 170 | 25 | 145 | 185 | 189 | 24 | 1 | 0 | 0 | 0 | 0 | 96% | 4% | 83.33% | 16.67% | 23 | 2 | 3 | 10 | 10
16/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 170 | 0 | 170 | 155 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
17/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 170 | 0 | 170 | 155 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
18/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 10 | 20 | 200 | 10 | 190 | 155 | 164 | 7 | 3 | 0 | 0 | 0 | 0 | 70% | 30% | 33.33% | 66.67% | 27 | 0 | 5 | 18 | 18
19/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 37 | -7 | 230 | 37 | 193 | 125 | 154 | 35 | 2 | 0 | 0 | 0 | 0 | 94.59% | 5.405% | 123.3% | -23.33% | 30 | 1 | 4 | 23 | 23
20/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 11 | 19 | 260 | 11 | 249 | 95 | 117 | 11 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 36.67% | 63.33% | 24 | 0 | 5 | 15 | 15
21/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 30 | 21 | 9 | 290 | 21 | 269 | 65 | 106 | 21 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 70% | 30% | 16 | 0 | 1 | 11 | 11
22/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 20 | 19 | 1 | 310 | 19 | 291 | 35 | 85 | 15 | 4 | 0 | 0 | 0 | 0 | 78.95% | 21.05% | 95% | 5% | 15 | 0 | 2 | 6 | 6
23/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 310 | 0 | 310 | 15 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
24/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 310 | 0 | 310 | 15 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
25/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 15 | 17 | -2 | 325 | 17 | 308 | 15 | 66 | 14 | 3 | 0 | 0 | 0 | 0 | 82.35% | 17.65% | 113.3% | -13.33% | 0 | 0 | 0 | 0 | 0
26/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 13 | -13 | 325 | 13 | 312 | 0 | 49 | 12 | 1 | 0 | 0 | 0 | 0 | 92.31% | 7.692% | 0% | 0% | 23 | 0 | 2 | 18 | 18
27/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 11 | -11 | 325 | 11 | 314 | 0 | 36 | 10 | 1 | 0 | 0 | 0 | 0 | 90.91% | 9.091% | 0% | 0% | 12 | 1 | 0 | 8 | 8
28/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 325 | 0 | 325 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 5 | 0 | 1 | 3 | 3
29/05/2015 | Release 1_ASPAC | End to End - Cycle 1 | 0 | 0 | 0 | 310 | 0 | 310 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
Release 1 : End to End - Cycle 1 Summary |  |  | 325 | 300 | 25 | 230 | 42 | 325 | 0 | 25 | 270 | 30 | 0 | 0 | 0 | 0 | 90% | 10% | 92.31% | 7.692% | 250 | 8 | 40 | 153 | 153

## Execution Dashboard (hidden)
Apollo Refresh - Release 1 - Build 1A - Cycle 1 : Test Execution Dashboard
Apollo Refresh - Release 1 - Build 1A - Cycle 2 : Test Execution Dashboard

## Execution Entry
S. No | Release Name | Cycle Name | Component Name | Test Name | Status | Execution Date | Tester Name | Priority
1 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC001 | Passed | 2015-05-08 | stsure
2 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC002 | Passed | 2015-05-08 | stsure
3 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC003 | Passed | 2015-05-08 | gxfati
4 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC004 | Passed | 2015-05-08 | aythom
5 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC005 | Passed | 2015-05-08 | axrath
6 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC006 | Failed | 2015-05-08 | szagar
7 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC007 | Passed | 2015-05-08 | akpand
8 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC008 | Passed | 2015-05-08 | stsure
9 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC009 | Passed | 2015-05-08 | stsure
10 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC010 | Passed | 2015-05-20 | gxfati
11 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC001_TC011 | Passed | 2015-05-20 | stsure
12 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC012 | Passed | 2015-05-08 | aythom
13 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC013 | Passed | 2015-05-08 | axrath
14 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC014 | Passed | 2015-05-08 | szagar
15 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC015 | Passed | 2015-05-08 | stsure
16 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC016 | Passed | 2015-05-08 | rxloga
17 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC017 | Passed | 2015-05-20 | stsure
18 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC018 | Passed | 2015-05-08 | aythom
19 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC019 | Passed | 2015-05-11 | gxfati
20 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC020 | Passed | 2015-05-11 | szagar
21 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC021 | Passed | 2015-05-11 | axrath
22 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC022 | Passed | 2015-05-11 | stsure
23 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC002_TC023 | Passed | 2015-05-11 | akpand
24 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC024 | Passed | 2015-05-11 | gxfati
25 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC025 | Passed | 2015-05-12 | aythom
26 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC026 | Passed | 2015-05-20 | stsure
27 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC027 | Passed | 2015-05-20 | stsure
28 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC028 | Passed | 2015-05-19 | akpand
29 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC029 | Passed | 2015-05-11 | axrath
30 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC030 | Failed | 2015-05-12 | sxtsat
31 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC031 | Passed | 2015-05-11 | akpand
32 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC032 | Passed | 2015-05-12 | aythom
33 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC033 | Passed | 2015-05-20 | stsure
34 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC003_TC034 | Passed | 2015-05-11 | szagar
35 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC035 | Passed | 2015-05-19 | akpand
36 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC036 | Passed | 2015-05-11 | stsure
37 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC037 | Failed | 2015-05-12 | sxtsat
38 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC038 | Passed | 2015-05-11 | gxfati
39 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC039 | Passed | 2015-05-11 | akpand
40 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC040 | Passed | 2015-05-11 | rxloga
41 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC041 | Passed | 2015-05-20 | szagar
42 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC042 | Passed | 2015-05-11 | akpand
43 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC043 | Failed | 2015-05-11 | stsure
44 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC004_TC044 | Passed | 2015-05-12 | sxtsat
45 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC045 | Failed | 2015-05-11 | gxfati
46 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC046 | Passed | 2015-05-11 | szagar
47 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC047 | Passed | 2015-05-11 | akpand
48 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC048 | Passed | 2015-05-11 | szagar
49 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC049 | Passed | 2015-05-11 | akpand
50 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC050 | Failed | 2015-05-11 | stsure
51 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC051 | Passed | 2015-05-12 | sxtsat
52 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC052 | Passed | 2015-05-11 | gxfati
53 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC053 | Passed | 2015-05-12 | aythom
54 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC005_TC054 | Passed | 2015-05-18 | axrath
55 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC055 | Passed | 2015-05-11 | akpand
56 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC056 | Passed | 2015-05-11 | akpand
57 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC057 | Passed | 2015-05-12 | stsure
58 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC058 | Passed | 2015-05-12 | sxtsat
59 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC059 | Passed | 2015-05-12 | gxfati
60 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC060 | Passed | 2015-05-12 | aythom
61 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC061 | Passed | 2015-05-18 | axrath
62 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC062 | Passed | 2015-05-11 | szagar
63 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC063 | Passed | 2015-05-12 | akpand
64 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC064 | Passed | 2015-05-14 | stsure
65 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC006_TC065 | Passed | 2015-05-12 | sxtsat
66 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC066 | Passed | 2015-05-12 | gxfati
67 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC067 | Passed | 2015-05-12 | aythom
68 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC068 | Passed | 2015-05-20 | stsure
69 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC069 | Passed | 2015-05-12 | szagar
70 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC070 | Passed | 2015-05-12 | akpand
71 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC071 | Passed | 2015-05-14 | stsure
72 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC072 | Passed | 2015-05-14 | sxtsat
73 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC073 | Passed | 2015-05-20 | gxfati
74 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC074 | Passed | 2015-05-12 | aythom
75 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC075 | Passed | 2015-05-21 | szagar
76 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC007_TC076 | Passed | 2015-05-12 | szagar
77 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC077 | Passed | 2015-05-12 | akpand
78 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC078 | Failed | 2015-05-12 | stsure
79 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC079 | Passed | 2015-05-14 | sxtsat
80 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC080 | Passed | 2015-05-14 | gxfati
81 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC081 | Passed | 2015-05-12 | aythom
82 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC082 | Passed | 2015-05-20 | stsure
83 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC083 | Passed | 2015-05-12 | szagar
84 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC084 | Passed | 2015-05-20 | akpand
85 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC085 | Passed | 2015-05-22 | stsure
86 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC008_TC086 | Failed | 2015-05-22 | stsure
87 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC087 | Passed | 2015-05-22 | stsure
88 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC088 | Passed | 2015-05-12 | aythom
89 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC089 | Passed | 2015-05-21 | szagar
90 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC090 | Passed | 2015-05-25 | stsure
91 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC091 | Passed | 2015-05-21 | szagar
92 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC092 | Passed | 2015-05-22 | szagar
93 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC093 | Passed | 2015-05-15 | sxtsat
94 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC094 | Passed | 2015-05-22 | szagar
95 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC095 | Passed | 2015-05-14 | aythom
96 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC096 | Passed | 2015-05-12 | rxloga
97 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC009_TC097 | Passed | 2015-05-22 | szagar
98 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC098 | Passed | 2015-05-25 | stsure
99 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC099 | Passed | 2015-05-22 | szagar
100 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC100 | Passed | 2015-05-19 | sxtsat
101 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC101 | Passed | 2015-05-25 | stsure
102 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC102 | Passed | 2015-05-14 | aythom
103 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC103 | Passed | 2015-05-22 | szagar
104 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC104 | Passed | 2015-05-19 | szagar
105 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC105 | Passed | 2015-05-14 | akpand
106 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC106 | Passed | 2015-05-22 | szagar
107 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC107 | Passed | 2015-05-19 | sxtsat
108 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC010_TC108 | Passed | 2015-05-14 | gxfati
109 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC011_TC109 | Passed | 2015-05-22 | aythom
110 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC011_TC110 | Passed | 2015-05-22 | stsure
111 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC011_TC111 | Passed | 2015-05-18 | szagar
112 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC011_TC112 | Passed | 2015-05-21 | akpand
113 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC011_TC113 | Passed | 2015-05-26 | stsure
114 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC012_TC114 | Passed | 2015-05-21 | akpand
115 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC012_TC115 | Failed | 2015-05-19 | stsure
116 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC012_TC116 | Passed | 2015-05-27 | aythom
117 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC012_TC117 | Passed | 2015-05-21 | akpand
118 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC012_TC118 | Passed | 2015-05-26 | stsure
119 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC013_TC119 | Passed | 2015-05-26 | akpand
120 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC013_TC120 | Passed | 2015-05-21 | akpand
121 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC013_TC121 | Passed | 2015-05-21 | akpand
122 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC013_TC122 | Failed | 2015-05-19 | stsure
123 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC014_TC123 | Passed | 2015-05-22 | stsure
124 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC014_TC124 | Passed | 2015-05-25 | stsure
125 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC014_TC125 | Failed | 2015-05-14 | stsure
126 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC014_TC126 | Failed | 2015-05-14 | stsure
127 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC015_TC127 | Passed | 2015-05-26 | stsure
128 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC015_TC128 | Failed | 2015-05-27 | stsure
129 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC015_TC129 | Passed | 2015-05-27 | stsure
130 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | TC130 | Failed | 2015-05-18 | stsure
131 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC131 | Passed | 2015-05-25 | aythom
132 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC132 | Failed | 2015-05-14 | stsure
133 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC133 | Failed | 2015-05-18 | stsure
134 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC134 | Failed | 2015-05-14 | stsure
135 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC135 | Failed | 2015-05-15 | stsure
136 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC136 | Passed | 2015-05-27 | stsure
137 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC016_TC137 | Passed | 2015-05-25 | aythom
138 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC017_TC138 | Passed | 2015-05-25 | aythom
139 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC017_TC139 | Failed | 2015-05-18 | stsure
140 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC018_TC140 | Passed | 2015-05-26 | aythom
141 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC018_TC141 | Passed | 2015-05-25 | stsure
142 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC019_TC142 | Passed | 2015-05-26 | aythom
143 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC019_TC143 | Passed | 2015-05-27 | aythom
144 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC020_TC144 | Passed | 2015-05-18 | aythom
145 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC021_TC145 | Passed | 2015-05-27 | aythom
146 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC022_TC146 | Passed | 2015-05-19 | szagar
147 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC023_TC147 | Passed | 2015-05-18 | akpand
148 | Release 1_ASPAC | End to End - Cycle 1 | E2E PO | ASPAC_E2E_PO_SC024_TC148 | Passed | 2015-05-27 | stsure
149 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC001_TC001 | Passed | 2015-05-13 | sxtsat
150 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC001_TC002 | Passed | 2015-05-13 | sxtsat
151 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC001_TC003 | Passed | 2015-05-13 | gxfati
152 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC001_TC004 | Passed | 2015-05-13 | aythom
153 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC001_TC005 | Passed | 2015-05-13 | axrath
154 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC002_TC006 | Failed | 2015-05-13 | szagar
155 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC002_TC007 | Passed | 2015-05-13 | akpand
156 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC002_TC008 | Passed | 2015-05-13 | sxtsat
157 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC002_TC009 | Passed | 2015-05-13 | sxtsat
158 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC002_TC010 | Passed | 2015-05-13 | gxfati
159 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC003_TC011 | Passed | 2015-05-13 | aythom
160 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC003_TC012 | Passed | 2015-05-13 | axrath
161 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC003_TC013 | Passed | 2015-05-13 | szagar
162 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC003_TC014 | Passed | 2015-05-13 | akpand
163 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC004_TC015 | Passed | 2015-05-13 | sxtsat
164 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC004_TC016 | Passed | 2015-05-13 | sxtsat
165 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC004_TC017 | Passed | 2015-05-13 | gxfati
166 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC004_TC018 | Passed | 2015-05-13 | aythom
167 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC005_TC019 | Passed | 2015-05-13 | axrath
168 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC005_TC020 | Passed | 2015-05-13 | szagar
169 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC005_TC021 | Passed | 2015-05-13 | akpand
170 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC005_TC022 | Passed | 2015-05-13 | sxtsat
171 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC006_TC023 | Failed | 2015-05-13 | sxtsat
172 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC006_TC024 | Failed | 2015-05-13 | gxfati
173 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC006_TC025 | Passed | 2015-05-13 | aythom
174 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC006_TC026 | Passed | 2015-05-13 | axrath
175 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC007_TC027 | Passed | 2015-05-13 | szagar
176 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC007_TC028 | Passed | 2015-05-13 | akpand
177 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC007_TC029 | Passed | 2015-05-13 | sxtsat
178 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC007_TC030 | Failed | 2015-05-13 | sxtsat
179 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC008_TC031 | Passed | 2015-05-13 | gxfati
180 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC008_TC032 | Passed | 2015-05-13 | aythom
181 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC008_TC033 | Passed | 2015-05-13 | axrath
182 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC008_TC034 | Passed | 2015-05-13 | szagar
183 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC009_TC035 | Passed | 2015-05-13 | akpand
184 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC009_TC036 | Passed | 2015-05-13 | sxtsat
185 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC009_TC037 | Passed | 2015-05-13 | sxtsat
186 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC009_TC038 | Passed | 2015-05-13 | gxfati
187 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC010_TC039 | Failed | 2015-05-22 | stsure
188 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC010_TC040 | Passed | 2015-05-13 | axrath
189 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC010_TC041 | Passed | 2015-05-26 | szagar
190 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC010_TC042 | Passed | 2015-05-13 | akpand
191 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC011_TC043 | Failed | 2015-05-25 | stsure
192 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC011_TC044 | Passed | 2015-05-14 | sxtsat
193 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC011_TC045 | Passed | 2015-05-14 | gxfati
194 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC011_TC046 | Passed | 2015-05-14 | aythom
195 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC012_TC047 | Failed | 2015-05-22 | stsure
196 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC013_TC048 | Passed | 2015-05-13 | szagar
197 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC013_TC049 | Passed | 2015-05-14 | akpand
198 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC013_TC050 | Passed | 2015-05-14 | stsure
199 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC013_TC051 | Passed | 2015-05-14 | sxtsat
200 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC013_TC052 | Passed | 2015-05-14 | gxfati
201 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC014_TC053 | Passed | 2015-05-13 | aythom
202 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC014_TC054 | Failed | 2015-05-25 | stsure
203 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC014_TC055 | Passed | 2015-05-14 | szagar
204 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC014_TC056 | Passed | 2015-05-14 | akpand
205 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC014_TC057 | Passed | 2015-05-15 | stsure
206 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC015_TC058 | Passed | 2015-05-14 | sxtsat
207 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC015_TC059 | Passed | 2015-05-14 | gxfati
208 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC015_TC060 | Passed | 2015-05-14 | aythom
209 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC015_TC061 | Passed | 2015-05-21 | szagar
210 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC016_TC062 | Passed | 2015-05-14 | szagar
211 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC016_TC063 | Passed | 2015-05-14 | akpand
212 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC016_TC064 | Passed | 2015-05-15 | stsure
213 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC016_TC065 | Passed | 2015-05-21 | szagar
214 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC017_TC066 | Passed | 2015-05-15 | gxfati
215 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC017_TC067 | Passed | 2015-05-14 | aythom
216 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC017_TC068 | Passed | 2015-05-21 | szagar
217 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC017_TC069 | Passed | 2015-05-14 | szagar
218 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC018_TC070 | Passed | 2015-05-15 | akpand
219 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC018_TC071 | Passed | 2015-05-15 | stsure
220 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC018_TC072 | Passed | 2015-05-15 | sxtsat
221 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC018_TC073 | Passed | 2015-05-15 | gxfati
222 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC019_TC074 | Passed | 2015-05-15 | aythom
223 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC019_TC075 | Passed | 2015-05-21 | szagar
224 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC019_TC076 | Passed | 2015-05-15 | szagar
225 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC019_TC077 | Passed | 2015-05-15 | akpand
226 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC020_TC078 | Passed | 2015-05-21 | szagar
227 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC020_TC079 | Passed | 2015-05-15 | sxtsat
228 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC020_TC080 | Passed | 2015-05-15 | gxfati
229 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC020_TC081 | Passed | 2015-05-15 | aythom
230 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC021_TC082 | Passed | 2015-05-22 | szagar
231 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC021_TC083 | Passed | 2015-05-15 | szagar
232 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC021_TC084 | Passed | 2015-05-15 | akpand
233 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC021_TC085 | Failed | 2015-05-25 | stsure
234 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC022_TC086 | Passed | 2015-05-22 | szagar
235 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC022_TC087 | Passed | 2015-05-15 | gxfati
236 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC022_TC088 | Passed | 2015-05-15 | aythom
237 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC022_TC089 | Passed | 2015-05-21 | akpand
238 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC023_TC090 | Passed | 2015-05-15 | szagar
239 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC023_TC091 | Passed | 2015-05-19 | akpand
240 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC023_TC092 | Passed | 2015-05-22 | stsure
241 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC023_TC093 | Passed | 2015-05-18 | sxtsat
242 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC024_TC094 | Passed | 2015-05-15 | gxfati
243 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC024_TC095 | Passed | 2015-05-19 | aythom
244 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC024_TC096 | Passed | 2015-05-21 | akpand
245 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC024_TC097 | Passed | 2015-05-15 | szagar
246 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC025_TC098 | Passed | 2015-05-15 | akpand
247 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC025_TC099 | Passed | 2015-05-15 | stsure
248 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC025_TC100 | Passed | 2015-05-18 | sxtsat
249 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC025_TC101 | Passed | 2015-05-19 | gxfati
250 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC026_TC102 | Passed | 2015-05-19 | aythom
251 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC026_TC103 | Passed | 2015-05-21 | akpand
252 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC026_TC104 | Passed | 2015-05-15 | szagar
253 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC026_TC105 | Passed | 2015-05-19 | akpand
254 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC027_TC106 | Passed | 2015-05-25 | stsure
255 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC027_TC107 | Passed | 2015-05-26 | sxtsat
256 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC027_TC108 | Passed | 2015-05-19 | gxfati
257 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC027_TC109 | Passed | 2015-05-25 | stsure
258 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC028_TC110 | Passed | 2015-05-26 | stsure
259 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC028_TC111 | Passed | 2015-05-19 | szagar
260 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC028_TC112 | Passed | 2015-05-19 | akpand
261 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC028_TC113 | Passed | 2015-05-26 | stsure
262 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC029_TC114 | Passed | 2015-05-26 | sxtsat
263 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC029_TC115 | Passed | 2015-05-19 | gxfati
264 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC029_TC116 | Passed | 2015-05-19 | aythom
265 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC029_TC117 | Passed | 2015-05-21 | aythom
266 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC030_TC118 | Passed | 2015-05-19 | szagar
267 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC030_TC119 | Passed | 2015-05-19 | akpand
268 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC030_TC120 | Passed | 2015-05-19 | stsure
269 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC030_TC121 | Passed | 2015-05-25 | sxtsat
270 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC031_TC122 | Passed | 2015-05-19 | gxfati
271 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC031_TC123 | Passed | 2015-05-19 | aythom
272 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC031_TC124 | Passed | 2015-05-21 | aythom
273 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC031_TC125 | Passed | 2015-05-19 | szagar
274 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC032_TC126 | Passed | 2015-05-25 | akpand
275 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC032_TC127 | Passed | 2015-05-19 | stsure
276 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC032_TC128 | Passed | 2015-05-19 | sxtsat
277 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC032_TC129 | Passed | 2015-05-19 | gxfati
278 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC033_TC130 | Passed | 2015-05-25 | aythom
279 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC033_TC131 | Passed | 2015-05-21 | aythom
280 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC033_TC132 | Passed | 2015-05-19 | szagar
281 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC033_TC133 | Passed | 2015-05-25 | akpand
282 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC034_TC134 | Passed | 2015-05-19 | stsure
283 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC034_TC135 | Passed | 2015-05-19 | sxtsat
284 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC034_TC136 | Passed | 2015-05-21 | aythom
285 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC034_TC137 | Passed | 2015-05-27 | aythom
286 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC035_TC138 | Passed | 2015-05-21 | aythom
287 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC035_TC139 | Passed | 2015-05-19 | szagar
288 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC035_TC140 | Passed | 2015-05-27 | akpand
289 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC035_TC141 | Passed | 2015-05-19 | stsure
290 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC036_TC142 | Passed | 2015-05-19 | sxtsat
291 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC036_TC143 | Failed | 2015-05-22 | stsure
292 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC036_TC144 | Passed | 2015-05-19 | aythom
293 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC036_TC145 | Failed | 2015-05-26 | stsure
294 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC037_TC146 | Passed | 2015-05-27 | stsure
295 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC037_TC147 | Passed | 2015-05-19 | akpand
296 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC037_TC148 | Passed | 2015-05-19 | stsure
297 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC037_TC149 | Passed | 2015-05-19 | sxtsat
298 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC038_TC150 | Passed | 2015-05-22 | stsure
299 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC038_TC151 | Passed | 2015-05-26 | stsure
300 | Release 1_ASPAC | End to End - Cycle 1 | E2E TE | ASPAC_E2E_TE_SC038_TC152 | Passed | 2015-05-27 | stsure
301 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC001 | No Run
302 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC002 | No Run
303 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC003 | No Run
304 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC004 | No Run
305 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC005 | No Run
306 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC006 | No Run
307 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC007 | No Run
308 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC008 | No Run
309 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC009 | No Run
310 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC010 | No Run
311 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC011 | No Run
312 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC012 | No Run
313 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC013 | No Run
314 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC014 | No Run
315 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC015 | No Run
316 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC016 | No Run
317 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC017 | No Run
318 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC018 | No Run
319 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC019 | No Run
320 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC020 | No Run
321 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC021 | No Run
322 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC022 | No Run
323 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC023 | No Run
324 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC024 | No Run
325 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC025 | No Run
326 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC026 | No Run
327 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC027 | No Run
328 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC028 | No Run
329 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC029 | No Run
330 | Release 1_ASPAC | End to End - Cycle 1 | PeopleSoft Integration | PeopleSoft Integration_TC030 | No Run
331 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | XS_GenerateDocument_004_TC019 | Passed | 2015-05-11 16:14
332 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_EmailBroker_011_TC_061 | N/A | 2015-05-15 08:12
333 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_SendEmail_001_TC002 | Passed | 2015-05-11 16:14
334 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_SendEmail_001_TC003 | Passed | 2015-05-15 08:09
335 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_EmailBroker_016_TC_079 | Failed | 2015-03-19 14:38
336 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | XS_GenerateDocument_012_TC020 | Passed | 2015-05-15 10:13
337 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_SendEmail_004_TC010 | Passed | 2015-05-15 08:11
338 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_SendEmail_004_TC012 | Passed | 2015-05-15 08:11
339 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | XS_GenerateDocument_028_TC033 | Passed | 2015-05-15 10:14
340 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1A | IS_SendEmail_005_TC014 | Passed | 2015-05-15 08:11
341 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | IS_ApolloPrint_004_TC004 | No Run
342 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | Alerts_and_Notifications_003_TC003 | No Run
343 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_003_TC084 | Passed | 2015-05-11 16:15
344 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Dairy_015_TC031 | Passed | 2015-05-11 16:17
345 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Notes_019_TC038 | No Run
346 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | IS_SendFax_007_TC014 | Passed | 2015-05-11 16:18
347 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Workbasket_005_TC010 | No Run
348 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Workbasket_009_TC024 | No Run
349 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Notes_019_TC039 | No Run
350 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | IS_Drag&Drop_033_TC054 | Passed | 2015-05-27 12:26
351 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Dairy_001_TC002 | Passed | 2015-05-11 16:18
352 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Dairy_002_TC004 | Passed | 2015-05-11 16:18
353 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | IS_Drag&Drop_033_TC055 | Passed | 2015-05-27 12:28
354 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Workbasket_017_TC040 | Passed | 2015-05-11 16:19
355 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Workbasket_009_TC029 | Passed | 2015-05-11 16:19
356 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | CE_Dairy_004_TC007 | Failed | 2015-04-07 14:05
357 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_017_TC098 | Passed | 2015-05-11 16:15
358 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_029_TC109 | No Run
359 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_030_TC110 | No Run
360 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_031_TC111 | Passed | 2015-05-11 16:16
361 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_032_TC112 | No Run
362 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_033_TC113 | No Run
363 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ApproveOrder_034_TC114 | No Run
364 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ReleasePaymentinCitiDirect_002_TC141 | No Run
365 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | ManualPostinPeopleSoft_004_TC234 | No Run
366 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_QuoteReceived_001_TC272 | Passed | 2015-05-11 16:16
367 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_PlaceOrder_001_TC275 | No Run
368 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_QuoteReceived_003_TC055 | No Run
369 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_QuoteReceived_005_TC056 | No Run
370 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_GoodsArrived_005_TC068 | Passed | 2015-05-11 16:17
371 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_ReleasePaymentinCitiDirect_010_TC152 | Passed | 2015-05-11 11:52
372 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1B | AS_SendforCitiDirectApproval_010_TC138 | Passed | 2015-05-11 16:17
373 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | XS_GenerateDocument_003_TC006 | Passed | 2015-05-27 12:30
374 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_030_TC047 | Passed | 2015-05-11 16:26
375 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | FS_ViewerConfig_42_TC020 | Passed | 2015-05-11 16:29
376 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_EmailBroker_002_TC_006 | Failed | 2015-03-26 12:01
377 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_Notes_020_TC041 | Failed | 2015-04-29 13:59
378 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_Workbasket_011_TC031 | Passed | 2015-05-15 10:15
379 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_DataCapScanning_010_TC033 | Failed | 2015-04-23 15:46
380 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_DataCapScanning_020_TC045 | Failed | 2015-04-23 15:43
381 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_Workbasket_017_TC039 | Passed | 2015-05-11 16:29
382 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_003 | Passed | 2015-05-11 16:24
383 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_EmailBroker_006_TC_021 | Failed | 2015-04-10 12:14
384 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_030_TC048 | Passed | 2015-05-11 16:27
385 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | XS_GenerateDocument_022_TC023 | Passed | 2015-05-11 16:25
386 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_CreatePOInvoiceFile_009_TC005 | Passed | 2015-05-11 16:22
387 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_Approve Invoice_026_TC047 | Failed | 2015-04-29 13:51
388 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | XS_GenerateDocument_024_TC026 | Passed | 2015-05-11 16:25
389 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_030_TC049 | Passed | 2015-05-11 16:27
390 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_006_TC006 | Passed | 2015-05-11 16:28
391 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_DataCapScanning_020_TC046 | Failed | 2015-04-23 15:44
392 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_031_TC050 | Passed | 2015-05-22 10:30
393 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | XS_GenerateDocument_014_TC030 | Passed | 2015-05-11 16:26
394 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_Approve Invoice_027_TC048 | Failed | 2015-04-29 13:51
395 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_Approve Invoice_029_TC050 | Failed | 2015-04-29 13:51
396 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_031_TC052 | Passed | 2015-05-22 10:29
397 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_007_TC008 | Passed | 2015-05-11 16:28
398 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_CreateFile_005_TC007 | Passed | 2015-05-11 16:24
399 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_008 | Passed | 2015-05-27 12:31
400 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC006 | Passed | 2015-05-11 16:30
401 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_008_TC009 | Passed | 2015-05-11 16:28
402 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_036_TC060 | Passed | 2015-05-11 16:27
403 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_Approve Invoice_030_TC051 | Failed | 2015-04-29 13:51
404 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_Approve Invoice_031_TC052 | Failed | 2015-04-29 13:51
405 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | IS_Drag&Drop_049_TC078 | Passed | 2015-05-11 16:27
406 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC007 | Passed | 2015-05-11 16:30
407 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_CreateFile_016_TC023 | Failed | 2015-04-09 11:04
408 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | Security_ManageUserAdmin_081_TC081 | Passed | 2015-05-27 12:32
409 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_CreateFile_019_TC028 | Passed | 2015-05-15 10:16
410 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_012 | Failed | 2015-03-26 10:03
411 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC008 | Passed | 2015-05-11 16:30
412 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_CreateCitiDirectFile_013_TC126 | Passed | 2015-05-11 16:23
413 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_SendforCitiDirectApproval_011_TC139 | Passed | 2015-05-11 16:23
414 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC009 | Passed | 2015-05-11 16:30
415 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_013 | Failed | 2015-03-26 09:42
416 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC010 | Passed | 2015-05-11 16:30
417 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_ReleasePaymentinCitiDirect_006_TC148 | Failed | 2015-04-29 13:51
418 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CreateTE_ExpenseFile_014_TC252 | Passed | 2015-05-11 16:23
419 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_021_TC025 | Passed | 2015-05-11 16:28
420 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC011 | Passed | 2015-05-11 16:31
421 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_009_TC043 | Failed | 2015-04-10 11:27
422 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_019 | Failed | 2015-04-30 10:25
423 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC012 | Passed | 2015-05-11 16:31
424 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_031_TC043 | Passed | 2015-05-27 12:38
425 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | AS_SendforCitiDirectApproval_006_TC135 | Passed | 2015-05-11 16:23
426 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | Security_ManageASPACFinSysAdmin_021_TC045 | Failed | 2015-04-16 14:03
427 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_005_TC013 | Passed | 2015-05-27 13:32
428 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_032_TC044 | Passed | 2015-05-27 12:38
429 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_002_TC013 | Passed | 2015-05-11 16:31
430 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | ASPAC_Correspondents_020 | Failed | 2015-04-30 11:45
431 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_014_TC054 | Failed | 2015-04-10 12:31
432 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_003_TC014 | Passed | 2015-05-11 16:31
433 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_033_TC045 | Passed | 2015-05-27 12:39
434 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_005_TC014 | Passed | 2015-05-27 13:33
435 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_005_TC015 | Passed | 2015-05-27 13:34
436 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_033_TC046 | Passed | 2015-05-27 12:40
437 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_003_TC015 | Passed | 2015-05-11 16:31
438 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_003_TC016 | Passed | 2015-05-11 16:32
439 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_022_TC069 | Failed | 2015-04-15 14:27
440 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_033_TC047 | Passed | 2015-05-27 12:40
441 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_033_TC048 | Passed | 2015-05-27 12:40
442 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_023_TC070 | Failed | 2015-04-15 14:29
443 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_003_TC017 | Passed | 2015-05-11 16:32
444 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_004_TC018 | Passed | 2015-05-11 16:32
445 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_024_TC071 | Failed | 2015-04-15 14:30
446 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_033_TC049 | Passed | 2015-05-27 12:41
447 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_034_TC050 | Passed | 2015-05-27 12:41
448 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenFile_024_TC072 | Failed | 2015-04-28 05:53
449 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_005_TC019 | Failed | 2015-04-09 15:04
450 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_005_TC020 | Failed | 2015-04-09 15:05
451 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_035_TC051 | Passed | 2015-05-27 13:09
452 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_005_TC021 | Failed | 2015-04-09 15:06
453 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ ManageFileAssociation_001_TC079 | Failed | 2015-04-10 14:07
454 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_007_TC021 | Passed | 2015-05-27 13:35
455 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_007_TC022 | Passed | 2015-05-27 13:36
456 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ ManageFileAssociation_003_TC081 | Failed | 2015-04-10 14:22
457 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Penditems_005_TC022 | Failed | 2015-04-09 15:06
458 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_Performindexing_012_TC043 | Passed | 2015-05-15 10:16
459 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_041_TC057 | Passed | 2015-05-27 13:10
460 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_041_TC058 | Passed | 2015-05-27 13:10
461 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_008_TC025 | Passed | 2015-05-27 13:36
462 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_008_TC026 | Failed | 2015-04-30 13:16
463 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_042_TC059 | Passed | 2015-05-27 13:11
464 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_043_TC060 | Passed | 2015-05-27 13:11
465 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_008_TC027 | Passed | 2015-05-27 13:37
466 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_008_TC028 | Passed | 2015-05-27 13:38
467 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_045_TC062 | Passed | 2015-05-27 13:12
468 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_046_TC063 | Passed | 2015-05-27 13:19
469 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_009_TC029 | Passed | 2015-05-27 13:38
470 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_009_TC030 | Passed | 2015-05-27 13:39
471 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_049_TC066 | Passed | 2015-05-27 13:20
472 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_050_TC067 | Passed | 2015-05-27 13:21
473 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_051_TC068 | Passed | 2015-05-27 13:22
474 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_005_TC097 | Failed | 2015-04-15 16:08
475 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_010_TC032 | Not Completed | 2015-05-12 16:00
476 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_005_TC098 | Failed | 2015-04-15 16:10
477 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_052_TC069 | Failed | 2015-04-17 13:53
478 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_007_TC100 | Failed | 2015-04-15 16:14
479 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_008_TC101 | Failed | 2015-04-29 13:10
480 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | SS_ManageUserpreference_063_TC078 | Failed | 2015-04-27 08:05
481 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_009_TC102 | Failed | 2015-04-15 16:16
482 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocumentTree_011_TC106 | Failed | 2015-04-20 16:38
483 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_005_TC128 | Passed | 2015-05-28 06:06
484 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_011_TC038 | Passed | 2015-05-27 13:39
485 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_012_TC039 | Passed | 2015-05-27 13:40
486 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_005_TC129 | Passed | 2015-05-28 06:11
487 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_018_TC148 | Passed | 2015-05-11 16:25
488 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_014_TC041 | Passed | 2015-05-27 13:40
489 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_015_TC042 | Failed | 2015-04-29 14:52
490 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_018_TC149 | Passed | 2015-05-11 16:25
491 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_023_TC157 | Failed | 2015-04-16 09:03
492 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_017_TC044 | Passed | 2015-05-27 13:40
493 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_017_TC045 | Passed | 2015-05-27 13:41
494 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_001_TC184 | Passed | 2015-05-27 12:33
495 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_001_TC185 | Passed | 2015-05-27 12:34
496 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_018_TC046 | Passed | 2015-05-27 13:41
497 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_019_TC047 | Passed | 2015-05-27 13:41
498 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC188 | Passed | 2015-05-22 09:52
499 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC189 | Passed | 2015-05-22 09:53
500 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_020_TC048 | Passed | 2015-05-27 13:42
501 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC190 | Passed | 2015-05-22 09:54
502 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC191 | Passed | 2015-05-27 12:35
503 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_020_TC050 | Passed | 2015-05-27 13:42
504 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_020_TC051 | Passed | 2015-05-27 13:43
505 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC192 | Passed | 2015-05-27 12:36
506 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_OpenDocument_003_TC193 | Passed | 2015-05-27 12:36
507 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_021_TC052 | Passed | 2015-05-27 13:43
508 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_022_TC053 | Passed | 2015-05-27 13:44
509 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CE_ManageDocument_004_TC127 | Passed | 2015-05-28 06:04
510 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_025_TC061 | Passed | 2015-05-27 13:44
511 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_027_TC063 | Failed | 2015-05-27 12:56
512 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_028_TC064 | Passed | 2015-05-27 13:44
513 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_029_TC065 | Failed | 2015-04-30 13:34
514 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_036_TC074 | Failed | 2015-04-30 08:23
515 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_036_TC075 | Failed | 2015-04-30 08:24
516 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_036_TC076 | Passed | 2015-05-27 13:45
517 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_036_TC077 | Failed | 2015-04-30 12:57
518 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_037_TC078 | Failed | 2015-04-30 12:58
519 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_037_TC079 | Failed | 2015-04-30 12:59
520 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_038_TC080 | Failed | 2015-04-30 13:50
521 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_039_TC081 | Failed | 2015-04-30 13:51
522 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_041_TC084 | Passed | 2015-05-27 13:45
523 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_044_TC089 | Passed | 2015-05-27 13:46
524 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_044_TC090 | Passed | 2015-05-27 13:46
525 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_045_TC091 | Failed | 2015-04-29 14:46
526 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC092 | Passed | 2015-05-27 13:46
527 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC093 | Passed | 2015-05-27 13:47
528 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC094 | Passed | 2015-05-27 13:47
529 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC095 | Failed | 2015-04-29 13:59
530 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC098 | Failed | 2015-04-30 14:11
531 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_046_TC099 | Failed | 2015-04-30 14:12
532 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_047_TC100 | Failed | 2015-04-30 14:13
533 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_048_TC0101 | Passed | 2015-05-27 13:48
534 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_049_TC0102 | Passed | 2015-05-27 13:48
535 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_050_TC0103 | Failed | 2015-04-29 13:17
536 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_051_TC0104 | Passed | 2015-05-27 13:48
537 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_054_TC0107 | Passed | 2015-05-27 13:49
538 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_055_TC0108 | Passed | 2015-05-27 13:49
539 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_056_TC0109 | Failed | 2015-04-30 10:51
540 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_057_TC0110 | Failed | 2015-04-30 10:52
541 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_059_TC0112 | Passed | 2015-05-27 13:50
542 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_059_TC0113 | Passed | 2015-05-27 13:50
543 | Release 1_ASPAC | Build 1A+1B+1C | Failed testcases 1C | CS_SearchTemplate_062_TC0116 | Failed | 2015-04-30 07:51
544 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 38 | closed | 2015-05-13 | bysiva
545 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 204 | Re-Opened | 2015-05-13 | bysiva
546 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 257 | closed | 2015-05-13 | bysiva
547 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 515 | closed | 2015-05-13 | bysiva
548 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 566 | closed | 2015-05-13 | bysiva
549 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 628 | closed | 2015-05-13 | bysiva
550 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 634 | closed | 2015-05-13 | bysiva
551 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 643 | closed | 2015-05-13 | bysiva
552 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 682 | closed | 2015-05-13 | bysiva
553 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 685 | closed | 2015-05-13 | bysiva
554 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 726 | closed | 2015-05-13 | bysiva
555 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 747 | closed | 2015-05-13 | bysiva
556 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 391 | closed | 2015-05-13 | bysiva
557 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 743 | Re-opened | 2015-05-19 | bysiva
558 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 579 | Re-opened | 2015-05-19 | bysiva
559 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 721 | Re-opened | 2015-05-19 | bysiva
560 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 780 | Re-opened | 2015-05-19 | bysiva
561 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 525 | Re-opened | 2015-05-19 | bysiva
562 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 527 | Re-opened | 2015-05-19 | bysiva
563 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 533 | Re-opened | 2015-05-19 | bysiva
564 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 692 | Pending | 2015-05-19 | bysiva
565 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 575 | Closed | 2015-05-19 | bysiva
566 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 582 | Closed | 2015-05-19 | bysiva
567 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 597 | Closed | 2015-05-19 | bysiva
568 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 615 | Closed | 2015-05-19 | bysiva
569 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 620 | Closed | 2015-05-19 | bysiva
570 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 652 | Closed | 2015-05-19 | bysiva
571 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 663 | Closed | 2015-05-19 | bysiva
572 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 693 | Closed | 2015-05-19 | bysiva
573 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 723 | Closed | 2015-05-19 | bysiva
574 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 777 | Closed | 2015-05-19 | bysiva
575 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 785 | Closed | 2015-05-19 | bysiva
576 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 803 | Closed | 2015-05-19 | bysiva
577 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 197 | Closed | 2015-05-19 | bysiva
578 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 290 | Closed | 2015-05-19 | bysiva
579 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 370 | Closed | 2015-05-19 | bysiva
580 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 425 | Closed | 2015-05-19 | bysiva
581 | Release 1_ASPAC | Build 1A+1B+1C | Defect Retesting | 496 | Closed | 2015-05-19 | bysiva

## Defect Report
DEFECT SUMMARY - CYCLE WISE
Release 1 - Defect Summary - Status |  | Final Defect Status
Release Name | Cycle Name | New | Open | Active | In Progress | Fixed | Ready for System Test | Retest Dependency | Failed Retest | Ready for Business Test | Deferred | Rejected | Re-Opened | Put On Hold | Closed | Total | % of Total
Release 1_ASPAC | Build 1A - Cycle 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 111 | 114 | 12.46%
| Build 1A - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0.4372%
| Build 1B - Cycle 1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 127 | 137 | 14.97%
| Build 1B - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 2.186%
| Build 1C - Cycle 1 | 9 | 17 | 0 | 1 | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 10 | 3 | 213 | 260 | 28.42%
| Build 1C - Cycle 2 | 19 | 18 | 0 | 4 | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 83 | 130 | 14.21%
| End to End - Cycle 1 | 77 | 61 | 0 | 5 | 11 | 2 | 0 | 0 | 0 | 1 | 0 | 3 | 2 | 88 | 250 | 27.32%
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Release 1 - Total |  | 105 | 101 | 0 | 10 | 18 | 3 | 1 | 0 | 0 | 7 | 0 | 19 | 5 | 646 | 915 | 100%
Release 1 - % of Total |  | 11.48% | 11.04% | 0% | 1.093% | 1.967% | 0.3279% | 0.1093% | 0% | 0% | 0.765% | 0% | 2.077% | 0.5464% | 70.6% | 100%
Release 1 - Defect Summary - Severity & Priority |  | Defect Severity |  |  |  | Defect Priority
Release Name | Cycle Name | 1 - Critical | 2 - High | 3 - Medium | 4 - Low | 1 - Urgent | 2 - High | 3 - Medium | 4 - Low
Release 1_ASPAC | Build 1A - Cycle 1 | 8 | 47 | 49 | 10 | 0 | 57 | 36 | 11
| Build 1A - Cycle 2 | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 1
| Build 1B - Cycle 1 | 8 | 82 | 33 | 14 | 0 | 87 | 24 | 16
| Build 1B - Cycle 2 | 0 | 14 | 5 | 1 | 0 | 14 | 5 | 1
| Build 1C - Cycle 1 | 9 | 117 | 107 | 27 | 0 | 136 | 87 | 27
| Build 1C - Cycle 2 | 3 | 38 | 63 | 26 | 0 | 53 | 49 | 26
| End to End - Cycle 1 | 8 | 40 | 153 | 49 | 0 | 44 | 144 | 48
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release 1 - Total |  | 37 | 338 | 412 | 128 | 0 | 391 | 347 | 130
Release 1 - % of Total |  | 4.044% | 36.94% | 45.03% | 13.99% | 0% | 42.73% | 37.92% | 14.21%
Release 1 - Defect Summary - Primary Reason |  | Defect - Primary Reason
Release Name | Cycle Name | Code | Requirement | Design | Environment | Known Issue | Testing | Total
Release 1_ASPAC | Build 1A - Cycle 1 | 56 | 10 | 1 | 22 | 7 | 2 | 98
| Build 1A - Cycle 2 | 2 | 0 | 0 | 1 | 0 | 1 | 4
| Build 1B - Cycle 1 | 99 | 7 | 1 | 4 | 3 | 5 | 119
| Build 1B - Cycle 2 | 11 | 0 | 1 | 0 | 3 | 0 | 15
| Build 1C - Cycle 1 | 155 | 5 | 4 | 5 | 12 | 14 | 195
| Build 1C - Cycle 2 | 65 | 2 | 0 | 1 | 3 | 5 | 76
| End to End - Cycle 1 | 57 | 4 | 0 | 3 | 5 | 10 | 79
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release 1 - Total |  | 445 | 28 | 7 | 36 | 33 | 37 | 586
Release 1 - Defect Summary - Secondary Reason |  | Primary Reason : Code | [5 empty] | Primary Reason : Requirement |  |  |  |  | Primary Reason : Design | [5 empty] | Primary Reason : Environment | [5 empty] | Primary Reason : Known Issue |  |  | Primary Reason : Testing
Release Name | Cycle Name | Interface Code | Code Error | Validation / Rules | Configurations | Code Merge | Total | Missed Business Requirement | Business Requirements Incorrect | Missed BA Requirement | New Functionality | Total | Infrastructure Design | Incomplete Design | Code Design | Performance Design | Data Model | Total | Build Issue | Environmental | Job Schedule | System / Service Failure | Interface System - Environment | Total | Accepted as it is | Future Fixes | Total | Invalid Test Case | QA Knowledge Gap | Incorrect Test Data | Tester Error | Duplicate | Inconsistent | Total
Release 1_ASPAC | Build 1A - Cycle 1 | 0 | 55 | 0 | 0 | 1 | 56 | 0 | 1 | 0 | 9 | 10 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 17 | 0 | 0 | 0 | 20 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Build 1A - Cycle 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Build 1B - Cycle 1 | 0 | 98 | 0 | 0 | 1 | 99 | 0 | 2 | 1 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2 | 1 | 3 | 0 | 2 | 0 | 0 | 2 | 1 | 5
| Build 1B - Cycle 2 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Build 1C - Cycle 1 | 0 | 155 | 0 | 0 | 0 | 155 | 0 | 1 | 0 | 3 | 4 | 2 | 0 | 2 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 3 | 11 | 1 | 12 | 4 | 0 | 1 | 0 | 3 | 3 | 11
| Build 1C - Cycle 2 | 0 | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 3 | 0 | 4
| End to End - Cycle 1 | 0 | 57 | 0 | 0 | 0 | 57 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 3 | 2 | 5 | 1 | 0 | 2 | 0 | 0 | 0 | 3
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release 1 - Total |  | 0 | 443 | 0 | 0 | 2 | 445 | 0 | 7 | 1 | 18 | 26 | 2 | 0 | 4 | 0 | 0 | 6 | 4 | 27 | 0 | 0 | 0 | 31 | 27 | 6 | 33 | 6 | 2 | 3 | 0 | 8 | 5 | 24
Release 1 - Defect Summary - Impacted System |  | Impacted Systems
Release Name | Cycle Name | ACEView | Classic Apollo | Deaja Viewer | FileNet | Datacap Scanning | Peoplesoft | Mercury | Total | % of Total
Release 1_ASPAC | Build 1A - Cycle 1 | 84 | 0 | 0 | 3 | 0 | 0 | 0 | 87 | 9.92%
| Build 1A - Cycle 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.2281%
| Build 1B - Cycle 1 | 133 | 0 | 0 | 1 | 0 | 0 | 0 | 134 | 15.28%
| Build 1B - Cycle 2 | 19 | 0 | 0 | 0 | 0 | 1 | 0 | 20 | 2.281%
| Build 1C - Cycle 1 | 251 | 0 | 0 | 0 | 0 | 5 | 0 | 256 | 29.19%
| Build 1C - Cycle 2 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 14.71%
| End to End - Cycle 1 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 28.39%
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Release 1 - Total |  | 867 | 0 | 0 | 4 | 0 | 6 | 0 | 877 | 100%
Release 1 - % of Total |  | 94.75% | 0% | 0% | 0.4372% | 0% | 0.6557% | 0% | 95.85%
Release 1 - Defect Summary - Defect Aging |  | Defect Aging - Closed Defects | [5 empty] | Defect Aging - Non Closed Defects
Release Name | Cycle Name | <= 3 | > 3 & <= 8 | > 8 & <= 15 | > 15 & <= 30 | > 30 & <= 50 | > 50 | <= 3 | > 3 & <= 8 | > 8 & <= 15 | > 15 & <= 30 | > 30 & <= 50 | > 50
Release 1_ASPAC | Build 1A - Cycle 1 | 21 | 30 | 17 | 9 | 11 | 20 | 0 | 0 | 0 | 0 | 0 | 3
| Build 1A - Cycle 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Build 1B - Cycle 1 | 23 | 34 | 11 | 12 | 24 | 17 | 0 | 0 | 0 | 0 | 0 | 10
| Build 1B - Cycle 2 | 5 | 10 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Build 1C - Cycle 1 | 21 | 45 | 39 | 55 | 49 | 2 | 0 | 0 | 0 | 1 | 31 | 15
| Build 1C - Cycle 2 | 9 | 19 | 27 | 24 | 2 | 0 | 0 | 0 | 0 | 18 | 29 | 0
| End to End - Cycle 1 | 27 | 27 | 21 | 3 | 0 | 0 | 34 | 25 | 83 | 20 | 0 | 0
| End to End - Cycle 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Freeze Cycle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Automation Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Performance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release 1 - Total |  | 107 | 165 | 116 | 106 | 87 | 40 | 34 | 25 | 83 | 39 | 60 | 28
DEFECT SUMMARY - STATUS WISE
Release 1 - Status Summary - Severity & Priority |  | Defect Severity |  |  |  | Defect Priority
Release Name | Cycle Name | 1 - Critical | 2 - High | 3 - Medium | 4 - Low | 1 - Urgent | 2 - High | 3 - Medium | 4 - Low
Release 1_ASPAC | New | 0 | 0 | 57 | 48 | 0 | 0 | 57 | 48
| Open | 0 | 6 | 71 | 24 | 0 | 5 | 68 | 26
| Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In Progress | 0 | 3 | 7 | 0 | 0 | 6 | 4 | 0
| Fixed | 0 | 3 | 12 | 3 | 0 | 7 | 9 | 2
| Ready for System Test | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
| Retest Dependency | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
| Failed Retest | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ready for Business Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deferred | 0 | 2 | 5 | 0 | 0 | 5 | 2 | 0
| Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-Opened | 0 | 3 | 12 | 4 | 0 | 5 | 9 | 5
| Put On Hold | 0 | 1 | 4 | 0 | 0 | 1 | 4 | 0
| Closed | 37 | 320 | 240 | 49 | 0 | 362 | 190 | 49
Release 1 - Total |  | 37 | 338 | 412 | 128 | 0 | 391 | 347 | 130
Release 1 - % of Total |  | 4.044% | 36.94% | 45.03% | 13.99% | 0% | 42.73% | 37.92% | 14.21%
Release 1 - Status Summary - Primary Reason |  | Defect - Primary Reason
Release Name | Cycle Name | Code | Requirement | Design | Environment | Known Issue | Testing
Release 1_ASPAC | New | 0 | 0 | 0 | 0 | 0 | 0
| Open | 0 | 0 | 0 | 0 | 0 | 0
| Active | 0 | 0 | 0 | 0 | 0 | 0
| In Progress | 0 | 0 | 0 | 0 | 0 | 0
| Fixed | 0 | 0 | 0 | 0 | 0 | 0
| Ready for System Test | 0 | 0 | 0 | 0 | 0 | 0
| Retest Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Failed Retest | 0 | 0 | 0 | 0 | 0 | 0
| Ready for Business Test | 0 | 0 | 0 | 0 | 0 | 0
| Deferred | 0 | 0 | 0 | 0 | 1 | 0
| Rejected | 0 | 0 | 0 | 0 | 0 | 0
| Re-Opened | 0 | 0 | 0 | 0 | 0 | 0
| Put On Hold | 0 | 0 | 0 | 0 | 0 | 0
| Closed | 445 | 28 | 7 | 36 | 32 | 37
Release 1 - Total |  | 445 | 28 | 7 | 36 | 33 | 37
Release 1 - % of Total |  | 48.63% | 3.06% | 0.765% | 3.934% | 3.607% | 4.044%

## Defect Entry
Defect ID | Final Defect Status | Summary | Component Name | Primary Reason | Secondary Reason | Severity | Priority | Detected By | Assigned To | Detected On Date | Impacted System | Detected in Cycle | Detected in Release | Closing Date | Defect Age (In Days) | Environment
1 | Closed | General Exception error while opening the Filenet Workspace XT with Java1.7 | Environment | Environment | Environmental | 3 - Medium | 3 - Medium | axravi | bysiva | 2015-01-22 | Filenet | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 12 | ASPAC - SIT 2
2 | Closed | Datacap Scan -User interface throws java error | Environment | Environment | Environmental | 3 - Medium | 3 - Medium | axravi | axplac | 2015-01-22 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-28 | 6 | ASPAC - SIT 2
3 | Closed | Daeja viewer version is 4.1 instead of 4.0.68 in SIT2 | Environment | Environment | Environmental | 3 - Medium | 4 - Low | axravi | axravi | 2015-01-22 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-02 | 11 | ASPAC - SIT 2
4 | Closed | Daeja Viewer - Does not include the custom components Auto Launch, Export | Viewer Configuration | Environment | Build issue | 2 - High | 3 - Medium | axravi | bysiva | 2015-01-22 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 15 | ASPAC - SIT 2
5 | Closed | ACEView_Barcode Generation: Code and Description data values is not populated and displayed in the screen | Barcode Generation | Config-Data | App DB | 2 - High | 2 - High | axplac | axplac | 2015-01-26 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-28 | 2 | ASPAC - SIT 2
6 | Closed | Document Generation -System does not allow to generate the PO document by clicking on the Publish Button | Document Generation | Code | Code Error | 1 - Critical | 1 - Critical | axravi | bysiva | 2015-01-26 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 8 | ASPAC - SIT 2
7 | Closed | Barcode Generation_The document is displayed in AceView in Daeja Viewer and not in ‘.pdf’ format. | Barcode Generation | Code | Code Error | 4 - Low | 2 - High | axplac | axplac | 2015-01-26 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-28 | 2 | ASPAC - SIT 2
8 | Closed | Document Generation :System does not display the expected value for the PO template for selecting the AceAddress | Document Generation | Code | Code Error | 2 - High | 2 - High | axravi | axplac | 2015-01-26 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-17 | 22 | ASPAC - SIT 2
9 | Closed | Barcode Generation_The Value is not displayed as expected for the Search criteria selected under generate Barcode | Barcode Generation | Config-Data | App DB | 1 - Critical | 1 - Critical | axplac | axplac | 2015-01-26 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-29 | 3 | ASPAC - SIT 2
10 | Closed | AceView - Application not working on IE 8 -32 bit and displays an error page cannot be displayed error | Environment | Environment | Environmental | 2 - High | 2 - High | axravi | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-30 | 3 | ASPAC - SIT 2
11 | Closed | Barcode Generation - System displays the same Barcode for any type of the barcode selected for Business unit,Country and Department | Barcode Generation | Environment | Environmental | 2 - High | 2 - High | axravi | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-29 | 2 | ASPAC - SIT 2
12 | Closed | ACEView Login Error. Need to click nearly 15 times to get the AceView Application displayed | ACEView | Environment | Environmental | 3 - Medium | 2 - High | stsure | bysiva | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 7 | ASPAC - SIT 2
13 | Closed | Send Email_Unable to attach multiple documents | Send Email | Code | Code Error | 3 - Medium | 2 - High | swsure | bysiva | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 15 | ASPAC - SIT 2
14 | Closed | Email : .MSG format mail with attachments is not getting Processed in ICC | Email | PMR |  | 2 - High | 2 - High | stsure | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 41 | ASPAC - SIT 2
15 | Closed | Send Email_ system displays "&nbsp" when there is a space in the subject line. | Send Email | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 14 | ASPAC - SIT 2
16 | Closed | Daeja Viewer_Annotations_LAN ID is not displayed when mouse pointer is placed over the annotation. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | bysiva | 2015-01-27 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 14 | ASPAC - SIT 2
17 | Closed | AceView_Daeja Viewer_ Workplace XT_ System displays the login screen when trying to view a document from the document grid in Ace view | Viewer Configuration | Environment | Build issue | 4 - Low | 2 - High | swsure | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 8 | ASPAC - SIT 2
18 | Closed | Document Generation_GST % takes values greater than 100 and also takes negative values | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-17 | 21 | ASPAC - SIT 2
19 | Closed | Daeja Viewer_Split_Functionality_The annotations present in the original document is not present in the new split document. | Viewer Configuration | Requirement | New functionality | 2 - High | 2 - High | ksseng | axplac | 2015-01-27 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-28 | 1 | ASPAC - SIT 2
20 | Closed | Document Generation_ Unit Price field is taking negative values | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 41 | ASPAC - SIT 2
21 | Closed | Document Generation_"Save button" is missing in the document tab | Document Generation | Requirement | New functionality | 2 - High | 2 - High | axrath | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-30 | 3 | ASPAC - SIT 2
22 | Closed | AceView: The column "Date Modified" does not display as Expected value | ACEView | Code | Code Error | 3 - Medium | 4 - Low | axplac | bysiva | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 10 | ASPAC - SIT 2
23 | Closed | AceView_Viewer: PopUp message displayed when trying to View the document in DaejaViewer | ACEView | Environment | Environmental | 3 - Medium | 2 - High | axplac | axplac | 2015-01-27 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 41 | ASPAC - SIT 2
24 | Closed | Document Generation_On clicking ‘Clear button’ system does not clear all contents of the PO Document tab | Document Generation | Code | Code Error | 3 - Medium | 3 - Medium | axrath | bysiva | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 98 | ASPAC - SIT 2
25 | Closed | Email: Mails are available in (Inbox , Error and Processed ) all the folders. | Email | Environment | Environmental | 2 - High | 2 - High | stsure | gvwill | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 97 | ASPAC - SIT 2
26 | Closed | Document Generation_While deleting the selected row/rows using Delete button, system does not prompt the user to confirm deletion | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 42 | ASPAC - SIT 2
27 | Closed | Daeja_Viewer_Annotation: Changes made to the annotations are not saved. | Viewer Configuration | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-01-28 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 6 | ASPAC - SIT 2
28 | Closed | Barcode Generation - Values are not getting populated in the code and description dropdowns when user selects STI as barcode type | Barcode Generation | Code | Code Error | 2 - High | 2 - High | bysiva | bysiva | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 42 | ASPAC - SIT 2
29 | Closed | Barcode Generation: Description values are getting displayed in Code dropdown | Barcode Generation | Code | Code Error | 2 - High | 3 - Medium | axplac | axplac | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 13 | ASPAC - SIT 2
30 | Closed | Barcode Generation: Generated Barcodes are not getting launched in the PDF reader instead it is getting launched in Dajea Viewer | Barcode Generation | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 77 | ASPAC - SIT 2
31 | Closed | Daeja_Viewer_BookMark: View bookmark icon is displayed as "Select Bookmark" in tooltip. | Viewer Configuration | Code | Code Error | 3 - Medium | 4 - Low | ksseng | ksseng | 2015-01-28 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 6 | ASPAC - SIT 2
32 | Closed | Barcode Generation: Decription field is getting displayed as text field instead of dropdown. | Barcode Generation | Code | Code Error | 3 - Medium | 3 - Medium | bysiva | axplac | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 37 | ASPAC - SIT 2
33 | Closed | DataCap: Mismatch between the value displayed under 'Department' and the Requirement sheet for "A&H Claims" | Datacap Scanning | Config-Data | App DB | 2 - High | 2 - High | axplac | bysiva | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 9 | ASPAC - SIT 2
34 | Closed | Enhnacement Request: Need to include the Build number or the version number in the build | ACEView | Known Issue | Accepted as it is | 4 - Low | 4 - Low | axravi | bysiva | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 6 | ASPAC - SIT 2
35 | Closed | Document Generation_System does not display the missing mandatory “PO Item row” to PO Item list in the mandatory field error message | Document Generation | Design | Code Design | 3 - Medium | 3 - Medium | axrath | axplac | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 14 | ASPAC - SIT 2
36 | Closed | Daeja_Viewer_Annotation: "Annotations failed to load" error message is displayed, when an annotated document is retrived post saving the annotations. | Viewer Configuration | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-01-28 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 6 | ASPAC - SIT 2
37 | Closed | Daeja_Viewer_BookMark: "View Bookmarks" dialog box is displayed instead of "delete bookmarks" dialog box, on clicking the "delete bookmark" icon. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-28 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 6 | ASPAC - SIT 2
38 | Closed | SendEmail : Prompt message("Yes" , "No" , "Cancel") is not getting displayed when selecting SendEmail in Document Action icon. | Send Email | Code | Code Error | 3 - Medium | 2 - High | swsure | axplac | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 105 | ASPAC - SIT 2
39 | Closed | All caseIDs has to be sent to Vega Interchange with 1 ack xml per caseID | ACEView | Environment | Configurations | 3 - Medium | 3 - Medium | hvpras | bysiva | 2015-01-28 | Vega Interchange | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-29 | 1 | ASPAC - SIT 2
40 | Closed | AceView: 'Barcode Generation'_Not able to view the values based on Filter fields updated | Barcode Generation | Code | Code Error | 1 - Critical | 1 - Critical | axplac | bysiva | 2015-01-28 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 7 | ASPAC - SIT 2
41 | Closed | Document Generation_Unable to scroll horizontally and view the the PO document tab fields and items | Document Generation | Product Limitation |  | 4 - Low | 4 - Low | axrath | axplac | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 106 | ASPAC - SIT 2
42 | Closed | Daeja_Viewer_Split_Functionality:Split documents functionality is available for single page TIFF and PDF documents. | Viewer Configuration | Code | Code Merge | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-29 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 8 | ASPAC - SIT 2
43 | Closed | Daeja_Viewer_Annotations: Strike through applied to the stamp is not retrieved, when the document is retrieved post saving the annotations. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-29 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 5 | ASPAC - SIT 2
44 | Closed | Daeja_Viewer_Annotations: Highlighted text is not viewable when the document is retrieved, post saving it. | Viewer Configuration | Requirement | New functionality | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-29 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 12 | ASPAC - SIT 2
45 | Closed | Email : Unable to view the attachments present in the email as a separate entity in ACEView. | Email | Known Issue | Accepted as it is | 2 - High | 2 - High | stsure | stsure | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 40 | ASPAC - SIT 2
46 | Closed | Document Generation_: Case Actions-Save does not save the contents of the PO document tab | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-18 | 20 | ASPAC - SIT 2
47 | Closed | Document Generation_: Random date is populated in the “Request date” and “Approval Date” fields when random values are given as input | Document Generation | Config-Data | App DB | 4 - Low | 4 - Low | axrath | axplac | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 83 | ASPAC - SIT 2
48 | Closed | Document Generation_Vendor ,Requestor, currency fields values are not extracted from PO invoicing tab and populated in the PO document tab | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 96 | ASPAC - SIT 2
49 | Closed | BarCodeGeneration - Sorting Option is not available in the header column in barocde generation tab. | Barcode Generation | Requirement | New functionality | 3 - Medium | 3 - Medium | swsure | swsure | 2015-01-29 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-09 | 11 | ASPAC - SIT 2
50 | Closed | Daeja_Viewer_Viewer_Config: View attachments icon is not available when the email body is annotated and retrieved post saving. | Viewer Configuration | Requirement | New functionality | 2 - High | 2 - High | ksseng | ksseng | 2015-01-29 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 12 | ASPAC - SIT 2
51 | Closed | ACEView URL Login page is not getting displayed. | Environment | Environment | Environmental | 1 - Critical | 1 - Critical | stsure | bysiva | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-30 | 0 | ASPAC - SIT 2
52 | Closed | Daeja Viewer URL Login page is not getting displayed. | Environment | Environment | Environmental | 1 - Critical | 1 - Critical | ksseng | bysiva | 2015-01-30 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-01-30 | 0 | ASPAC - SIT 2
53 | Closed | We are not able to login with Filenet Workplace XT. | Environment | Environment | Environmental | 1 - Critical | 1 - Critical | stsure | axplac | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-02 | 3 | ASPAC - SIT 2
54 | Closed | Daeja_Viewer_Bookmark: Bookmark description field is accepting more than 50 characters. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-30 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-16 | 17 | ASPAC - SIT 2
55 | Closed | Error Folder is not available in ApolloRefresh-ICCS2-Test2@acegroup.com Mailbox. | Email | Environment | Environmental | 2 - High | 2 - High | stsure | bysiva | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-02 | 3 | ASPAC - SIT 2
56 | Closed | Daeja_Viewer_Annotations: "Annotations failed to load" error message is displayed when a document is annotated with various "Draw Stamp" options available and retrieved post saving the annotations changes made. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-01-30 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 4 | ASPAC - SIT 2
57 | Closed | Viewer Configuration_System does not navigate to the hyperlinked page on clicking the annotation on which hyperlink is created | Viewer Configuration | Code | Code Error | 2 - High | 2 - High | axrath | ksseng | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 7 | ASPAC - SIT 2
58 | Closed | AceView: Business Unit value is not displayed as Expected<code Description> | ACEView | Config-Data | App DB | 2 - High | 2 - High | axplac | bysiva | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 12 | ASPAC - SIT 2
59 | Closed | Datacap scanning _Mismatch of 'Modified By" data between 'Workplace XT Properties' and 'ACEVIEW' | Datacap Scanning | Testing | Not Reproducible | 2 - High | 2 - High | swsure | swsure | 2015-01-30 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 38 | ASPAC - SIT 2
60 | Closed | ACEView - Barcode Generation: Document Separator Barcode Text Value is not generated/displayed as expected in ACEView when viewing in Viewer | Barcode Generation | Code | Code Error | 2 - High | 1 - Critical | rxvenk | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 10 | ASPAC - SIT 2
61 | Closed | ACEView - Barcode Generation: Work Item Separator Barcode Text Value is not as expected in ACEView | Barcode Generation | Code | Code Error | 2 - High | 2 - High | rxvenk | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 10 | ASPAC - SIT 2
62 | Closed | ACEView - Barcode Generation: Business Unit Barcode (ACE INA Taiwan Branch) Description and Text Value is not as expected in ACEView | Barcode Generation | Config-Data | App DB | 2 - High | 2 - High | rxvenk | rxvenk | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
63 | Closed | ACEView - Barcode Generation: Underwriting Year (UW Year 2010) Barcode Text Value is not displayed as expected (Ref. ASPAC_IngestionConfiguration_1.1_Updated Document) | Barcode Generation | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 10 | ASPAC - SIT 2
64 | Closed | ACEView - Barcode Generation: Priority Barcode Text is not not displayed as Expected | Barcode Generation | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 74 | ASPAC - SIT 2
65 | Closed | ACEView - Barcode Generation: Mentioned field in the defect in the generated barcode pdf document for Post Type | Barcode Generation | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 74 | ASPAC - SIT 2
66 | Closed | ACEView - "Log out" button not displayed in Page Header (Right Hand corner) | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | axplac | hvpras | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 79 | ASPAC - SIT 2
67 | Closed | ACEView - Barcode Generation: Business Unit Barcode (ACE MIDC Malaysia) Description is not as expected in ACEView | Barcode Generation | Config-Data | App DB | 3 - Medium | 2 - High | rxvenk | bysiva | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
68 | Closed | ACEView - Daeja Viewer not displayed as Expected(Sporadic issue) | ACEView | Environment | Environmental | 3 - Medium | 3 - Medium | axplac | bysiva | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 3 | ASPAC - SIT 2
69 | Closed | ACEView - Barcode Generation: Business Unit Barcode (ACE AIOIC Thailand Branch) Description is not as expected in ACEView | Barcode Generation | Config-Data | App DB | 3 - Medium | 2 - High | rxvenk | bysiva | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
70 | Closed | DataCap_Business Unit field not displaying the full value | Datacap Scanning | Environment | Environmental | 3 - Medium | 2 - High | axplac | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
71 | Closed | ACEView - Barcode Generation: Country Barcode text displayed in Daeja Viewer has a mismatch with the config sheet value displayed | ACEView | Requirement | Business Requirements Incorrect | 2 - High | 1 - Critical | axplac | axplac | 2015-01-31 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 3 | ASPAC - SIT 2
72 | Closed | ACEView - Barcode Generation: The Department Barcode text displayed in the Application has a mismatch with the config sheet | Barcode Generation | Config-Data | App DB | 2 - High | 2 - High | axplac | axplac | 2015-01-31 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
73 | Closed | ACEView - Barcode Generation: File, Folder, Document type barcode is not generated as expected. | Barcode Generation | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 74 | ASPAC - SIT 2
74 | Closed | ACEView - Barcode Generation: Business Unit - 0 - Others barcode is not listed in Ingestion Configuration sheet. | Barcode Generation | Config-Data | App DB | 3 - Medium | 3 - Medium | rxvenk | rxvenk | 2015-01-31 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 4 | ASPAC - SIT 2
75 | Closed | Document Generation_For quantity field , the values after decimal point is not getting displayed in the generated preview document | Document Generation | Code | Code Error | 3 - Medium | 2 - High | axravi | axplac | 2015-02-02 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 102 | ASPAC - SIT 2
76 | Deferred | Multipage Embedded document is not getting loaded in Daeja viewer. | Viewer Configuration | PMR | Accepted as it is | 3 - Medium | 2 - High | stsure | axplac | 2015-02-02 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC |  | 115.7972 | ASPAC - SIT 2
79 | Closed | Daeja_Viewer_Annotations: The changes made to an existing sticky note is not getting retrieved, when the document is retrieved post saving it. | Viewer Configuration | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-02-02 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 4 | ASPAC - SIT 2
80 | Closed | When trying to Open the document injested in Finance Indexing Queue by double clicking on it, error message is displayed. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | stsure | stsure | 2015-02-02 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-30 | 56 | ASPAC - SIT 2
81 | Closed | Query - Daeja_Viewer_Viewer_Config: Annotations toolbar is not enabled for the attachments present in the Email document. | Viewer Configuration | Requirement | New functionality | 2 - High | 2 - High | ksseng | bysiva | 2015-02-02 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-05 | 3 | ASPAC - SIT 2
82 | Closed | Query_Daeja_Viewer_General_Viewer_Config: There's no option to view the document that was previously being viewed. | Viewer Configuration | Requirement | New functionality | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-02-02 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 4 | ASPAC - SIT 2
83 | Closed | Daeja_Viewer_Annotations: Appropriate message is not displayed, when an annotation is deleted. | Viewer Configuration | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-02-02 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-04 | 2 | ASPAC - SIT 2
84 | Closed | ViewerConfiguration_Unable to Print the current page of the document through Daeja viewer | Viewer Configuration | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axplac | 2015-02-02 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 8 | ASPAC - SIT 2
85 | Closed | ACE View_Unable to Login to ACE view URL | ACEView | Environment | Build issue | 1 - Critical | 1 - Critical | axrath | bysiva | 2015-02-03 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-03 | 0 | ASPAC - SIT 2
86 | Closed | Document Generation_Complete address of vendor as given in the Ace view is not displayed in the Generated document | Document Generation | Code | Code Error | 4 - Low | 4 - Low | axrath | axrath | 2015-02-03 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 3 | ASPAC - SIT 2
87 | Closed | Daeja_Viewer_BookMarks: Add, view, update and delete bookmarks options are not available for the file types .png, .xls, .jpeg, .msg, .bmp, etc. | Viewer Configuration | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-02-03 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-06 | 3 | ASPAC - SIT 2
90 | Closed | UI Validation : Dropdown field arrows are not getting displayed properly in ACE View UI | ACEView | Code | Code Error | 4 - Low | 4 - Low | stsure | stsure | 2015-02-03 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-30 | 55 | ASPAC - SIT 2
91 | Closed | Issue: Email Broker: Mail formats like Meeting invite and Mails without attachments(sent to noheader mailbox)are ignored by ICC and neither processed nor moved to error folder | Email | Known Issue | Accepted as it is | 2 - High | 2 - High | bysiva | axravi | 2015-02-04 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 7 | ASPAC - SIT 2
92 | Closed | Daeja_Viewer_Annotations: The unsaved annotations are not getting saved, once the user clicks "Ok" button on the prompt box that appears on refreshing the page. | Viewer Configuration | Requirement | New functionality | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-02-04 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 6 | ASPAC - SIT 2
93 | Deferred | Daeja_Viewer_Annotations: The number displayed over the sticky notes is varying once the document is retrieved post saving it. | Viewer Configuration | PMR | Accepted as it is | 3 - Medium | 3 - Medium | ksseng | kxkana | 2015-02-04 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC |  | 113.7972 | ASPAC - SIT 2
94 | Deferred | ACEView_: ACE View application logs out when backspace is pressed | ACEView | Known Issue | Accepted as it is | 2 - High | 2 - High | axrath | bybull | 2015-02-04 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC |  | 113.7972 | ASPAC - SIT 2
95 | Closed | Document Generation_ System throws Un Expected error when tried to preview a document with multiple rows | Document Generation | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-30 | 53 | ASPAC - SIT 2
96 | Closed | Barcode Generation : The "Select All " check box should be removed | Barcode Generation | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 33 | ASPAC - SIT 2
97 | Closed | Daeja_Viewer_Annotation: "Transparent" edit option available for "Draw Transparent Text" and "Draw Solid Text" is not functioning. | Viewer Configuration | Requirement | New functionality | 4 - Low | 4 - Low | ksseng | ksseng | 2015-02-05 | Daeja Viewer | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 5 | ASPAC - SIT 2
98 | Closed | The rotated documents after scanning is not displayed in ACEView | Datacap Scanning | PMR |  | 3 - Medium | 3 - Medium | swsure | bysiva | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 29 | ASPAC - SIT 2
99 | Closed | The Ingestion File number is not displayed in the Filenet Properties | Datacap Scanning | Testing | Not Reproducible | 3 - Medium | 3 - Medium | swsure | axplac | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-12 | 7 | ASPAC - SIT 2
100 | Closed | 'Document Type Code' and 'Folder Type Code' is not displayed as per Configuration sheet | Datacap Scanning | Config-Data | App DB | 3 - Medium | 3 - Medium | swsure | swsure | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 6 | ASPAC - SIT 2
101 | Closed | The Application is hanged by clicking on 'Hold' button | Datacap Scanning | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | swsure | bysiva | 2015-02-05 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 5 | ASPAC - SIT 2
103 | Closed | Document Generation_Unable to enter values for the PO Item fields | Document Generation | Code | Code Error | 4 - Low | 4 - Low | axrath | axrath | 2015-02-06 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 28 | ASPAC - SIT 2
105 | Closed | Email: Emails are not getting processed and remains in inbox even after 15 minutes. | Environment | Environment | Environmental | 2 - High | 2 - High | ksseng | ksseng | 2015-02-09 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 1 | ASPAC - SIT 2
106 | Closed | Document Generation_ Unable to preview or Publish document | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-02-09 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 78 | ASPAC - SIT 2
107 | Closed | Barcode_Generation: Unable to view Barcode when we click on "Generate Barcode". | Barcode Generation | Environment | System/Service failure | 2 - High | 2 - High | stsure | stsure | 2015-02-09 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-10 | 1 | ASPAC - SIT 2
108 | Closed | DataCap: Able to scan in "Simplex Grayscale Scan" but not in "Simplex Black and White Scan" | Datacap Scanning | Code | Code Error | 3 - Medium | 2 - High | axplac | axplac | 2015-02-09 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 2 | ASPAC - SIT 2
109 | Closed | Email: Audit logs are not available in Processed Files folder for the emails that got processed successfully. | Environment | Environment | Environmental | 3 - Medium | 3 - Medium | stsure | stsure | 2015-02-10 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 1 | ASPAC - SIT 2
110 | Closed | Daeja_Viewer_Filenet: Unable to view documents in Daeja Viewer via filenet | Environment | Environment | Environmental | 2 - High | 2 - High | ksseng | ksseng | 2015-02-10 | Filenet | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-02-11 | 1 | ASPAC - SIT 2
111 | Closed | Barcode Generation: Error Message is not displayed when clicking generate barcode without selecting filters | Barcode Generation | Code | Code Error | 3 - Medium | 2 - High | swsure | axplac | 2015-02-10 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 73 | ASPAC - SIT 2
112 | Closed | Filter panel Hide Icon is not visible | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | swsure | axplac | 2015-02-10 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 24 | ASPAC - SIT 2
113 | Closed | Barcode Generation - Reset funcationality is not clearing the right side panel details, when we click reset button. | Barcode Generation | Code | Code Error | 3 - Medium | 2 - High | swsure | axplac | 2015-02-10 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 62 | ASPAC - SIT 2
114 | Closed | BarCode Generation - After clicking reset button, Code and Description drop down boxes are still enabled without the selecting barcode type. | Barcode Generation | Code | Code Error | 3 - Medium | 3 - Medium | swsure | axplac | 2015-02-10 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 52 | ASPAC - SIT 2
115 | Closed | SendEmail - Subject line is not displaying 'Various Documents attached' as expected when multiple documents attached in Email. | Send Email | Code | Code Error | 4 - Low | 4 - Low | swsure | axplac | 2015-02-11 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 44 | ASPAC - SIT 2
116 | Closed | The T&E files displayed in Workplace Xnet is not available in ACEView | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | swsure | swsure | 2015-02-11 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 30 | ASPAC - SIT 2
117 | Closed | Ingestion File number is not displayed in Workplace XT for Scanned T&E file | Datacap Scanning | Code | Code Error | 3 - Medium | 3 - Medium | swsure | bysiva | 2015-02-11 | Filenet | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-05 | 22 | ASPAC - SIT 2
119 | Closed | Document Generation_ Generated document in document panel does not contain Folder type, Document type and Filename details | Document Generation | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-02-12 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 71 | ASPAC - SIT 2
120 | Closed | Send Email - Subject Line is not displaying as same as Document description in Microsoft Outlook. | Send Email | Code | Code Error | 3 - Medium | 3 - Medium | swsure | swsure | 2015-02-12 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 43 | ASPAC - SIT 2
121 | Closed | Query_Daeja_Viewer_BookMark: No warning message is displayed, when user tries to add a bookmark without description(empty). | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | axplac | 2015-02-16 | Daeja Viewer | Build 1A - Cycle 2 | Release 1_ASPAC | 2015-02-16 | 0 | ASPAC - SIT 2
122 | Closed | Daeja_Viewer_BookMark: Alert message is not displayed when a user tries to add a bookmark with blank description. | Viewer Configuration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-02-16 | Daeja Viewer | Build 1A - Cycle 2 | Release 1_ASPAC | 2015-02-19 | 3 | ASPAC - SIT 2
123 | Closed | ACE View_ Unable to Login to ACEView | ACEView | Environment | Environmental | 1 - Critical | 1 - Critical | axrath | bysiva | 2015-02-17 | ACEView | Build 1A - Cycle 2 | Release 1_ASPAC | 2015-02-17 | 0 | ASPAC - SIT 2
124 | Closed | Document Generation_System throws an unexpected error when user clicks on PO document tab | Document Generation | Testing | Inconsistent | 4 - Low | 4 - Low | axrath | axrath | 2015-02-18 | ACEView | Build 1A - Cycle 2 | Release 1_ASPAC | 2015-04-22 | 63 | ASPAC - SIT 2
125 | Closed | AceView: Smoke test: Error message is displayed when trying to login to AceView | ASPAC Workflow | Environment | Environmental | 1 - Critical | 1 - Critical | axplac | axplac | 2015-02-24 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-02-24 | 0 | ASPAC - SIT 2
126 | Closed | ASPAC_ Unable to Create a new PO | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | axrath | bysiva | 2015-02-24 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-02-26 | 2 | ASPAC - SIT 2
127 | Closed | ASPAC_Unable to view the drop down list for the field “Payment Method” displayed in Po invoicing tab | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | bysiva | 2015-02-24 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-01 | 5 | ASPAC - SIT 2
128 | Closed | ASPAC_ Unable to add rows in the Cost Allocation tab for New or already created PO Invoice | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | axrath | axplac | 2015-02-24 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-07 | 11 | ASPAC - SIT 2
129 | Closed | Unable to View the document in Daeja Viewer in AceView Application | Environment | Environment | Environmental | 2 - High | 2 - High | axrath | bysiva | 2015-02-25 | Daeja Viewer | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-02-25 | 0 | ASPAC - SIT 2
130 | Closed | AceView: Drag n Drop: Screen layout not displayed as Expected | Drag and Drop | Code | Code Error | 4 - Low | 4 - Low | axplac | stsure | 2015-02-25 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 57 | ASPAC - SIT 2
131 | Closed | AceView: Daeja Viewer: Not able to view th file File with .jpg extension | Daeja_Viewer ACEView Integration | Code | Code Error | 2 - High | 2 - High | axplac | bysiva | 2015-02-26 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-03 | 5 | ASPAC - SIT 2
132 | Closed | AceView: Drag and Drop: Field "Folder Type" not displaying the expected values when selected PO Invoice in the field "File Type" displayed under Document tab | Drag and Drop | Config-Data | App DB | 2 - High | 2 - High | axplac | bysiva | 2015-02-26 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-01 | 3 | ASPAC - SIT 2
133 | Closed | Security_ “Status “of an existing user is not displayed in the search results | Security | Code | Code Error | 3 - Medium | 4 - Low | axrath | bysiva | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-02 | 3 | ASPAC - SIT 2
134 | Closed | AceView: Drag n Drop: Error message displayed when trying to Drag n Drop multiple document to AceView | Drag and Drop | Code | Code Error | 2 - High | 2 - High | axplac | bysiva | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 11 | ASPAC - SIT 2
135 | Closed | ACEView_ApolloPrint : The naming convention of the printed document is not in correct format. | ACEViewPrint | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 10 | ASPAC - SIT 2
136 | Closed | Security_When trying to select another contact, previous contact is getting deselected but newly clicked contact in not getting selected(search results screen) | Security | Code | Code Error | 4 - Low | 4 - Low | axrath | axplac | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-04 | 5 | ASPAC - SIT 2
137 | Closed | Security_ In user profile, Instead of “User country” the field name is displayed as “country” | Security | Code | Code Error | 4 - Low | 4 - Low | axrath | axplac | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 7 | ASPAC - SIT 2
138 | Closed | ACEView_ApolloPrint : The documents are not getting deleted from the ACEView Print Clipboard folder upon the successful completion of document importing into ACEView. | ACEViewPrint | Environment | Environmental | 2 - High | 2 - High | ksseng | ksseng | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 11 | ASPAC - SIT 2
139 | Re-opened | ACEViewPrint : The original filename is not getting displayed in the convention <filename> rather somether name is getting displayed, when original file is in the .tiff, .bmp, .png and .msg format. | ACEViewPrint |  |  | 3 - Medium | 3 - Medium | ksseng | axravi | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 90.7972 | ASPAC - SIT 2
140 | Closed | Document properties should be read only but they are editable in ACEView application. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 49 | ASPAC - SIT 2
141 | Closed | Drag and Drop - Error message is getting displayed when email is drag and drop to the work item. | Drag and Drop | Requirement | Missed BA requirement | 3 - Medium | 3 - Medium | swsure | axplac | 2015-02-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-02-27 | 0 | ASPAC - SIT 2
142 | Closed | Security_ Super Administrator is unable to assign a personal workbasket of an user to another user | Security | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 4 | ASPAC - SIT 2
143 | Closed | SendFax : Fax number field in the send fax dialog box is not accepting the fax number in correct format. | Send Fax | Requirement | New functionality | 1 - Critical | 1 - Critical | ksseng | bysiva | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-03 | 1 | ASPAC - SIT 2
144 | Closed | Send Fax : The fax ID in the "To" field of the newly triggered mail is not in correct format. | Send Fax | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 4 | ASPAC - SIT 2
145 | Closed | ASPAC Workflow_Unable to perform "Send Invoice for Checking" action on a "INVOICE AWAITING CODING” Status workitem | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | axrath | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-04 | 2 | ASPAC - SIT 2
146 | Closed | Upload Document: Folder Type and Document Type should be automatically populated. | Upload Document | Code | Code Error | 2 - High | 2 - High | stsure | bysiva | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 9 | ASPAC - SIT 2
147 | Re-opened | Vega UI - The PO work basket names are not in sequence in Home Screen. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | swsure | axdubo | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 87.7972 | ASPAC - SIT 2
148 | Closed | Security_ System does not warn the user to save the changes made when user clicks on any other menu option without saving the changes made during “Add user “ flow | Security | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axrath | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 38 | ASPAC - SIT 2
149 | Closed | Upload Document : System does not populate Object ID field when the document is uploaded. | Upload Document | Requirement | Business Requirements Incorrect | 2 - High | 2 - High | stsure | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 50 | ASPAC - SIT 2
150 | Closed | Drag & Drop: When email(s) are added to the File via Drag & Drop, PackageID and IsParent document properties should be displayed. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-24 | 22 | ASPAC - SIT 2
151 | Closed | Security_ System displays the message that “Admin user is inactive”, when tried to make the an user inactive whose personal workbasket is assigned to an user with privilege “Read only” | Security | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 4 | ASPAC - SIT 2
152 | Closed | Manage Notes:System Notes are not getting generated in Notes/Audit Trial tab when user performs an action on a work item | Notes | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 25 | ASPAC - SIT 2
153 | Closed | Security_ system displays message “ updated successfully” even though when no changes made are updated | Security | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axrath | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 38 | ASPAC - SIT 2
155 | Closed | Drag and Drop - Documents are not able to copy/move/Link to another folders/files. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 42 | ASPAC - SIT 2
157 | Closed | Drag and Drop - Drop Left and Drop Right Functionality is not working as expected. | Drag and Drop | Product Limitation |  | 2 - High | 2 - High | swsure | axplac | 2015-03-02 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 81 | ASPAC - SIT 2
158 | Closed | Security_ No user is displayed in the available list in the “assigned list” in the assign workbasket screen | Security | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
159 | Closed | Security_Search results are not displayed when Status is selected as "Active" while searching for an existing active user | Security | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
160 | Closed | Security_ Changes made is the assign workbasket screen are not updated when tried to save and retrieve | Security | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
161 | Closed | Drag and Drop - Reload option is not working as expected to change the failed status to 'in progress'. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | swsure | swsure | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 44 | ASPAC - SIT 2
162 | Closed | Add button not enabled on the Cost Allocation | ASPAC Workflow | Wrongly Logged | Duplicate | 1 - Critical | 1 - Critical | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-03 | 0 | ASPAC - SIT 2
163 | Closed | LAN ID in App DB | Security | Code | Code Error | 2 - High | 2 - High | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 7 | ASPAC - SIT 2
164 | Closed | Saving Filter does not work | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
165 | Closed | Behaviour of new PO Button is not consistent across Work Baskets | Workbasket | Code | Code Error | 2 - High | 2 - High | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
166 | Closed | PO Details Tab shows dollar signs next to amount fields irrespective of the selected currency | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 3 | ASPAC - SIT 2
167 | Closed | File Type should not be selectable in Documents Tab (should be inherited from the File) | ASPAC Workflow | Requirement | New functionality | 2 - High | 2 - High | jyrowl | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-01 | 59 | ASPAC - SIT 2
168 | Closed | PO Details Tab does not Save Data automatically when switching between Work Items | ASPAC Workflow | Known Issue | Accepted as it is | 2 - High | 2 - High | jyrowl | axravi | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 49 | ASPAC - SIT 2
169 | Closed | Reset does not reset Work Basket Filter Criteria | Workbasket | Code | Code Error | 3 - Medium | 2 - High | jyrowl | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 66 | ASPAC - SIT 2
170 | Closed | Active Mega Filter Icon disappears when switching Work Baskets | Workbasket | Code | Code Error | 3 - Medium | 2 - High | jyrowl | jyrowl | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 63 | ASPAC - SIT 2
171 | Closed | Error Text Not defined for Unexpected Error | ASPAC Workflow | Testing | Inconsistent | 4 - Low | 3 - Medium | jyrowl | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 50 | ASPAC - SIT 2
172 | Closed | Document properties are displayed as expected when ingesting Email Using Email Service | Email | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | stsure | axplac | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-19 | 15 | ASPAC - SIT 2
173 | Closed | Changes made in the PO Invoice tab are not reflected in the PO document tab | Document Generation | Testing | Duplicate | 2 - High | 2 - High | axrath | bysiva | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-04 | 0 | ASPAC - SIT 2
174 | Re-opened | ACEView : The fields are not present in the expected format in the Vendor Search page. | ASPAC Workflow |  |  | 3 - Medium | 4 - Low | ksseng | axsavi | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 85.7972 | ASPAC - SIT 2
175 | Closed | ACEView : The column header in the vendor search results is not displayed in the expected format. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | bysiva | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 6 | ASPAC - SIT 2
177 | Closed | Manage Notes: We are able to save "Notes" without giving values in Mandatory fields. | Notes | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 7 | ASPAC - SIT 2
178 | Closed | Upload document: Not able to enter the file path of the document when we try to upload document using "Upload" icon. | Upload Document | Wrongly Logged | Accepted as it is | 2 - High | 2 - High | stsure | axplac | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 5 | ASPAC - SIT 2
179 | Closed | Manage Notes: 'Note type' field is disabled when we try to Edit the Note details individually. | Notes | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 7 | ASPAC - SIT 2
180 | Closed | Security : Business units moves all the Assigned Business Unit to Available Business Unit , when we try to move a particular Country from Assigned country to Available country . | Security | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 2 | ASPAC - SIT 2
181 | Closed | ACEView_Daeja_Viewer_Split_Functionality : Audit notes are not captured when a document is split. | Notes | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-03-04 | Daeja Viewer | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-24 | 20 | ASPAC - SIT 2
182 | Closed | Diary – Open File is not checked by default, when close is checked. | Diary | Code | Code Error | 2 - High | 2 - High | swsure | swsure | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 7 | ASPAC - SIT 2
183 | Closed | ACEView_Daeja_Viewer_Split_Functionality : "Ingestion type" in the document properties is displayed as "Phone" instead of "Split". | Daeja_Viewer ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-03-04 | Daeja Viewer | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 6 | ASPAC - SIT 2
184 | Closed | Diary : Error Message is not displayed properly, when time is not given while creating diary. | Diary | Code | Code Error | 3 - Medium | 3 - Medium | swsure | swsure | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 7 | ASPAC - SIT 2
185 | Closed | Diary – Sort functionality option is disabled. | Diary | Code | Code Error | 3 - Medium | 3 - Medium | swsure | swsure | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 7 | ASPAC - SIT 2
186 | Closed | ACEView_Daeja_Viewer_Split_Functionality : The document description of the newly created document is not in expected format. | Daeja_Viewer ACEView Integration | Code | Code Error | 4 - Low | 4 - Low | ksseng | ksseng | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 2 | ASPAC - SIT 2
187 | Closed | ASPAC flow_ Work Item is moved to "Po Invoice Payments" workbasket on performing "Send Invoice for Approval" action | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 2 | ASPAC - SIT 2
189 | Closed | AceView_PO Invoicving Tab:The fields displayed does not define the mandatory fields | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-03 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-01 | 29 | ASPAC - SIT 2
190 | Closed | AceView: PO Invoicing Tab: The drop down values for the field Purchase Category, does not reflect the Choice list values. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-04 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 2 | ASPAC - SIT 2
191 | Open | Manage Notes: When we deselect all the columns from the list of the column headings, there is no option to "Add columns" again | Open File and Open Case |  |  | 3 - Medium | 4 - Low | stsure | kxbizi | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 84.7972 | ASPAC - SIT 2
192 | Closed | Manage Notes: "Type" filter functionality for Notes is not displayed as Expected. | Notes | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 46 | ASPAC - SIT 2
193 | Closed | Diary – Filter icon is not present in status field to sort “Expired” & “Active”. | Diary | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 43 | ASPAC - SIT 2
195 | Closed | ACEView_SendFax : Documents are not faxed in their native format. | Send Fax | Code | Code Error | 2 - High | 1 - Critical | ksseng | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 8 | ASPAC - SIT 2
196 | Closed | ACEView_SendFax : Sent fax is not ingested back into ACEView when the "Save generated email/fax to ACEView" checkbox is Checked. | Send Fax | Code | Code Error | 2 - High | 1 - Critical | ksseng | ksseng | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 60 | ASPAC - SIT 2
197 | Closed | Field names displayed in UI mismatches with Use case document | ASPAC Workflow |  |  | 3 - Medium | 2 - High | rxloga | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 75 | ASPAC - SIT 2
198 | Closed | Irrelevant error note is displayed for 'Business Unit' mandatory field | ASPAC Workflow | Code | Code Error | 4 - Low | 4 - Low | rxloga | dzmais | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 60 | ASPAC - SIT 2
199 | Closed | ACEView_Print : The expected error message is not displayed when the mandatory fields in the "Send Fax" window is left blank. | Send Fax | Code | Code Error | 2 - High | 2 - High | ksseng | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 29 | ASPAC - SIT 2
200 | Closed | ASPAC flow_System prompts a comment box when peforming approve order action, but the comment box is not mandatory. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 48 | ASPAC - SIT 2
201 | Closed | ASPAC Workflow_Ok button is enabled in the comment pop up even when the comment box is left blank - decline order action | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 64 | ASPAC - SIT 2
202 | Closed | ACEView_SendFax : It is not eminent that the "Cancel" button is present there in the "SendFax" window. | Send Fax | Code | Code Error | 4 - Low | 4 - Low | ksseng | ksseng | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 5 | ASPAC - SIT 2
203 | Closed | ASPAC: Purchase Type and Requestor fields should be editable for an "Order awaiting approval" work item | ASPAC Workflow | Known Issue | Accepted as it is | 2 - High | 2 - High | axrath | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-26 | 21 | ASPAC - SIT 2
204 | Re-opened | ASPAC: Error message screen mismatches with the Screen in Usecase document | ASPAC Workflow |  |  | 4 - Low | 4 - Low | rxloga | dzmais | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 84.7972 | ASPAC - SIT 2
205 | Closed | ASPAC Workflow_System does not validate the mandatory fields while performing "Approve order" action | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 8 | ASPAC - SIT 2
206 | Closed | ASPAC: Title of the Comment pop-up window displayed mismatcehs with Usecase document | ASPAC Workflow | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 63 | ASPAC - SIT 2
207 | Closed | ACEView_SendFax : The extension of the documents attached to the newly triggered email is repeated. | Send Fax | Code | Code Merge | 3 - Medium | 3 - Medium | ksseng | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 8 | ASPAC - SIT 2
208 | Closed | ASPAC – PO Invoice screen:Though the drop values are displayed, but still user can enter any value in the field without selecting the dropdown values and can be saved. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 22 | ASPAC - SIT 2
209 | Closed | ACEView_SendFax : "Send Fax" option is not disabled when no documents are selected from the document panel. | Send Fax | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 29 | ASPAC - SIT 2
210 | Open | ASPAC – Prompt message is not displaying stating ““Are you sure you want to perform the Close – Created in Error action?”, after clicking on “Closed – Created in Error”. | ASPAC Workflow |  |  | 4 - Low | 4 - Low | swsure | kxbizi | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 84.7972 | ASPAC - SIT 2
213 | Closed | AceView: Cost Allocation_System does not allow to enter value for the Alternate account, Affliate code, Department and hence cannot add cost allocation to a PO invoice | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axplac | bysiva | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 41 | ASPAC - SIT 2
214 | Closed | AceView: Cost Allocation Tab: The field 'Amount', the default value is not displayed as Expected | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axplac | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 5 | ASPAC - SIT 2
215 | Closed | ASPAC Workflow_ Unable to select country value in PO Invoice tab, so unable to perform any action on the workitem, since country is a mandatory field | ASPAC Workflow | Requirement | New functionality | 1 - Critical | 1 - Critical | axrath | bysiva | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-06 | 0 | ASPAC - SIT 2
216 | Closed | ACEView_Alerts & Notifications : Unable to add alert notes to a file/workitem. | Alerts & Notification | Requirement | New functionality | 2 - High | 2 - High | ksseng | ksseng | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 3 | ASPAC - SIT 2
217 | Closed | ASPAC: New PO Invoice button is unavailable for all PO workbaskets except 'PO Invoice Processing' workbasket | ASPAC Workflow | Testing | QA Knowledge Gap | 2 - High | 2 - High | axrath | axrath | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-09 | 3 | ASPAC - SIT 2
218 | Open | ACEView_Alerts & Notification : The notes getting listed in the "Alert Note" window is not properly aligned. | Alerts & Notification |  |  | 4 - Low | 4 - Low | ksseng | kxbizi | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 83.7972 | ASPAC - SIT 2
219 | Closed | ACEView_Alerts & Notification : Unable to view the alert note added to a document by clicking on the visual indicator in the document panel. | Alerts & Notification | Code | Code Error | 2 - High | 2 - High | ksseng | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 7 | ASPAC - SIT 2
220 | Closed | AceView: System should not allow the PO invoice posted with Status "Invoice Approved-Pending Auto Post" when Cost Allocation Tab is not updated (blank). | ASPAC Workflow | Testing | QA Knowledge Gap | 2 - High | 2 - High | axplac | axplac | 2015-03-05 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-12 | 7 | ASPAC - SIT 2
221 | Open | ACEView_Alerts & Notification : Expected label is not present in the "View Note" popup for the alerts note description. | Alerts & Notification |  |  | 4 - Low | 4 - Low | ksseng | kxbizi | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 83.7972 | ASPAC - SIT 2
222 | Closed | ACEView_Alerts & Notification : Unable to update existing notes. "Unknown error while updating note" error message is displayed. | Alerts & Notification | Code | Code Error | 2 - High | 2 - High | ksseng | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 7 | ASPAC - SIT 2
223 | Closed | Workbasket : Unable to Perform "Action" on a workitem from the workbasket | Workbasket | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 7 | ASPAC - SIT 2
224 | Closed | Workbasket : "Count Refresh" button in the workbasket panel is not displayed as expected. | Workbasket | Requirement | Business Requirements Incorrect | 2 - High | 2 - High | stsure | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 45 | ASPAC - SIT 2
225 | Closed | ASPAC: New PO record(a row) is created even when no data is entered and not Saved.No file number is displayed | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 63 | ASPAC - SIT 2
227 | Closed | AceView: File number for an PO invoice created is not displayed as Expected | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-06 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 11 | ASPAC - SIT 2
228 | Closed | AceView: Cost Allocation Tab: The row already created is not displayed immediately once clicked on the Cost Allocation tab. Have to wait for atleast 30 to 40 seconds to the row to appear. | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-07 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 4 | ASPAC - SIT 2
229 | Closed | Aceview: Under PO invoice, Currency dropdown values not displayed as expected . Choice list screen shot attached as reference | ACEView | Code | Code Error | 3 - Medium | 2 - High | axplac | bysiva | 2015-03-07 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-10 | 3 | ASPAC - SIT 2
230 | Closed | AceView: Cost Allocation: During the process of selecting a value for a field/entering a test field in the row; all of a sudden the row disappears. Hence would require to again start the process of adding a row and entering the data’s. | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-07 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 4 | ASPAC - SIT 2
231 | Closed | AceView: Cost Allocation: When added and saved the second row, then the first row which was already displayed is not displayed(removed) from the Cost Allocation screen | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | axplac | axplac | 2015-03-09 | ACEView | Build 1A - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 4 | ASPAC - SIT 2
232 | Re-opened | Workbasket: By default "Number of items per page " is set to 50. | Workbasket |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-03-09 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 80.7972 | ASPAC - SIT 2
233 | Open | Workbasket: Filter name text box is accepting more than 50 characters, | Workbasket |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-03-09 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC |  | 80.7972 | ASPAC - SIT 2
234 | Closed | ASPAC_In Cost allocation tab, Invoice date is displayed in mm/dd/yyyy format, instead of dd/mm/yyyy | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 30 | ASPAC - SIT 2
235 | Closed | ASPAC _Unable to Preview a PO Document | ASPAC Workflow | Environment | Environmental | 2 - High | 2 - High | axrath | axrath | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-11 | 1 | ASPAC - SIT 2
236 | Closed | ASPAC_System displays numbers in the ACE address field drop down of PO Document tab | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | kanixd | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-16 | 6 | ASPAC - SIT 2
237 | Closed | Reset button in Barcode Generation Page is not working as expected. | Barcode Generation | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 24 | ASPAC - SIT 2
238 | Closed | ACEView_Cost_Allocation_Tab : The columns in cost allocation tab are not displayed in expected order. | ASPAC Workflow | Code | Code Error | 4 - Low | 4 - Low | ksseng | dzmais | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 77 | ASPAC - SIT 2
239 | Closed | ASPAC – In cost allocation tab, affiliated code field is present as a mandatory field wrongly. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 17 | ASPAC - SIT 2
240 | Closed | ASPAC_Cost Allocation: Default values are not displayed for "Project code" and "Function code" fields in the Cost allocatiion tab | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 7 | ASPAC - SIT 2
241 | Closed | Email: Mails are not getting processed from Inbox folder. | Email | Code | Code Error | 2 - High | 1 - Critical | stsure | stsure | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 59 | ASPAC - SIT 2
242 | Closed | ASPAC: PO and T&E file number is not displayed in the right format | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-03-10 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 55 | ASPAC - SIT 2
243 | Closed | Manage Notes :Error message is getting displayed while saving the Edited Note details | Notes | Testing | Duplicate | 2 - High | 2 - High | stsure | stsure | 2015-03-11 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-12 | 1 | ASPAC - SIT 2
244 | Closed | AceView:Diary: Reminder message is getting displayed often in ACE View, even after Diary is inactive. | ACEView | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-11 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 2 | ASPAC - SIT 2
245 | Closed | Read only rules on Properties - This is a catch all defect for all instances where Read Only rules on properties are not correct. The desciption can be used as these are found | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-11 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 42 | ASPAC - SIT 2
246 | Closed | ASPAC – System not throwing error message, when mandatory fields are not entered/selected. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-11 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-13 | 2 | ASPAC - SIT 2
247 | Closed | ASPAC_ System does not detect the blank "Payment batch Date" mandatory field when "Pay cycle approved in PS" action is performed | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-03-11 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-26 | 15 | ASPAC - SIT 2
248 | Closed | ASPAC – Work Flow Status is not getting displayed in the Case Action drop down when trying to create a new PO. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 15 | ASPAC - SIT 2
249 | Closed | ASPAC Workflow: Citi Direct: System does not display the status of the linked PO file status, in Linked Payment tab of a CD file | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 5 | ASPAC - SIT 2
250 | Closed | ASPAC Workflow : Pop up dialog box is not displayed as expected. , when we try to perform "Send for Higher Approval" in Action tab . | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | bysiva | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 47 | ASPAC - SIT 2
251 | Closed | ASPAC_Workflow_T&E: T&E File Number field is not editable | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | ksseng | axplac | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 43 | ASPAC - SIT 2
252 | Closed | Similar to Defect 245, this is a catch all defect for all Read Only vs Read/Mandatory vs Optional | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | rxloga | rxloga | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 36 | ASPAC - SIT 2
253 | Closed | Citi Direct_ No search results are displayed, in link payment file search, when search is conducted with search criteria for "Status starts with" | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 5 | ASPAC - SIT 2
254 | Closed | ASPAC Workflow : File number is not getting displayed as expected , when New T & E expenses is created. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 43 | ASPAC - SIT 2
255 | Closed | ACEView_ASPAC_WorkFlow_CitiDirect : "Unexpected error.Please try again" warning message is displayed when "Close-Created in Error" action is performed. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | ksseng | axplac | 2015-03-12 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 5 | ASPAC - SIT 2
256 | Closed | Diary – Expired diary lists are not present in Global Diary. | Diary | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 31 | ASPAC - SIT 2
257 | Closed | Diary – Status in the Global Diary list is not displaying appropriately | Diary | Code | Code Error | 3 - Medium | 2 - High | bysiva | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 61 | ASPAC - SIT 2
258 | Closed | Manage Notes: By default, Type field is displayed as "Audit" in the grid view, when we update the existing note. | Notes | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 31 | ASPAC - SIT 2
259 | Closed | ASPAC Workflow_System throws an inappropiarte message when tried to save the cost allocation row data | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-27 | 14 | ASPAC - SIT 2
260 | Closed | T&E_ Status of the workitem is not getting updated from "New" to "Submitted" after performing "Sumbiited in PS" action on a New status T&E workitem | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | j9norb | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 31 | ASPAC - SIT 2
261 | Closed | Workbasket: Unable to perform Actions on a workitem from the workbasket. | Workbasket | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-13 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 4 | ASPAC - SIT 2
262 | Closed | FileNet annotation table: Field should be populated with Status Code rather than Status description | ACEView | Known Issue | Future Fixes | 2 - High | 2 - High | axplac | axplac | 2015-03-13 | Filenet | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 63 | ASPAC - SIT 2
263 | Closed | ASPAC – Country is not getting auto populated in the new PO, when performing clone functionality. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-14 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-17 | 3 | ASPAC - SIT 2
264 | Closed | ASPAC – File number is not generated, once we save a Cloned PO. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-14 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 55 | ASPAC - SIT 2
265 | Closed | ASPAC – when we perform “Clone” functionality, rest of the status (“Wait for Quote”, “Send Invoice for Coding”, “Close – Created in Error”) are not getting displayed in the existing PO. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | bysiva | bysiva | 2015-03-14 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 33 | ASPAC - SIT 2
266 | Closed | ASPAC - "Close - Created in Error" is not getting displayed when we click on Case Action drop down menu. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | axplac | 2015-03-16 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-26 | 10 | ASPAC - SIT 2
267 | Closed | ASPAC - File Level Security Groups Field is not present in the PO Work items, which is expected to be displayed | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | bysiva | szagar | 2015-03-16 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 36 | ASPAC - SIT 2
268 | Closed | Security – Reset functionality is not working as expected. | Security | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | bysiva | axplac | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-20 | 3 | ASPAC - SIT 2
269 | Closed | Security: Unable to perform any action, once we click on “Cancel” button. | Security | Code | Code Error | 2 - High | 2 - High | bysiva | jxkosh | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-20 | 3 | ASPAC - SIT 2
270 | Closed | ASPAC_Workflow_Pend_Action : The workitem disappears from the workbasket when "Pend" status is applied to a workitem. | Workflow Design | Design | Code Design | 2 - High | 2 - High | ksseng | ksseng | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-04-09 | 23 | ASPAC - SIT 2
271 | Closed | Security – “Clone” functionality is not working as expected for the new users. | Security | Code | Code Error | 2 - High | 2 - High | bysiva | ksseng | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-30 | 13 | ASPAC - SIT 2
272 | Closed | Security: LAND ID is not displayed as First column when a new user is searched. | Security | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | jxkosh | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-20 | 3 | ASPAC - SIT 2
273 | Closed | Security: A user is getting added automatically in Assigned Roles, while performing Assign work basket. | Security | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | jxkosh | 2015-03-17 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-20 | 3 | ASPAC - SIT 2
274 | Closed | Security: Mismatch between Use case and TDD document. | Security | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | rxloga | 2015-03-19 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 8 | ASPAC - SIT 2
275 | Closed | Security: BU and Department is not a 'Multi Select Choice List' field. | Security | Code | Code Error | 2 - High | 2 - High | rxloga | rxloga | 2015-03-19 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 8 | ASPAC - SIT 2
276 | Closed | Security: A New Role is saved successfully without enterign any values for 'Description' field. | Security | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-03-19 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 8 | ASPAC - SIT 2
277 | Closed | Security: While entering '*' value in Search field, it is converting into '%' field. | Security | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-03-19 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 8 | ASPAC - SIT 2
278 | Closed | Security: Unable to deactivate a user, even after sharing his personal workbasket. | Security | Wrongly Logged | Accepted as it is | 2 - High | 2 - High | rxloga | bysiva | 2015-03-19 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 8 | ASPAC - SIT 2
279 | Closed | Security – After editing the existing user details, when we click on ‘Save’ button system throwing an error. | Security | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-03-20 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-24 | 4 | ASPAC - SIT 2
280 | Closed | Security – Edit User button should be displayed as View/Edit button. | Security | Code | Code Error | 4 - Low | 4 - Low | sxtsat | sxtsat | 2015-03-20 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 7 | ASPAC - SIT 2
281 | Closed | ASPAC PeopleSoft Integration: POs are not available in Peoplesoft Application | ASPAC Peoplesoft Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | rxloga | hvpras | 2015-03-20 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-24 | 4 | ASPAC - SIT 2
282 | Closed | ASPAC PeopleSoft Integration: POs are not displayed in Peoplesoft application. | ASPAC Peoplesoft Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | rxloga | hvpras | 2015-03-20 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-24 | 4 | ASPAC - SIT 2
283 | Closed | The Data entered in the Function code on Aceview and shows up ACC/Exp year in PeopleSoft indicate data mapping may not be correct | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | axravi | axplac | 2015-03-20 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-03-25 | 5 | ASPAC - SIT 2
284 | Closed | MCC has predefined values in PeopleSoft and does not accept any random values coming from Ace view | ASPAC Peoplesoft Integration | Design | Accepted as it is | 2 - High | 2 - High | axravi | axplac | 2015-03-20 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 32 | ASPAC - SIT 2
285 | Closed | ASPAC Peoplesoft Integration: Miscellaneous charge amount entered in ACEView is not displayed in PeopleSoft application | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-03-23 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-04-21 | 29 | ASPAC - SIT 2
286 | Closed | ASPAC PeopleSoft Integration:System does not display the code values for the fields 'BU' and 'Alt Account' field and only displays the descrption in the user interface | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-03-23 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-27 | 4 | ASPAC - SIT 2
287 | Closed | PeopleSoft: Description displayed in the "Cost Allocation" tab is not displayed in PeopleSoft in "Invoice Information" tab | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-23 | PeopleSoft | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-03-25 | 2 | ASPAC - SIT 2
288 | Closed | PeopleSoft: Error message displayed for VAT Code "TSE Prompt table edit; value not found in prompt table" | ASPAC Peoplesoft Integration | Config-Data | App DB | 2 - High | 2 - High | axplac | axplac | 2015-03-23 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-04-17 | 25 | ASPAC - SIT 2
289 | Closed | ASPAC-Correspondents_ bold red font message that states "Vendor Locked to PeopleSoft" is not displayed after selecting a ‘vendor’ in PO Invoice tab | Correspondents | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-03-25 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 30 | ASPAC - SIT 2
290 | Closed | ASPAC-Correspondents_'Search results' are not gettinng cleared on clicking 'Reset' button in the vendor search screen | Correspondents | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-25 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 55 | ASPAC - SIT 2
292 | Closed | PO File type: Flags & Milestone - unable to perform flags and milestones in ACE View. | Flags and Milestones | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | sxtsat | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-02 | 7 | ASPAC - SIT 2
293 | Re-opened | Email : Document Package from Document list is not displayed as expected. | Email_ACEView Integration |  |  | 3 - Medium | 3 - Medium | stsure | kxbizi | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 63.7972 | ASPAC - SIT 2
294 | Closed | ASPAC-Correspondents_ Mismatch in the names of fields displayed in the correspondent tab and the fields mentioned in the configuration document | Correspondents | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 29 | ASPAC - SIT 2
295 | Open | ASPAC-Correspondent_ System does not display the warning message even if the maximum records returned is more than 1000 in the vendor search results | Correspondents |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 63.7972 | ASPAC - SIT 2
296 | Closed | ASPAC-Correspondents_ system does not display the appropriate message to the user when no search results have been found for the given search criteria | Correspondents | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 40 | ASPAC - SIT 2
297 | Open | ASPAC-Correspondents_ Reset option to rest the columns to default search template in not present in the options displayed ,when column header arrow is clicked in vendor search result screen | Correspondents |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 63.7972 | ASPAC - SIT 2
298 | Closed | ASPAC – Status is not displayed as “Invoice Awaiting Coding” in PO Invoice Coding work basket. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-01 | 6 | ASPAC - SIT 2
299 | Closed | ASPAC-flow_Wrong actions are displayed for a "New" status PO workitem | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 39 | ASPAC - SIT 2
300 | Closed | ASPAC – PS Voucher number is editable in “Posted in peoplesoft” status. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 27 | ASPAC - SIT 2
301 | Closed | ASPAC-Correspondents_System does not retain the column selection (hidden columns) in the vendor search screen when closed and opened after selection is done | Correspondents | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 14 | ASPAC - SIT 2
302 | Closed | ASPAC-Correspondent_ Mismatch between the configuration document and use case document about additional search parameters in the vendor search screen | Correspondents | Testing | Invalid Test Case | 3 - Medium | 3 - Medium | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 27 | ASPAC - SIT 2
303 | Closed | Indexing_ Document tree is not updated after performing indexing action | Workflow Design | Code | Code Error | 1 - Critical | 1 - Critical | axrath | axplac | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 18 | ASPAC - SIT 2
304 | Closed | Cognos to ACE View Integration URL Not working | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | srvxxx | srvxxx | 2015-03-26 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 8 | ASPAC - SIT 2
305 | Closed | ASPAC Workflow: System allows to edit the field values, after the payment is approved in PeopleSoft | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 26 | ASPAC - SIT 2
306 | Closed | ASPAC Workflow : Project Name\Co.. should be displayed as Project Name\Code in cost allocation tab. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-01 | 5 | ASPAC - SIT 2
307 | Re-opened | AceView: Vendor field details not displayed when clicked on 'Search' | ACEView |  |  | 3 - Medium | 2 - High | axplac | cxturl | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 62.7972 | ASPAC - SIT 2
308 | Closed | Security_Unable to retrieve the saved changes in the ““My Workbasket share” screen | Manage User Preference | Code | Code Error | 2 - High | 2 - High | axrath | sxsard | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 13 | ASPAC - SIT 2
309 | Closed | Security_"Cancel" button is missing in the "My workbasket share" screen | Manage User Preference | Code | Code Error | 2 - High | 2 - High | axrath | kxrsxx | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 7 | ASPAC - SIT 2
310 | Closed | ASPAC – Flags and milestones tab is not getting displayed. | Flags and Milestones | Code | Code Error | 1 - Critical | 2 - High | sxtsat | stsure | 2015-03-27 | ACEView | Build 1B - Cycle 1 | Release 1_ASPAC | 2015-04-14 | 18 | ASPAC - SIT 2
311 | Closed | Security_ In "My Workbasket share " screen "<<" functionality is not working | Manage User Preference | Code | Code Error | 3 - Medium | 3 - Medium | axrath | stsure | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 27 | ASPAC - SIT 2
312 | Closed | Security_System does not set the privilege as "Normal" when an user is added to assigned list in "My Workbasket Share" screen | Manage User Preference | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axrath | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 13 | ASPAC - SIT 2
313 | Closed | ASPAC Workflow_Unable to perform "Send Invoice for Checking" action on a "INVOICE AWAITING CODING" Status workitem | ASPAC Workflow | Code | Code Error | 2 - High | 3 - Medium | stsure | axplac | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 19 | ASPAC - SIT 2
314 | Closed | Security_Click away functionality is not working in Manage user preferences | Manage User Preference | Code | Code Error | 2 - High | 2 - High | axrath | sxsard | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 7 | ASPAC - SIT 2
315 | Closed | Manage User Preference: Values are not available in any of the fields in Work basket Email notifications screen | Manage User Preference | Testing | Not Reproducible | 2 - High | 2 - High | sxtsat | sxtsat | 2015-03-27 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-01 | 5 | ASPAC - SIT 2
316 | Closed | ASPAC – VAT Rate should be changed as “Optional” field in cost allocation tab. | ASPAC Workflow |  |  | 3 - Medium | 2 - High | sxtsat | axplac | 2015-03-30 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 50 | ASPAC - SIT 2
317 | Closed | ASPAC-Workflow: Mismatch in the dropdown Values of Payment Method Field displayed in the PO Invoice tab and the Values mentioned in the Choice List document. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 23 | ASPAC - SIT 2
318 | Closed | ASPAC-Workflow: Mismatch in the dropdown Values of Purchase Type Field displayed in the PO Invoice tab and the Values mentioned in the Choice List document. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 15 | ASPAC - SIT 2
319 | Closed | ASPAC-Workflow: "Null" values getting displayed in the dropdown values of the Alt Account field in the Cost Allocation tab. | ASPAC Workflow | Code | Code Error | 2 - High | 1 - Critical | stsure | kanixd | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 57 | ASPAC - SIT 2
320 | Closed | ASPAC – Quotation amount field is not reflecting as mandatory field in invoice awaiting coding status. | ASPAC Workflow |  |  | 2 - High | 2 - High | sxtsat | axplac | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 17 | ASPAC - SIT 2
321 | Closed | Flags & Milestones - A milestone is created in the ACE View application UI, it is not being stored in the File_Miestone table inthe App DB. | Flags and Milestones | Config-Data | App DB | 2 - High | 2 - High | sxtsat | axplac | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 22 | ASPAC - SIT 2
322 | Closed | AceView: Cost Allocation: Affiliate Code and Project Name/Code field drop down values should display Code + Description, but displays only the Description | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-03-31 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 3 | ASPAC - SIT 2
323 | Closed | Workflow Design: Dropdown values are getting populated for File Type , Folder Type and Document Type fields in Document tab. | Workflow Design | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-01 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 2 | ASPAC - SIT 2
324 | Closed | Open File and Open case : Tree nodes are not getting displayed in the Document Tree View of a Open File. | Open File and Open Case | Code | Code Error | 1 - Critical | 1 - Critical | stsure | axplac | 2015-04-01 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-08 | 7 | ASPAC - SIT 2
325 | Closed | Flags and Milestones : As per the CR044, Payment Approved by Email and Order Approved by Email Milestone should not be visible in Flags and Milestone Tab. | Flags and Milestones | Code | Code Error | 2 - High | 2 - High | swsure | axplac | 2015-04-01 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 14 | ASPAC - SIT 2
326 | Closed | query PS Dept and Operating Unit for Cost Alloc where Set_ID='GLOBE' | ASPAC Peoplesoft Integration | Config-Data | App DB | 2 - High | 2 - High | J9NORB | axplac | 2015-04-01 | ACEView | Build 1B - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 34 | ASPAC - SIT 2
327 | Closed | UI Validation : "Search" button is not displayed as expected. | ACEView | Code | Code Error | 4 - Low | 4 - Low | stsure | axsavi | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 20 | ASPAC - SIT 2
328 | Closed | Notes : Slide Out Filter Panel is not getting displayed as expected in "Notes\Audit Trails" tab. | Notes | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 36 | ASPAC - SIT 2
329 | Closed | Security_ACEView Integration: This is a master defect for early security related issues. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 32 | ASPAC - SIT 2
330 | Open | Barcode - Values are not populated while typing values in 'Code' drop down field | Barcode Generation |  |  | 3 - Medium | 3 - Medium | sxtsat | dzmais | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 56.7972 | ASPAC - SIT 2
331 | Closed | UI Validation - Log out button is not working in ACE View. | ACEView | Known Issue | Future Fixes | 2 - High | 2 - High | sxtsat | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-14 | 12 | ASPAC - SIT 2
332 | Closed | Flags and Milestones : As per the CR044, Receipt Attached Milestone should be changed to Flags in Flags and Milestone Tab. | Flags and Milestones | Wrongly Logged | Invalid Test Case | 2 - High | 3 - Medium | stsure | bybull | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 15 | ASPAC - SIT 2
334 | Closed | Security_ACEView Integration: Pagination value is not getting updated in manage role screen. | Security_ACEView Integration | Code | Code Error | 4 - Low | 4 - Low | sxtsat | sxtsat | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-08 | 6 | ASPAC - SIT 2
335 | Closed | ACEView: Irrelevant value is displayed for ‘Priority’ drop down field. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-03 | 1 | ASPAC - SIT 2
336 | Closed | Security_ACEView Integration: Naming convention is not displayed as 'ACEView' across the application | Security_ACEView Integration | Code | Code Error | 4 - Low | 4 - Low | rxloga | rxloga | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-08 | 6 | ASPAC - SIT 2
337 | Closed | ACEView: 'The case is already locked ...' error message is displayed even if the user has closed a File | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 13 | ASPAC - SIT 2
338 | Re-opened | ACEView: Sorting is not happening for any of the Field in ACEView homepage | ACEView |  |  | 3 - Medium | 2 - High | rxloga | j9norb | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 56.7972 | ASPAC - SIT 2
339 | Closed | Security_ACEView Integration: Search results are not getting displayed properly while searching with ‘Department’ field value. | Security_ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | sxtsat | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-08 | 6 | ASPAC - SIT 2
340 | Closed | Manage User Preference: When user preference of Notes and Diary is set to alert in Settings, but it’s not reflecting in any of the work items. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-02 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 15 | ASPAC - SIT 2
341 | Closed | ACEView: PO file is not available in 'PO Invoice Processing' workbasket after saving it. | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | rxloga | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 6 | ASPAC - SIT 2
342 | Closed | ACEView: 'Select All' icon is not working properly | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 34 | ASPAC - SIT 2
343 | Closed | ACEView: Irrelevant values are getting displayed for 'Department' field | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 12 | ASPAC - SIT 2
344 | Closed | Barcode Generation – Barcode is not getting generated in ACE View. | Barcode Generation | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 12 | ASPAC - SIT 2
346 | Closed | Security_ACEView Integration: When trying to Search with Blank values in all fields, system throws error message as 'Please enter either LANID or First Name or Last Name' | Security_ACEView Integration | Testing | Inconsistent | 4 - Low | 4 - Low | rxloga | rxloga | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-10 | 7 | ASPAC - SIT 2
347 | Closed | Search Template : Status of the workitem is not getting Displayed as "New" after performing PO Invoicing - Quick Search from Search template dropdown. | Search Template | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 34 | ASPAC - SIT 2
348 | Closed | ACEView: Datacap Scanned files are not available in respective Workbasket application | Scanning_ACEView Integration | Code | Code Error | 2 - High | 2 - High | rxloga | rxloga | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 12 | ASPAC - SIT 2
349 | Closed | ACEView: Irrelevant values are getting displayed for ‘Alt Account’ and ‘PeopleSoft Department’ field. | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | kanixd | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-29 | 26 | ASPAC - SIT 2
350 | Retest Dependency | ACEView - Barcode Generation: Not able to save the Barcode document into local desktop as Save button is in disable mode. | Barcode Generation |  |  | 3 - Medium | 3 - Medium | szagar | axdubo | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 55.7972 | ASPAC - SIT 2
351 | Closed | ASPAC Workflow - PO File number is not generated in the work item, after proceeding the status to ‘Invoice Awaiting Coding’. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 12 | ASPAC - SIT 2
352 | Closed | ASPAC Workflow– Vendor field is editable in 'Invoice Awaiting Coding' status of the work item in PO. | ASPAC Workflow | Code | Code Error | 2 - High | 3 - Medium | sxtsat | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 12 | ASPAC - SIT 2
353 | Closed | Send Email – Document is not getting attached in Email, while performing Send Email functionality in a work item. | Send Email | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 19 | ASPAC - SIT 2
354 | Closed | Open File and Open Case – In Document tab, system generates the value of security by default as “1”. | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 20 | ASPAC - SIT 2
355 | Closed | ACE View: System throws an inconsistent error message in the ACE View login page, after entering the valid credentials. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 33 | ASPAC - SIT 2
356 | New | Diary: After selecting ‘Diary’ value from the drop down and perform Tab action into ‘TIME’ field, the Time value box is aligned downwards compared to ‘Date’ field. | Diary |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-04-04 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 54.7972 | ASPAC - SIT 2
357 | Closed | Diary: After Editing a ‘Diary’, the record is not available in the File. | Diary | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-04 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-13 | 9 | ASPAC - SIT 2
358 | Closed | Diary: There is a delay in Reminder message when two Diary is created for same file at same Reminder time. | Diary | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-04 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 33 | ASPAC - SIT 2
359 | Closed | Diary: System allows the user to create a Duplicate record for Diary/Alert | Diary | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-04 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 33 | ASPAC - SIT 2
360 | Closed | Search Template : Unable to create "New File" via Search Template Page. | Search Template | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-03 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 25 | ASPAC - SIT 2
361 | Closed | Search Template : "Payment Due date in between" field is not displayed as expected in PO Invoice Quick search template. | Search Template | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 39 | ASPAC - SIT 2
362 | Closed | Search Template : "Code" is getting displayed instead of "Description" for Business Unit of the selected work item in PO Invoice Quick search template. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | stsure | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 30 | ASPAC - SIT 2
363 | Closed | Diary: Note type is not defaulted to 'Alert' when user adds a note from 'Document Notes' tab | Diary | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 11 | ASPAC - SIT 2
364 | New | Diary: When no value is entered in 'Message' text box, error message icon displayed is not visible in the Pop-up window | Diary |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
365 | Closed | Diary: Error message is not displayed if the user does not select Date and time in the 'Diary' record from 'Document' drop down | Diary | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 31 | ASPAC - SIT 2
366 | Closed | Diary: 'Visual indicator' is not displayed against the document when 'Diary' note is added | Diary | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 30 | ASPAC - SIT 2
367 | New | Diary: 'Expiry date & Time' label is displayed instead of 'Reminder Date & Time' for a 'Diary' note | Diary |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
368 | Re-opened | Search Template : No search results are displayed, in PO Invoice Quick search, when Wildcard search is performed. | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axravi | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
369 | New | ACEView: While clicking on 'Finance Accounts Payable' work basket, the Header tab is not displayed as 'Finance Accounts Payable' | ACEView |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
370 | Closed | Search Template : "Auto Posted to PS" dropdown values in PO Invoice Search is not displayed as expected. | Search Template |  |  | 4 - Low | 4 - Low | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 43 | ASPAC - SIT 2
371 | Closed | ACEView: Irrelevant Name is displayed under 'My Work' basket when logging into the application with valid User credentials | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 31 | ASPAC - SIT 2
372 | Closed | WorkBasket_Mega Filter: When selecting Multi select option for fields in Mega filter, the newly added row does not display the description of the field | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 39 | ASPAC - SIT 2
373 | Open | WorkBasket_Mega Filter: When value entered in 'Payment Batch Amount from' is greater than value in 'Payment Batch Amount to', system does not throw an error message | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | axdubo | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
374 | Open | WorkBasket_Mega Filter: When value entered in 'Payment Batch Date from' is greater than value in 'Payment Batch Date to', system does not throw any error message | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | axshme | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
375 | Closed | Selected User is not displayed in the Available list when the user is moved from Assigned List to Available list. | Manage User Preference | Testing | Inconsistent | 2 - High | 2 - High | szagar | szagar | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-10 | 4 | ASPAC - SIT 2
376 | Closed | Workbasket_Mega Filter: Pop-up message is not visible clearly in ACEView after saving Mega FIlter successfully | Workbasket | Design | Code Design | 4 - Low | 4 - Low | rxloga | axdubo | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 50 | ASPAC - SIT 2
377 | Re-opened | Workbasket_Mega Filter: Entering values for Mega filter and clicking on 'Apply to all workbasket' checkbox, the applied filter is not reflected in other work baskets. | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 52.7972 | ASPAC - SIT 2
378 | Closed | ACEView: Irrelevant values are getting displayed for 'Currency' field | ACEView | Requirement | New functionality | 2 - High | 2 - High | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-14 | 8 | ASPAC - SIT 2
379 | Closed | ASPAC Workflow : Wild card search is not avalaible for Searching Staff Name in T& E Expenese Tab in AceView | ASPAC Workflow | Wrongly Logged | Accepted as it is | 2 - High | 2 - High | stsure | stsure | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-14 | 8 | ASPAC - SIT 2
380 | Closed | Workbasket_Mega Filter: Selecting any Filter as 'Default filter' in one work basket and navigating to the next workbasket, the preivously defaulted filter is set to the new workbasket also | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 32 | ASPAC - SIT 2
381 | Closed | ASPAC-Workflow: Mismatch in the Field displayed in the T&E Expense tab and the Fields mentioned in the Config sheet (Wave_1_WorkflowConfiguration_ASPAC_Finance_TE_1.0) . | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 16 | ASPAC - SIT 2
382 | Closed | ASPAC-Workflow: Mismatch in the Field displayed in the T&E Expense tab and the Fields mentioned in the Config sheet (Wave_1_WorkflowConfiguration_ASPAC_Finance_TE_1.0) . | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 16 | ASPAC - SIT 2
383 | Closed | ASPAC Workflow: A new PO invoice is created even without entering the few mandatory fields such as Purchase Type & purchase Category. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 18 | ASPAC - SIT 2
384 | Closed | ASPAC-Workflow: Mismatch in the Field displayed in the T&E Expense tab and the Fields mentioned in the Config sheet (Wave_1_WorkflowConfiguration_ASPAC_Finance_TE_1.0) . | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 9 | ASPAC - SIT 2
385 | Closed | Open File & Open Case – System not prompting/warning with a message, when user close the work item without saving. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 11 | ASPAC - SIT 2
386 | Closed | Workbasket_Mega FIlter: Unable to save a filter with '35401 - ACE Insurance New Zealand' Business Unit | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 30 | ASPAC - SIT 2
387 | Closed | ASPAC Workflow :Staff Name is not showing the current user as the default value in T& E Expenses tab | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 17 | ASPAC - SIT 2
388 | Closed | Workbasket_Mega FIlter: Clicking on "reset' button in the mega filter section, the values entered in the fields are not reset | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-11 | 35 | ASPAC - SIT 2
389 | Closed | Notes :Audit Notes displays Status as "27" instead of "New" in the history of "Notes/audit trails" tab | Notes | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 16 | ASPAC - SIT 2
390 | Closed | On Pending a workitem the Comment option should be Mandatory in the Pend dialog box. | Workflow Design | Requirement | New functionality | 2 - High | 2 - High | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 15 | ASPAC - SIT 2
391 | Closed | By default Pend Time in the Pend Dialog box is displayed as 00:00:00 | Workflow Design | Code | Code Error | 3 - Medium | 2 - High | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 37 | ASPAC - SIT 2
392 | Closed | ACE View – While saving the work item by using the shortcut key (Alt+Shift+C), system displays the dialog box. | ACEView | Code | Code Error | 3 - Medium | 2 - High | sxtsat | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 28 | ASPAC - SIT 2
393 | Closed | ACE View – When a user is navigated to another work basket, right side reading pane(document properties) is still displaying the previous work item record. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 30 | ASPAC - SIT 2
394 | Closed | ACE View – System displays the mandatory symbol in Centre of the mandatory (BU) field. | ACEView | Testing | Tester Error | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 46 | ASPAC - SIT 2
395 | Closed | Workbasket_Mega Filter: There are duplicate values available in 'Status' drop down of Mega Filter section | Workbasket | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 32 | ASPAC - SIT 2
396 | Closed | Workbasket_Mega Filter: Results are not fetched correctly for the applied Search filter | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-11 | 35 | ASPAC - SIT 2
397 | Closed | Past Time and Date in Pend dialog box should not be accepted. | Workflow Design | Code | Code Error | 3 - Medium | 2 - High | rxloga | axplac | 2015-04-07 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-01 | 24 | ASPAC - SIT 2
398 | Closed | Workbasket_Mega Filter: System deletes the Saved filter even when user does not select any filter record to delete | Workbasket | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-07 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 29 | ASPAC - SIT 2
399 | Closed | There are few PO Files Whose Workbasket_ID is 0 | Workbasket | Requirement | New functionality | 2 - High | 2 - High | srvxxx | axplac | 2015-04-07 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 13 | ASPAC - SIT 2
400 | Closed | ACEView : Application is down , After Login to ACEView it displays "Initializing" in Home Page | ACEView | Environment | Environmental | 1 - Critical | 1 - Critical | stsure | axplac | 2015-04-06 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-08 | 2 | ASPAC - SIT 2
401 | Closed | ACEView: Unable to create a PO. 'Unexpected error. Please try again' error message is displayed | ACEView | Environment | Configurations | 1 - Critical | 1 - Critical | rxloga | kanixd | 2015-04-08 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 1 | ASPAC - SIT 2
402 | Closed | All the workitems are getting exported from the application to the Excel instead the selected workitems. | Search Template | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-08 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 30 | ASPAC - SIT 2
403 | Closed | ACEView_Home page: Navigation page icon is not working as expected | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-08 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 7 | ASPAC - SIT 2
404 | Closed | ACEView_Home page: System does not display the Records based on the 'No of item per page' value which is given in the pagination section | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-04-08 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 7 | ASPAC - SIT 2
405 | Closed | ASPAC Workflow : Dropdown Values are not displayed for "Security Policy" field. | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | stsure | axplac | 2015-04-08 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-09 | 1 | ASPAC - SIT 2
406 | New | Preview icon is not displayed as expected | Workbasket |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
407 | Closed | Priority of work item is changed to 50 | Workbasket | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 36 | ASPAC - SIT 2
408 | Closed | Workbasket_Bulk Action: 'Action' menu is enabled when records are selected with different statuses | ACEView | Design | Code Design | 2 - High | 2 - High | rxloga | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 12 | ASPAC - SIT 2
409 | Closed | In "Set default filter" popup, "None" value is not present | Workbasket | Product Limitation |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 41 | ASPAC - SIT 2
410 | Fixed | Workbasket_Bulk workflow: File number is not displayed in Error message when user performs Bulk action for Locked item | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | axdubo | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
411 | Fixed | "Filter applied icon" is active in the right bottom of workbasket pane even when no filter is applied | Workbasket |  |  | 4 - Low | 4 - Low | axrath | axdubo | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
412 | Closed | ACEView_Cost Allocation: 'Operating Unit' values are not displayed based on the Business Unit selected in Cost Allocation tab | ACEView | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-11 | 32 | ASPAC - SIT 2
413 | Closed | ACEView_Cost Allocation: Values displayed in 'Alt Account' is displaye wrongly when compared with ASPAC Choice list value | ACEView | Wrongly Logged | Duplicate | 2 - High | 2 - High | rxloga | cxturl | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 14 | ASPAC - SIT 2
414 | Closed | ASPAC workflow – System throws an “unexpected error” message, when trying to save the cost allocation details in the cost allocation tab. | ASPAC Peoplesoft Integration | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-12 | 33 | ASPAC - SIT 2
415 | Re-opened | The "Set default filter" is not retaining the default filter when moved to other work basket and returned | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
416 | Closed | Filter name is allowing special characters | Workbasket | Product Limitation |  | 4 - Low | 3 - Medium | axrath | bybull | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 36 | ASPAC - SIT 2
417 | Re-opened | Workbasket_Mega Filter: After saving a new filter and clicking on 'Set default filter' icon, already saved Filter records are not displayed in the Pop-up window | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | dzmais | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
418 | Closed | ASPAC workflow – Vendor not getting populated for “35660 - ACE India Rep Office” Business Unit | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 29 | ASPAC - SIT 2
419 | Open | Workbasket_Reassign: ‘Refresh’ icon present in the ‘User’ dropdown is not refreshing the ‘User’ value list | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | dzmais | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
420 | Closed | ACEView_Homepage: When user selects the File/record and navigates to the next page and comes back to the previous page, the selection is refreshed | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 29 | ASPAC - SIT 2
421 | Closed | Workbasket_Reassign: Error message is not displayed when reassigning a workbasket without selecting any User value. | Workbasket | Code | Code Error | 3 - Medium | 2 - High | rxloga | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 25 | ASPAC - SIT 2
422 | Closed | Open File and Open Case : During New PO creation, on resetting and refreshing the Vendor Look up screen, search result is displayed based on previous search. | Open File and Open Case | Testing | Inconsistent | 4 - Low | 4 - Low | szagar | kxbizi | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 48 | ASPAC - SIT 2
423 | Closed | Open File and Open case : Viewing the document by using right click and selecting view document option, an error message is displayed "Class NULL not found" . | Open File and Open Case | Code | Code Error | 3 - Medium | 2 - High | szagar | axdubo | 2015-04-09 | Daeja Viewer | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 49 | ASPAC - SIT 2
424 | Closed | Pend Reason field which is a mandatory field is not present in the Pend dialog box to Pend a workitem. | Workflow Design |  |  | 2 - High | 2 - High | rxloga | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 19 | ASPAC - SIT 2
425 | Closed | Incorrect assignment of status to File Types | ACEView | Code | Code Error | 2 - High | 2 - High | srvxxx | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 40 | ASPAC - SIT 2
426 | Closed | DOCVERSION Fact Filelds are having String and Integer Values | ACEView | Known Issue | Accepted as it is | 2 - High | 2 - High | srvxxx | srvxxx | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 6 | ASPAC - SIT 2
427 | Closed | Drag and Drop – Unable to import documents to ACE View in an existing work item via drag and drop. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 43 | ASPAC - SIT 2
428 | Closed | Diary – When postpone the reminder date of the diary with the past date, system displays improper error message. | Diary | Code | Code Error | 4 - Low | 4 - Low | sxtsat | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 43 | ASPAC - SIT 2
429 | Closed | ASPAC workflow – Mandatory symbol (asterisk) is not present in the mandatory fields, when creating a new T & E work item. | ASPAC Workflow | Testing | Invalid Test Case | 4 - Low | 4 - Low | sxtsat | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 34 | ASPAC - SIT 2
430 | Closed | Security_ACEView Integration: Multiple records of the same user is getting displayed in Available roles of My Work basket share screen. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 6 | ASPAC - SIT 2
431 | Closed | Security_ACEView Integration: My Workbasket Share is not updating the changes made by the user | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | rxloga | rxloga | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 6 | ASPAC - SIT 2
432 | Fixed | Filter icon is not being displayed beside work basket name | Workbasket |  |  | 3 - Medium | 2 - High | axrath | axdubo | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 49.7972 | ASPAC - SIT 2
433 | Closed | Number of Unread Work Items, Number High Priority Work Items, Number of Pended Work Items, Number of Locked Work Items is not displayed in the left bottom of the work basket. | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 8 | ASPAC - SIT 2
434 | Closed | Security_ACEView Integration: Unable to save the changes made in Assgin work basket for the user. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-09 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 6 | ASPAC - SIT 2
435 | Fixed | Bulk work action is not working as expected | Workflow Design |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
436 | Closed | Priority of the work item is not changed when priority is given with pend action | Workflow Design | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 28 | ASPAC - SIT 2
437 | Closed | pend icon not removed after expiring pend time and the item colour is not changed automatically | Workflow Design | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 24 | ASPAC - SIT 2
438 | Re-opened | Confirmation message is not being asked on clicking “Unpend" | Workflow Design |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
439 | Closed | No icon is added to the work item after Unpend action | Workflow Design | Requirement | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axrath | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 48 | ASPAC - SIT 2
440 | In Progress | Pend time in “Pend” action is not being saved as expected | Workflow Design |  |  | 3 - Medium | 2 - High | axrath | vxshme | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
441 | Closed | Open File and OPen Case : Error message is displayed "File does not a valid header row" when tried to upload the data in Cost Allocation using an excel sheet. | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | szagar | szagar | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 33 | ASPAC - SIT 2
442 | Closed | ASPACE Workflow – Lock symbol appears in PO work items, when the File is not opened in PO work baskets. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 26 | ASPAC - SIT 2
443 | Open | Open File and Open Case: Right click on any folder in Tree view displayed only Attach Case, Detach case, Refresh and paste option. Attach Correspondents and Detach correspondents option is not displayed. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
444 | Closed | ASPAC Workflow – Right side reading pane is editable for the work items. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 26 | ASPAC - SIT 2
445 | Closed | Open File and Open Case: Options Permanent Link – One Way Link, Permanent Link – Two Way Link are not displayed after clicking on Attach button to attach the selected file. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 7 | ASPAC - SIT 2
446 | Open | Open File and Open Case : After selecting Multiple files and clicking on Attach button, only the lastly selected file is displayed in the Linked folder of Tree view. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
447 | Open | Open File or Open Case : Related cases option is not displayed on Right clicking the file which is linked to two or more work items. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 48.7972 | ASPAC - SIT 2
448 | Closed | Security_ACEView Integration: System does not warn the user to save the changes made after cloning action is performed for a new user. | Security_ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | sxtsat | 2015-04-10 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-15 | 5 | ASPAC - SIT 2
449 | Closed | ASPAC Workflow – File number is generating incorrectly for BU – AIOIC Branch Thailand. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | kanixd | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 45 | ASPAC - SIT 2
450 | Closed | AceView: AceView screen Screen displayed is not showing the entire full screen | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 11 | ASPAC - SIT 2
451 | Closed | ASPAC Work Flow : Error message is not displayed by clicking on save button with value entered only for Business unit while creating a New T&E Expense. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 9 | ASPAC - SIT 2
452 | Closed | ASPAC Work flow : On selecting PO Invoice option from New File dropdown, error message is displayed "Unexpected Error.Please try again" when trying to create a PO file after indexing the Invoice in the Finance queue. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | szagar | szagar | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 24 | ASPAC - SIT 2
453 | Open | Diary – System allows the user to create diary without entering the mandatory fields, while adding a new diary record. | Diary |  |  | 3 - Medium | 3 - Medium | sxtsat | kxbizi | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 45.7972 | ASPAC - SIT 2
454 | Closed | ASPAC workflow - PO Invoice Approvals Workbasket is not getting refreshed after cliking the Refersh button. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-07 | 24 | ASPAC - SIT 2
455 | Open | UI Validation - Fields in Cost allocation tab is not displaying the record properly. | ACEView |  |  | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-13 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 45.7972 | ASPAC - SIT 2
456 | Put On Hold | ACE View: User Id is not getting displayed in User drop down in ACE View home screen. | ACEView |  |  | 3 - Medium | 3 - Medium | sxtsat | dzmais | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 44.7972 | ASPAC - SIT 2
457 | Closed | Security_ACEView Integration: System displays all the PO work baskets, when a user is assigned to only “PO invoicing processing work basket” in Manage Role. | Security_ACEView Integration | Wrongly Logged | Incorrect Test Data | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 7 | ASPAC - SIT 2
458 | New | Barcode Generation: System is not displaying the full description in drop down for “File, Folder & Document type” in barcode. | Barcode Generation |  |  | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 44.7972 | ASPAC - SIT 2
459 | New | ACE View: System displays double filter icons while performing “Filter” functionality in document panel of the work item. | ACEView |  |  | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 44.7972 | ASPAC - SIT 2
460 | Closed | ASPAC Workflow: A newly created work item is not getting displayed in any of the work baskets, when a work item created with the security policy field given as “None”. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 7 | ASPAC - SIT 2
461 | Closed | Send Email: Unable to perform Send Email functionality for a work item in Finance indexing work basket. | Send Email | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 8 | ASPAC - SIT 2
462 | Closed | ASPAC Workflow: Sort functionality is not enabled in any of the columns of Notes/Audit trial tab to perform sorting. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 38 | ASPAC - SIT 2
463 | Closed | ACE View: A newly created finance indexing work item is getting invisible (with the white color font) in finance indexing work basket, when documents are ingested through upload option. | Upload Document | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 6 | ASPAC - SIT 2
464 | Closed | ACE View: File count of “Total/Unread/Priority/Pended/Locked” for Finance indexing work basket is getting mismatched. | ACEView | Code | Code Error | 3 - Medium | 2 - High | sxtsat | stsure | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-12 | 28 | ASPAC - SIT 2
465 | Closed | Send Fax: Unable to perform Send Fax functionality for a work item in Finance indexing work basket. | Send Fax | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 10 | ASPAC - SIT 2
466 | Closed | Send Fax: System is not performing Send Fax functionality properly in PO invoicing work basket. | Send Fax | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 10 | ASPAC - SIT 2
467 | Open | ACE View: Show Hidden icon in document panel is not working as expected. | ACEView |  |  | 3 - Medium | 4 - Low | sxtsat | kxbizi | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 44.7972 | ASPAC - SIT 2
468 | Put On Hold | ACE View: ACE View system requires frequent cache clearance for the functionalities to reflect in the system. | ACEView |  |  | 3 - Medium | 3 - Medium | sxtsat | j9norb | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 44.7972 | ASPAC - SIT 2
469 | Closed | Security Policy on the Create forms for PO, T&E and CD should be re-labelled File Level Security Groups AND should require mandatory entry ie either Finance Restricted or None from the Choice List | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-04-14 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 3 | ASPAC - SIT 2
470 | Closed | Correspondents : Vendor Correspondence Name and Address not getting populated correctly in Correspondent tab. | Correspondents | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 23 | ASPAC - SIT 2
471 | Closed | ASPAC Workflow – System throws an error message, after uploading the data sheet in cost allocation tab. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-01 | 16 | ASPAC - SIT 2
472 | Closed | ACE View : User LAN ID is not displayed in User dropdown after logging into ACE View. | ACEView | Wrongly Logged | Duplicate | 3 - Medium | 3 - Medium | szagar | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-01 | 16 | ASPAC - SIT 2
473 | Closed | ASPAC Workflow – A newly created work item (POAU100061) which is proceeded to “invoice awaiting coding” status is not getting displayed in any of the work baskets. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | bysiva | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-04 | 19 | ASPAC - SIT 2
474 | Closed | Security_ACEView Integration: Personal settings and System Administration drop down is not working as expected in IE 11. | Security_ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | sxtsat | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 9 | ASPAC - SIT 2
475 | Closed | Open File and Open Case: System is not allowing to link different files via tree view by right clicking Attach File option. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 5 | ASPAC - SIT 2
476 | Open | Open File and Open Case: System is not displaying a visual indicator when a Priority is changed/Set for a work item. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 43.7972 | ASPAC - SIT 2
477 | Closed | System displays more than one work item with same File Number while searching | ACEView | Config-Data | App DB | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 28 | ASPAC - SIT 2
478 | Closed | System is not displaying the Vendor Short name column details in Vendor Search screen when creating PO. | ACEView | Code | Code Error | 2 - High | 2 - High | axrath | cxturl | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 9 | ASPAC - SIT 2
479 | Closed | <DaejaViewer_ACEView_Integration> : Annotations toolbar is enabled for attachments present in the email. | Daeja_Viewer ACEView Integration | Code | Code Error | 2 - High | 2 - High | ksseng | ksseng | 2015-04-15 | Daeja Viewer | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-29 | 14 | ASPAC - SIT 2
480 | Closed | Security_ACEView Integration: System displays PO Invoice Checking workbasket, when a user is assigned to only “PO invoicing processing work basket” in Manage Role. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | stsure | bysiva | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 9 | ASPAC - SIT 2
481 | Closed | <DaejaViewer_ACEView_Integration> : PDF documents are not getting auto launched in it's native format. | Environment | Environment | Environmental | 2 - High | 2 - High | ksseng | ksseng | 2015-04-15 | Daeja Viewer | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 1 | ASPAC - SIT 2
482 | Closed | Security_ACE View Integration : System displays PO Invoice Coding workbasket, when a user is assigned the role of "Purchase Order Approval" in Manage Role screen. | Security_ACEView Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | szagar | bysiva | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 9 | ASPAC - SIT 2
483 | Closed | Prompt message is not asked while drag and drop a document from one queue to another/within workitem. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 2 | ASPAC - SIT 2
484 | Closed | <DaejaViewer_ACEView_Integration> : "The process cannot access the file because it is being used by the another process" message is getting displayed randomly while loading some documents in Daeja Viewer. | Environment | Environment | Environmental | 3 - Medium | 3 - Medium | ksseng | ksseng | 2015-04-15 | Daeja Viewer | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 1 | ASPAC - SIT 2
485 | Closed | Manage Notes: System Notes are getting generated twice in Notes/Audit Trial tab when user performs an action on a work item | Notes | Code | Code Error | 3 - Medium | 3 - Medium | stsure | stsure | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 8 | ASPAC - SIT 2
486 | Closed | Focus not moving to another tab when drag and drop from one open work item to another open work item | Drag and Drop | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 37 | ASPAC - SIT 2
487 | Closed | Prompt message is not displayed when dragging documents within the work item | Drag and Drop | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 2 | ASPAC - SIT 2
488 | Closed | Security_ACEView Integration: By default, "Active/InActive" value should be displayed in User status field. | Security_ACEView Integration | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 8 | ASPAC - SIT 2
489 | Closed | Package ID and IsParent fields are not present in the document tab in work item viewer | Drag and Drop | Config-Data | App DB | 3 - Medium | 3 - Medium | axrath | stsure | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-30 | 15 | ASPAC - SIT 2
490 | Put On Hold | The application is not behaving as expected after keeping it inactive for long time | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-04-15 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 43.7972 | ASPAC - SIT 2
491 | Closed | MQ(Message Queue) Failed | ACEView | Code | Code Error | 2 - High | 2 - High | axplac | aykhan | 2015-04-15 | PeopleSoft | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 1 | ASPAC - SIT 2
492 | Closed | ACEView : System displays "Loading Icon" continuously in Home page and also when we Navigate from one tab to another. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 7 | ASPAC - SIT 2
493 | Closed | Security_ACEView Integration: Mismatch in “Security Policies” values displayed in ACEView Application and the values displayed in Use Case. | Security_ACEView Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | stsure | axravi | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 5 | ASPAC - SIT 2
494 | Re-opened | Security_ACE View Integration: Work basket Email notification in Settings icon is not working as expected for personal work basket. | Security_ACEView Integration |  |  | 2 - High | 2 - High | sxtsat | axdubo | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 42.7972 | ASPAC - SIT 2
495 | Closed | Security_ACEView Integration: System displays User Administration and System Administration tab, when a user is assigned to only "Purchase Order Processor" in Assigned Roles. | Security_ACEView Integration | Design | Infrastructure Design | 2 - High | 2 - High | stsure | stsure | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-16 | 0 | ASPAC - SIT 2
496 | Closed | ASPAC Workflow : On an Indexing Work Item, Transaction Type values is not displayed based on Transaction File Type selected. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 33 | ASPAC - SIT 2
497 | Closed | Security_ACEView Integration: System displays PO Invoice Approvals workbasket, when a user is assigned the role of "PO Invoice Checking" in Manage Role screen. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | axrath | bysiva | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 8 | ASPAC - SIT 2
498 | Closed | Security_ACE View Integration: System allows the user to perform actions in the assigned work baskets without assigning any roles. | Security_ACEView Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | sxtsat | bysiva | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 7 | ASPAC - SIT 2
499 | Closed | Unable to view documents by directly entering document URL in browser | Open File and Open Case | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 36 | ASPAC - SIT 2
501 | Re-opened | "Payment Approved by Email" & "Order Approved by Email" milestone is not getting highlighted automatically in any of the completed status in PO invoice File. | Flags and Milestones |  |  | 2 - High | 2 - High | rxloga | axdubo | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 42.7972 | ASPAC - SIT 2
502 | New | ASPAC Workflow: In Open status work item of Citi Direct Payment, Comment text field is in “Read Only”. | ASPAC Workflow |  |  | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-16 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 42.7972 | ASPAC - SIT 2
503 | Closed | Security_ACE View Integration: A user is able to perform actions for Citi Direct and proceed to next status with “PO invoice approver” role, when a user assigned only to “PO invoice approval” and “Citi Direct processing” work baskets in Manage role. | Security_ACEView Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | sxtsat | bysiva | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 6 | ASPAC - SIT 2
504 | New | ACE View: Tool tip is not working as expected, while placing the cursor on the status of the work item in ACE View. | ACEView |  |  | 4 - Low | 4 - Low | sxtsat | axsavi | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 41.7972 | ASPAC - SIT 2
506 | Closed | ACE View: System is not displaying the screen properly, when maximizes the screen. | ACEView | Code | Code Error | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 39 | ASPAC - SIT 2
507 | Closed | Security_ACEView Integration: When a User creates a Role type in manage Role screen, it is not getting displayed in Available Roles of User association details page. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | jxkosh | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 3 | ASPAC - SIT 2
508 | Closed | Manage User Preference : Clone button is in disable mode in User Search screen. | Manage User Preference | Testing | Duplicate | 3 - Medium | 3 - Medium | szagar | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-17 | 0 | ASPAC - SIT 2
509 | Closed | ASPAC Workflow: Error on page is getting displayed, When the user creates a new work item and proceeds to next status (Invoice awaiting coding). | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-20 | 3 | ASPAC - SIT 2
510 | Closed | Manage User Preference : In User Preference screen, changed values are getting saved while navigating to other screen and clicking on OK button of the warning pop up displayed. | Manage User Preference | Testing | Invalid Test Case | 2 - High | 2 - High | szagar | szagar | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 5 | ASPAC - SIT 2
511 | Closed | PeopleSoft: Vendor name is not getting displayed in PeopleSoft after posting a PO to PeopleSoft. | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 5 | ASPAC - SIT 2
512 | Deferred | Unable to view files or work items from "inactive tab" icon left to the open workitems tab | Open File and Open Case | Product Limitation | Future Fixes | 3 - Medium | 2 - High | axrath | axravi | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 41.7972 | ASPAC - SIT 2
513 | Closed | Document Generation: System is displaying a column name wrongly as "Qty" instead of "Quantity" in the PO Document Tab table details. | Document Generation | Testing | Duplicate | 4 - Low | 4 - Low | akpand | dzmais | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 35 | ASPAC - SIT 2
515 | Closed | No operation is performed on clicking the 'Use Last File' button in the document tab. | Workflow Design | Code | Code Error | 3 - Medium | 2 - High | gxfati | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 26 | ASPAC - SIT 2
516 | Closed | Create New File pop up dialog box is not prompted on clicking 'New File' button in the document tab. | Workflow Design | Code | Code Error | 2 - High | 2 - High | gxfati | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-27 | 10 | ASPAC - SIT 2
517 | Closed | Security_ACE View Integration: User is able to perform actions(editing) in finance indexing work basket, when a user is assigned to a role “Read Only” and Workbasket “Finance indexing” in Manage Role. | Security_ACEView Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | sxtsat | bysiva | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 6 | ASPAC - SIT 2
518 | Closed | DataCap Scanning: Unable to find the Work Item properties in the front end after work item created using datacap scanning | Datacap Scanning | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 5 | ASPAC - SIT 2
519 | Closed | DataCap Scanning_Audit notes is not getting logged correctly for work item created using datacap scanning | Datacap Scanning | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axrath | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 21 | ASPAC - SIT 2
520 | Closed | Scannig_ACEViewIntegration: The Work item in 'FInance Indexing Queue' is greyed out automatically | Scanning_ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axrath | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 21 | ASPAC - SIT 2
521 | Closed | Workbasket: Error message is being displayed when "Close-created in error" action is performed | Scanning_ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-17 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 35 | ASPAC - SIT 2
522 | Closed | Manage User Preference : Columns are getting displayed upon logout and login again after unchecking the checkboxes. | Manage User Preference | Code | Code Error | 3 - Medium | 3 - Medium | szagar | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 25 | ASPAC - SIT 2
523 | Closed | Manage User Preference : Resized Column changes are not displayed when the User access ACE View system, even after log out and log in. | Manage User Preference | Testing | Duplicate | 4 - Low | 4 - Low | szagar | szagar | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 32 | ASPAC - SIT 2
524 | Closed | ASPAC Peoplesoft Integration : Voucher No is not getting generated for a successfully Posted transaction in PeopleSoft | ASPAC Peoplesoft Integration | Environment | Accepted as it is | 2 - High | 2 - High | stsure | axplac | 2015-04-20 | PeopleSoft | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 2 | ASPAC - SIT 2
525 | Closed | Manage User Preference: For Drag and Drop, Drop Zone Confirmation Prompt drop down is not working as expected on selecting value as NO in User Preference screen. | Manage User Preference | Code | Code Error | 3 - Medium | 2 - High | szagar | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 32 | ASPAC - SIT 2
526 | Closed | ASPAC Peoplesoft Integration : Mismatch in Payment Method value displayed for a successfully posted transaction in Peoplesoft. | ASPAC Peoplesoft Integration | Config-Data | MDS | 2 - High | 2 - High | stsure | bybull | 2015-04-20 | PeopleSoft | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-01 | 11 | ASPAC - SIT 2
527 | Closed | Manage User Preference: For Drag and Drop, Prompt user for Email Import drop down is not working as expected on selecting value as No, Do Not Prompt for Email Import in User Preference screen | Manage User Preference | Code | Code Error | 3 - Medium | 2 - High | szagar | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 32 | ASPAC - SIT 2
528 | Closed | ASPAC PeopleSoft Integration : Mismatch in Payment Due Date between (ACEView & PS) for a successfully posted transaction in PeopleSoft. | ASPAC Peoplesoft Integration | Known Issue | Accepted as it is | 2 - High | 2 - High | stsure | axplac | 2015-04-20 | PeopleSoft | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 3 | ASPAC - SIT 2
529 | Closed | Manage User Preference: Send Email, Auto Save Sent Email drop down is not working as expected on selecting Always Add Email option in User Preference screen. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 18 | ASPAC - SIT 2
530 | Closed | ACEview : Horizontal Scroll Bar not available in the Notes/Audit Trail Tab in the Read only View ( Right Pane) | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 37 | ASPAC - SIT 2
531 | Closed | Security_ACEView Integration : System displays PO Invoice Processing workbasket, when a user is assigned a role of "PO Invoice Coding" in Manage Role screen of Settings icon. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | akpand | bysiva | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 4 | ASPAC - SIT 2
532 | Closed | Manage User Preference : System does not warn the user to save the changes made when user clicks on any other menu option without saving the changes made in User Preference settings. | Manage User Preference | Design | Infrastructure Design | 2 - High | 2 - High | stsure | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-21 | 1 | ASPAC - SIT 2
533 | Closed | Manage User Preference : System does not display any changes when we set the "Search Screen Layout" field value as "Horizontal" in User Preference tab. | Manage User Preference | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 30 | ASPAC - SIT 2
534 | Closed | Security_ACEView Integration : System displays "Work Basket: Number of recently Accessed work items to Display" as a data entry field instead of choice list. | Security_ACEView Integration | Testing | Invalid Test Case | 3 - Medium | 3 - Medium | akpand | axplac | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 2 | ASPAC - SIT 2
535 | Closed | Manage User Preference : For Drag and Drop, Methods to store Emails+ Attachemnts drop down default value is not displayed as expected for a New User in User Preference screen. | Manage User Preference | Testing | Incorrect Test Data | 2 - High | 2 - High | szagar | szagar | 2015-04-20 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-23 | 3 | ASPAC - SIT 2
536 | Open | Manage User Preference : In General settings, Default Calendar type drop down is not working as expected. | Manage User Preference |  |  | 3 - Medium | 3 - Medium | szagar | axdubo | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 37.7972 | ASPAC - SIT 2
537 | Closed | ACE View - Windows security warning message is getting displayed when trying to save a new PO invoice file. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 15 | ASPAC - SIT 2
538 | Closed | ASPAC workflow – System is not displaying all the mandatory fields in error message, when user clicks on “Send for Checking” from Action drop down in ACE View. | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | sxtsat | stsure | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-12 | 21 | ASPAC - SIT 2
539 | Closed | Manage User Preference : System is not displaying any error message/pop-up when any number greater than 99 is entered in the Workbasket field. | Manage User Preference |  |  | 3 - Medium | 3 - Medium | akpand | akpand | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-22 | 1 | ASPAC - SIT 2
540 | Closed | Manage User Preference : Work basket share functionality is not working as expected. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 17 | ASPAC - SIT 2
541 | Closed | ASPAC workflow: In Send for Higher Approval dialog box only limited QA users those who set for OA limits is displayed in the Approver dropdown list box. | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | gxfati | bysiva | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-08 | 17 | ASPAC - SIT 2
546 | Closed | AceView: UI fields not displayed as Expected in PO Invoice | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | axplac | axplac | 2015-04-21 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 36 | ASPAC - SIT 2
547 | Closed | ASPAC Work Flow : While creating a New T&E Expense, giving any random value for File Number field is accepted and no error message is displayed. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | szagar | axdubo | 2015-04-22 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 34 | ASPAC - SIT 2
548 | Closed | Send Email: System displays some combination of characters/special characters in BCC filed while performing Send Email action for a document of a work item in Finance indexing workbasket. | Send Email | Code | Code Error | 2 - High | 2 - High | akpand | sxtsat | 2015-04-22 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-12 | 20 | ASPAC - SIT 2
549 | Closed | ASPAC Workflow: T&E : The system should not allow a new T&E file to be saved with the file number which was already saved for a T&E file number. | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | axplac | 2015-04-22 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 6 | ASPAC - SIT 2
550 | Closed | ASPAC Work Flow : No error message is displayed while re-assigning a work item from PO Invoice Processing work basket without selecting the user. | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | szagar | j9norb | 2015-04-22 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-06 | 14 | ASPAC - SIT 2
551 | Closed | ASPAC Work flow : While Re-assigning a work item to another user, work item is not available in both Primary and Secondary work basket. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-22 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 13 | ASPAC - SIT 2
552 | Deferred | ACE View: System displays the deaja viewer after naviagating to settings screen in IE 11. | ACEView | Product Limitation | Future Fixes | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 35.7972 | ASPAC - SIT 2
553 | Closed | Open File and Open Case:Attached files are not shown in TreeView | Open File and Open Case | Requirement | Business Requirements Incorrect | 2 - High | 2 - High | axrath | j9norb | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-29 | 6 | ASPAC - SIT 2
555 | Open | Workbasket : ”Clone” does not prompt confirmation message | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 35.7972 | ASPAC - SIT 2
556 | Open | 'Payment Approved by email' & 'Order Approved by email' milestones are not getting highlighted even after Approval document is Indexed. | Flags and Milestones |  |  | 2 - High | 2 - High | gxfati | axsavi | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 35.7972 | ASPAC - SIT 2
557 | Closed | ASPAC workflow: On clicking Linked Payments button in the Link Payments dialog box, workitems are not getting linked to CitiDirect File in the Linked Payment Tab. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | gxfati | axplac | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-05 | 12 | ASPAC - SIT 2
558 | Closed | Datacap Scanning : The system generates a new workitem and attaches the document to it when a "Document Seperator" barcode is placed between two documents while scanning | Datacap Scanning | Testing | Not Reproducible | 2 - High | 2 - High | axrath | axplac | 2015-04-23 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-24 | 1 | ASPAC - SIT 2
559 | Closed | BizTalk responded to “failure to connect with FTP server exception” is just fine. But Biztalk should not send the VoucherNumber in it’s ack xml | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-04-23 | PeopleSoft | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-04-28 | 5 | ASPAC - SIT 2
560 | New | ASPAC Workflow – While creating a new PO, requestor field name is not displayed in the error message when user leaves the requestor field “blank”. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | sxtsat | bybull | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
561 | Closed | ASPAC Workflow – Vendor short name is not displayed in ACE View as same as in the PeopleSoft. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | kanixd | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-28 | 34 | ASPAC - SIT 2
562 | Re-opened | Drag and Drop – Security policy field value is getting displayed as “1” in document properties, once the work item is created by drag and drop a document. | Drag and Drop |  |  | 4 - Low | 4 - Low | sxtsat | sxtsat | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
563 | Closed | Send Fax: System displays some combination of characters/special characters in BCC filed while performing Send Email action for a document of a work item in Finance indexing workbasket & PO Work basket. | Send Fax | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 10 | ASPAC - SIT 2
564 | Closed | Barcode Generation – When user clicks on "Generate Barcode", system throws an error message. | Barcode Generation | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | axplac | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-28 | 4 | ASPAC - SIT 2
565 | Closed | ASPAC Work Flow : While creating a T&E file manually, no error message is displayed on entering the New file number same as existing. | ASPAC Workflow | Testing | Duplicate | 2 - High | 2 - High | szagar | axplac | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-27 | 3 | ASPAC - SIT 2
566 | Closed | ASPAC Workflow : Approver dropdown list box is not displayed in Send for Higher Approval dialog box , when user Perform action via Workbasket “Action” button . | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 19 | ASPAC - SIT 2
567 | Open | ASPAC Workflow : Mandatory field validation are not working as expected when we perform action via workbasket "Action" button. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | stsure | dzmais | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
568 | Closed | ASPAC Workflow_ System is not displaying the proper list of Higer Approvals in the drop-down during Currency Conversion based on OA limit. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | akpand | axplac | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 10 | ASPAC - SIT 2
569 | Open | Workbasket_MegaFilter: System allows the user to save the filter even for all the workbaskets under the 'PO Invoice' workbasket. | Workbasket |  |  | 3 - Medium | 3 - Medium | gxfati | axdubo | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
570 | New | ASPAC Workflow: In Open status work item of Citi Direct Payment, Comment text field is not getting displayed | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | stsure | axdubo | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
571 | Closed | ASPAC workflow: After a new PO is created, payment method is getting saved as “CHK” by default. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-07 | 13 | ASPAC - SIT 2
572 | Closed | ASPAC Workflow : File Number is getting duplicated twice in Citi Direct Payment. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | bysiva | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-28 | 4 | ASPAC - SIT 2
573 | Closed | ASPAC Workflow: User is able to edit the "File Number" field after opening a work item. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 11 | ASPAC - SIT 2
574 | New | ASPAC workflow – Mandatory symbol (asterisk) is not present in the Requestor field (mandatory field), when creating a new PO work item. | ASPAC Workflow |  |  | 4 - Low | 4 - Low | sxtsat | bybull | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
575 | Closed | Workbasket:Actions menu dropdown list in workbasket is displaying Actions twice. | Workbasket | Code | Code Error | 4 - Low | 4 - Low | axrath | axplac | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 24 | ASPAC - SIT 2
576 | Closed | Workbasket : When multiple locked items are selected and clicked on "Pend" action from "Actions" dropdown list, error message is displayed only for one workitem | Workbasket | Testing | Duplicate | 4 - Low | 4 - Low | axrath | axsavi | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 18 | ASPAC - SIT 2
577 | Closed | Workbasket Megafilter : Applying a filter in a workbasket and clicking on other workbasket,the Megafilter is not resetted.. | Workbasket | Code | Code Error | 4 - Low | 4 - Low | axrath | bysiva | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-12 | 17 | ASPAC - SIT 2
578 | Closed | Open File and Open Case: System does not allow user to type values in fields properly | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-27 | 32 | ASPAC - SIT 2
579 | Closed | ASPAC Workflow: Error message is not displayed when clicked on OK without entering the comments fields in the "Approve Order" popup. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-20 | 25 | ASPAC - SIT 2
580 | Closed | ASPAC Workflow: The field name is not displayed in the "Approve Order popup" | ASPAC Workflow | Requirement | New functionality | 4 - Low | 4 - Low | axrath | axravi | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 18 | ASPAC - SIT 2
581 | Closed | System displays error message when 10 to 15 workitems are opened. | ACEView | Testing | Not Reproducible | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 9 | ASPAC - SIT 2
582 | Closed | ASPAC Workflow: Proper error message is not displayed when multiple T&E files are selected and clicked on "Submitted in PS" | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 24 | ASPAC - SIT 2
583 | New | Open File and Open Case: Hide button is enabled for already hidden documents | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 33.7972 | ASPAC - SIT 2
584 | New | Open File and Open Case: The document filter field "Ingestion Type" has duplicate values | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 33.7972 | ASPAC - SIT 2
585 | Closed | Open File and Open Case: Document filter is not displaying valid results | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-25 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 9 | ASPAC - SIT 2
586 | Open | Diary : System displays error messsage when valid reminder time is given for the first time. | Diary |  |  | 3 - Medium | 3 - Medium | akpand | axdubo | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 31.7972 | ASPAC - SIT 2
587 | Closed | Manage User Preference: System is not updating the changes in ACE View after navigating from Personal settings screen or refreshing the page, when a user does any changes in personal settings. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-30 | 3 | ASPAC - SIT 2
588 | Closed | Manage User Preference: System is not prompting any message in ACE View while performing Send Email functionality, When a user select “Prompt for User Action” of Send Email drop down in User preference. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 11 | ASPAC - SIT 2
589 | Fixed | User cannot able to view multiple documents in the Daeja viewer. | ACEView |  |  | 2 - High | 2 - High | gxfati | axdubo | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 34.7972 | ASPAC - SIT 2
592 | Closed | Security_ACE View Integration: User is able to perform actions(editing) in finance indexing work basket, when a user is assigned to a role “Read Only”. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 25 | ASPAC - SIT 2
593 | New | UI Validation : Case Action Dropdown values are not dislayed properly in Citi Direct Payment workbasket. | ACEView |  |  | 4 - Low | 4 - Low | stsure | dzmais | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 31.7972 | ASPAC - SIT 2
594 | Closed | Query - ASPAC Correspondent : Reset funcationality is not clearing the right side panel details, when we click reset button i n Vendor search Page. | Correspondents | Code | Code Error | 3 - Medium | 3 - Medium | stsure | sxtsat | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-26 | 29 | ASPAC - SIT 2
596 | In Progress | Barcode Generation : Invalid values are getting displayed in "Code" dropdown in Barcode geneartion page. | Barcode Generation |  |  | 3 - Medium | 3 - Medium | stsure | cxturl | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 31.7972 | ASPAC - SIT 2
597 | Closed | Drag and Drop : While creating Finance Indexing work item using Drag and Drop, no prompt is displayed by the system to user to select the followings: Create Single Work item, Create Multiple Work Item and Cancel. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 22 | ASPAC - SIT 2
598 | Open | Alerts and Notifications : No notification is displayed by the system when an alert is set by the user. | Alerts & Notification |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 31.7972 | ASPAC - SIT 2
599 | New | Security_ACE View Integration: Pagination is not working properly as expected, when a user is logged in ACE View and assigned only with PO invoice processing work basket. | Security_ACEView Integration |  |  | 4 - Low | 4 - Low | sxtsat | yxkhom | 2015-04-27 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 31.7972 | ASPAC - SIT 2
601 | Open | ASPAC Workflow : The error message is not same when selected "Approve Order" from workbasket "Actions" Vs "Case Actions" after opening the workitem | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
602 | Closed | Open File and Open Case: The "Two way Link" in "Attach File" is not creating link in the "Linked Files" folder in the tree view of linked file. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 6 | ASPAC - SIT 2
603 | New | Open File and Open Case: The "Link Document" icon is displayed as search icon | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
605 | New | Open File and Open Case: The system allows to attach a workitem that has already been attached | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
606 | Open | Open File and Open Case: "View Related Files" option is not avialable in the application | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
607 | Closed | <DaejaViewer_ACEView_Integration> : The highlight made to a text present in a .doc and .ppt attachments are not present in the same position when the attachment is retrieved post saving it. | Daeja_Viewer ACEView Integration | Code | Code Error | 3 - Medium | 3 - Medium | ksseng | akpand | 2015-04-28 | Daeja Viewer | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 10 | ASPAC - SIT 2
608 | Open | Diary:Mandatory field description is not prompted in the remainder date & time field when clicking on that field and leaving the field empty. | Diary |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
610 | Closed | Search Template: Duplicate files are getting displayed while performing search using File number. | Search Template | Known Issue | Future Fixes | 2 - High | 2 - High | szagar | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-29 | 1 | ASPAC - SIT 2
611 | Open | No message display for Empty search results. | Search Template |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
612 | Open | Open File Open Case : System not displaying the correct value in the Ingestion Type column when the documents in work item is exported to the local drive in a CSV format. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | akpand | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
613 | New | Attach Case : User not able to attach a file from the list of work items displayed using search criteria. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | akpand | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
614 | Deferred | Search Template : "System Search" and "My Search" tab is not getting displayed in Search Page of the Query Slider. | Search Template | Product Limitation | Accepted as it is | 3 - Medium | 2 - High | stsure | axravi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
615 | Closed | Search Template : Mismatch in the Auto Post in PS field values displayed in ACEView PO Invoice Search template and value displayed in Config sheet. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 21 | ASPAC - SIT 2
616 | Open | There is no checkbox option for selecting multiple files in the Query Dialog box while performing Attach Case. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
617 | Closed | Search results varying for case sensitive "Contains search criteria". | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 24 | ASPAC - SIT 2
618 | Closed | Search Template : Instead of T & E Expenses Search it is getting displayed as " T&E Expensess Search" in search template dropdown. | Search Template | Code | Code Error | 4 - Low | 4 - Low | stsure | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 7 | ASPAC - SIT 2
619 | New | Mega Filter: Creating a new Filter with the existing filter name is not overwriting the previous filter criteria. | Workbasket |  |  | 3 - Medium | 3 - Medium | akpand | axdubo | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
620 | Closed | Search Template : CitiDirect Payment - Not selected as search template by default. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 21 | ASPAC - SIT 2
621 | Closed | Search Template : Data Export menu is not displayed as expected. | Search Template | Code | Code Error | 3 - Medium | 2 - High | szagar | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 10 | ASPAC - SIT 2
622 | Open | Undefined characters are displayed in the column header of the new tab after performing Data Export function in the document tab. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
623 | New | Document icon is missing in the new tab dialog box while performing Data Export action. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
624 | New | Search Template : No warning message is displayed to the user when search result exceeded the maximum limit of 1000. | Search Template |  |  | 4 - Low | 4 - Low | szagar | axsavi | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
626 | Closed | Search Template: Not able to type the Security policy type under the search criteria. | Search Template | Code | Code Error | 3 - Medium | 2 - High | axdubo | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 24 | ASPAC - SIT 2
627 | New | Security_ACE View Integration: My work workbasket count is mismatches, when a user is logged in ACE View and assigned only with my work and PO invoice approval work basket. | Security_ACEView Integration |  |  | 4 - Low | 4 - Low | sxtsat | axdubo | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 30.7972 | ASPAC - SIT 2
628 | Closed | Pend: Pend action is performed even for pended workitem. No Unpend action is displayed in the case actions drop down box of a Pended workitem. | Workflow Design | Code | Code Error | 2 - High | 2 - High | gxfati | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 15 | ASPAC - SIT 2
629 | Closed | Security_ACE View Integration: User is able to edit the work item of other BU(Eg: Korea, NZ), when a user assigned BU only with “Australia”. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-28 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 10 | ASPAC - SIT 2
630 | Closed | Search Template: All the relevant values are not getting displayed in “Case actions” drop down to proceed the work item to next status, when the user is opened the file using “search” functionality. | Search Template | Known Issue | Accepted as it is | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-30 | 1 | ASPAC - SIT 2
631 | Closed | Search Template : Unable to perform "Clone" functionality via "Search" tab | Search Template | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 9 | ASPAC - SIT 2
632 | Closed | ASPAC workflow: Payment batch amount and payment due date is editable in Awaiting Citi Direct approval status work item in Citi Direct work basket. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-06 | 7 | ASPAC - SIT 2
634 | Closed | Search Template : As per the Config sheet "Requestor" field value should be dropdown field but in ACEView it is getting displayed as textbox. | Search Template | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 14 | ASPAC - SIT 2
635 | Closed | Search Template: System is not clearing the results which are getting displayed in search screen, when user clicks on “Reset” button. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-15 | 16 | ASPAC - SIT 2
636 | Open | Search Template: The Title of the New PO Invoice created using the search tab varies from PO Invoice. | ACEView |  |  | 4 - Low | 4 - Low | rxloga | axsavi | 2015-04-29 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC |  | 29.7972 | ASPAC - SIT 2
637 | Closed | Search Template: File Type column in Note search results displays as File_Type code instead of Text. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 14 | ASPAC - SIT 2
638 | Closed | Flags and Milestones : System not displaying the Flags list in the Flags and Milestones tab in any PO Invoice workbasket. | Flags and Milestones | Wrongly Logged | Duplicate | 2 - High | 2 - High | akpand | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 5 | ASPAC - SIT 2
639 | Closed | Search Template: Saved filter is not working as expected in search screen. | Search Template | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 9 | ASPAC - SIT 2
640 | New | Open File and Open case : To expand or collapse the Tree View "<<" or ">>" icon is not available in ACE View. | Open File and Open Case |  |  | 4 - Low | 4 - Low | szagar | kxbizi | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 29.7972 | ASPAC - SIT 2
641 | Closed | Search Template: System is throwing an error message, when a user select folder type drop down in Search screen. | Search Template | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 6 | ASPAC - SIT 2
642 | Closed | Open File and Open case: On selecting a file and clicking on Attach button, a pop up is displayed "Please select atleast one record" in Attach case screen. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-04 | 5 | ASPAC - SIT 2
643 | Closed | Search Template: User is unable to delete any search results, when a user using the search functionality with “Append Search Results”. | Search Template | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 14 | ASPAC - SIT 2
644 | Ready for System Test | ACEView : The values displayed in "Peoplesoft Department" and "Alt Account" are not matching with the configuration sheet exactly | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 29.7972 | ASPAC - SIT 2
645 | Closed | Search Template: Vendor search and Deleted document search is not getting displayed in Search templates drop down as per the Config sheet. | Search Template | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-29 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 6 | ASPAC - SIT 2
647 | Closed | Search Template : Business Unit is not a 'Multi Select Choice List' field in Search template. | Search Template | Product Limitation |  | 2 - High | 2 - High | stsure | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-15 | 15 | ASPAC - SIT 2
648 | Closed | Pend: Pended workitem remains Pended even after performing Workflow case actions. | Workflow Design | Code | Code Error | 3 - Medium | 3 - Medium | gxfati | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 13 | ASPAC - SIT 2
649 | Closed | Search Template: Append results search is not working as expected in search screen. | Search Template | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-04-30 | 0 | ASPAC - SIT 2
650 | Closed | Open File and Open Case : Unexpected Error message is displayed by clicking on OK button in Upload pop up without selecting any document. | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | szagar | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 8 | ASPAC - SIT 2
651 | Closed | Search Template: Search screen is not getting displayed properly, when user navigating to search screen initially after login to ACE View. | Search Template | Config-Data | App DB | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 13 | ASPAC - SIT 2
652 | Closed | Search Template: Horizontal Scroll Bar not available in the Search screen. | Search Template | Code | Code Error | 3 - Medium | 2 - High | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 19 | ASPAC - SIT 2
653 | Closed | Search Template : Pagination is not getting displayed at the right side bottom of the search result screen. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 19 | ASPAC - SIT 2
654 | New | Open File and Open case : Audit record is not added in Audit/Notes trail tab on deletion of a document from Document list. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 28.7972 | ASPAC - SIT 2
655 | Closed | Data descrpency for Single Case | ACEView | Config-Data | MDS | 2 - High | 2 - High | srvxxx | srvxxx | 2015-04-24 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 11 | ASPAC - SIT 2
656 | Closed | Search Template : System does not displaying "No Default" radio button option in the default search template dialog. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-27 | 27 | ASPAC - SIT 2
657 | Closed | ASPAC Workfolw : System not diplaying the Send for Higher Approval drop down field when "Send for Higher Approval" action is performed | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | akpand | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-15 | 15 | ASPAC - SIT 2
658 | Closed | Open File and Open case : No error message is displayed while Indexing a document without selecting any value for Document type field which is mandatory. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 5 | ASPAC - SIT 2
659 | Closed | All the display columns for PO Invoice search template is not displayed in the Result set displayed. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | aythom | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 13 | ASPAC - SIT 2
661 | Closed | ASPAC Workflow: The status is not updated in the right side preview panel when status of the workitem is changed by performing "Action". | ASPAC Workflow | Requirement | New functionality | 3 - Medium | 3 - Medium | axrath | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 13 | ASPAC - SIT 2
663 | Closed | Vendor Search: Select button is not present in the Vendor search results page while selecting vendor magnifying icon under the PO Invoicing tab of a file. | Correspondents | Code | Code Error | 2 - High | 2 - High | gxfati | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 19 | ASPAC - SIT 2
664 | Closed | ASPAC Work flow: PO is not displayed in the “PO Invoice Payment “Workbasket after the Approver has approved it | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | gxfati | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 8 | ASPAC - SIT 2
665 | Closed | ASPAC Workflow: “Approve invoice” status is not getting displayed for higher approver in Case Actions to process the PO to “invoice approved Pending Auto/Manual post” status. | ASPAC Workflow | Wrongly Logged | Accepted as it is | 2 - High | 2 - High | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-01 | 1 | ASPAC - SIT 2
666 | Closed | ASPAC Workflow: The work item is not getting moved from my work basket after approving the PO. | ASPAC Workflow | Testing | Duplicate | 2 - High | 2 - High | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-01 | 1 | ASPAC - SIT 2
667 | Closed | Search Template : Sort Functionality(Ascending/Descending) is not working as expected in Search screen. | Search Template | Code | Code Error | 3 - Medium | 2 - High | sxtsat | axplac | 2015-04-30 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-27 | 27 | ASPAC - SIT 2
668 | Closed | PO file approved (which is displayed in his/her "My Work") to "Invoice Approved - Pending Auto Post", is not moved to the "PO Invoice Payments" work basket. | ASPAC Workflow | Code | Code Error | 1 - Critical | 2 - High | axplac | axplac | 2015-05-01 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-05 | 4 | ASPAC - SIT 2
669 | Closed | ASPAC Workflow: System is displaying “Case is not modified, there is nothing to save. Would like to save case anyway” message, when the user is modified the file and press “Alt+Shift+C” key. | ASPAC Workflow | Code | Code Error | 4 - Low | 4 - Low | sxtsat | dzmais | 2015-05-04 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 4 | ASPAC - SIT 2
670 | Closed | Drag&Drop: Automatic refresh is not happening to display the recently ingested Document file. | Drag and Drop | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-05-04 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 9 | ASPAC - SIT 2
671 | Closed | Search Template : Operating Units and PeopleSoft Department fields are not displayed in "Cost Allocation " search template | Search Template | Code | Code Error | 3 - Medium | 2 - High | axdubo | axplac | 2015-05-05 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 17 | ASPAC - SIT 2
672 | Closed | ASPAC Workflow : "No result found" error message is getting displayed along with the search result. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-05 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 3 | ASPAC - SIT 2
673 | Closed | Cost Allocation_Project Name/Code field should not be a mandatory | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | axdubo | axplac | 2015-05-05 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-15 | 10 | ASPAC - SIT 2
674 | New | ACEView : No action is performed when we select view option from User tab dropdown in Home page. | ACEView |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
675 | Closed | ACEView – System throws an "unexpected error" message, when trying to perform any actions in ACEView. | ACEView | Environment | Environmental | 1 - Critical | 1 - Critical | stsure | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-06 | 0 | ASPAC - SIT 2
676 | Closed | Search Template: "Top Search" button is not displayed beside "MI" button in the Application | Search Template | Known Issue | Future Fixes | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 2 | ASPAC - SIT 2
677 | Fixed | Workbasket Megafilter: Default filter is displayed when other filter is applied and moved to other workbasket and returned to the first workbasket. | Workbasket |  |  | 3 - Medium | 2 - High | axrath | axdubo | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
678 | Closed | Document Generation : Unable to edit GST % VAT rate . | Document Generation | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-15 | 9 | ASPAC - SIT 2
679 | Fixed | Search Template: "Date Created" field in "CitiDirect Payment Search" is accepting future dates in the start and end | Search Template |  |  | 4 - Low | 4 - Low | axrath | axdubo | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
680 | Open | Peoplesoft Integration- Vouchers including the Payment Method "MAN" are not being created In PS. (Telegraphic Transfer in ACEView) | ASPAC Peoplesoft Integration |  |  | 3 - Medium | 3 - Medium | swsure | bybull | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
681 | Open | Search Template : Mismatch in the values displayed in the Dropdown and the result displayed in the search result. | Search Template |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
682 | Closed | Search template : After setting default filter , Pop up message is getting displayed at the top of the home message but it is not visible. | Search Template | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 7 | ASPAC - SIT 2
683 | Open | Search template : Invalid error message is getting displayed in Cost Allocation search template. | Search Template |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
684 | Open | Search Template : Mismatch in the Error message displayed in the Usecase and in ACEView, While trying to save the search parameter with the existing name in search template. | Search Template |  |  | 4 - Low | 4 - Low | stsure | dzmais | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
685 | Closed | Search Template: No action is being performed when clicked on "Data Export" by right clicking on the workitem displayed in results | ACEView | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 7 | ASPAC - SIT 2
686 | Closed | Search Template: Upload,Case Actions and Doc Actions are displayed even after closing the file. | Search Template | Testing | Invalid Test Case | 3 - Medium | 3 - Medium | axrath | bysiva | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-08 | 2 | ASPAC - SIT 2
687 | Open | Search Templte: Warning message should be displayed while deleting a saved Default Search template.But the system shows normal message that is displayed while deleting any saved filter. | Search Template |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 22.7972 | ASPAC - SIT 2
688 | Closed | Search Template: System should prompt for Template name if not entered and clicked on "Save".But system displays an error message | Search Template | Code | Code Error | 4 - Low | 4 - Low | axrath | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 16 | ASPAC - SIT 2
689 | Closed | Search Template: Reset Columns to Default functionality is not present in the application | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-06 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-27 | 21 | ASPAC - SIT 2
690 | Closed | Open File and Open case: The file number is not updated in the tree view after saving the new PO Invoice. | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-27 | 20 | ASPAC - SIT 2
691 | Open | Workbasket: Pagination displays an unwanted box with total number of pages in the right end. | Workbasket |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
692 | Closed | Drag and Drop : Drag and Drop an email with attachment as excel document, email is getting ingested as an Excel document in the Document panel. | Drag and Drop | Code | Code Error | 3 - Medium | 2 - High | szagar | axplac | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-22 | 15 | ASPAC - SIT 2
693 | Closed | Security_ACE View Integration: User is able to edit the work item of the other’s Personal work basket, when a user assigned to the Personal work basket with “Read only” access in My work basket share. | Security_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-19 | 12 | ASPAC - SIT 2
694 | New | Search Template : Performing search using criteria as "Note Search for File" in Search Template and "All" in Note type, no result is displayed. | Search Template |  |  | 3 - Medium | 3 - Medium | szagar | dzmais | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
695 | In Progress | Workbasket Mega filter : File Type , Transaction Type and No of Transactions do not appear as Filter fields when filtering Finance Indexing Work Items. | Workbasket |  |  | 3 - Medium | 2 - High | stsure | axdubo | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
696 | In Progress | Unable to upload multiple documents. | Upload Document |  |  | 3 - Medium | 2 - High | aythom | axshme | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
697 | Open | Open File and Open Case: "Document Type" field values are not matched with the values in configuration document. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
698 | Closed | Pend: System is not updating the audit trail noting that 'Pend has Expired' for a workitem which has been unpended automatically. | Workflow Design | Wrongly Logged | Accepted as it is | 3 - Medium | 2 - High | gxfati | hvpras | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-14 | 7 | ASPAC - SIT 2
699 | Closed | System does not allow user to Unlock a workitem. | Workbasket | Wrongly Logged | Accepted as it is | 2 - High | 2 - High | gxfati | axplac | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-11 | 4 | ASPAC - SIT 2
700 | In Progress | Open File and Open Case: After linking a PO,CD and T&E documents to a document and clicking on "New File" button, "PO Invoice","CitiDirect Payment" and "T&E Expense" options are not enabled. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | j9norb | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
701 | Closed | Upload document: System displays “Unexpected” error message, when a user click on “ok” button without selecting the document while using Upload functionality in ACE View. | Upload Document | Code | Code Error | 4 - Low | 4 - Low | sxtsat | axplac | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC | 2015-05-13 | 6 | ASPAC - SIT 2
702 | New | MyWork Workbasket: When an action is performed on a workitem in "MyWork" workbasket, the workitems that belong to other workbasket are getting displayed | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-07 | ACEView | Build 1C - Cycle 2 | Release 1_ASPAC |  | 21.7972 | ASPAC - SIT 2
703 | Fixed | Open File and Open Case:The vendor name is not displayed properly in the tree view of a PO Invoice workitem | Open File and Open Case |  |  | 4 - Low | 3 - Medium | axrath | axdubo | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 20.7972 | ASPAC - SIT 2
704 | Closed | Workbasket: The count in the workbasket is displayed as (0/0) | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 5 | ASPAC - SIT 2
705 | Open | No prompt displayed while Uploading Email with attachments. | Upload Document |  |  | 4 - Low | 4 - Low | aythom | axdubo | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 20.7972 | ASPAC - SIT 2
706 | Fixed | Open File and Open Case: The "Payment Batch Amount" is displayed beside the File number in the tree view of CD File | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 20.7972 | ASPAC - SIT 2
707 | Closed | Search Template: Error message is getting displayed when right clicked on workitem from search results | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 5 | ASPAC - SIT 2
708 | Closed | PO File: Pop-up mesages is not appropriate when user enters all mandatory fields and tries to close the file without saving | ACEView | Environment | Environmental | 3 - Medium | 2 - High | axplac | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 11 | ASPAC - SIT 2
709 | Closed | ASPAC Workflow : Unable to perform "Closed created in error" on a workitem by right clicking functionality | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 14 | ASPAC - SIT 2
711 | New | ACEView : LanID's are getting displayed instead of the name in the workbasket names under the Mywork workbasket. | ACEView |  |  | 4 - Low | 4 - Low | axrath | axdubo | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 20.7972 | ASPAC - SIT 2
712 | Closed | BizTalk: Payment due date should be optional and not Mandatory | ASPAC Peoplesoft Integration | Code | Code Error | 2 - High | 2 - High | axplac | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-14 | 6 | ASPAC - SIT 2
714 | Closed | ASPAC Workflow: Warning message is being displayed evn after saving the Work item. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | bysiva | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 5 | ASPAC - SIT 2
715 | Open | PO file gets displayed in Home tab without a PO file number, when it is not saved. Not same to Defect 225(225 is now closed) | ACEView |  |  | 4 - Low | 4 - Low | axplac | axsavi | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 20.7972 | ASPAC - SIT 2
716 | Closed | Search Template: The "Select All" box in search results is not unselecting workitems. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-08 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 19 | ASPAC - SIT 2
717 | Closed | CR059 : System should display "Alert Popup" when we click on checkbox "Auto Post to PS" | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 4 | ASPAC - SIT 2
718 | Re-opened | CR042_ Not able to view the File Audit Notes/Document Audit notes, directly from the File Search Results | ACEView |  |  | 2 - High | 2 - High | axplac | axdubo | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 17.7972 | ASPAC - SIT 2
719 | New | Clone: In PO Document tab, "Address" field is not prepopulated in the workitem created using "Clone" | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | yxkhom | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 17.7972 | ASPAC - SIT 2
720 | Closed | Document Generation_ Unable to preview or Publish document in IE 8. | Document Generation | Code | Code Error | 2 - High | 2 - High | stsure | stsure | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 4 | ASPAC - SIT 2
721 | Closed | Search Template : Unable to Search for the "Deleted Document" in Search Template. | Search Template | Code | Code Error | 2 - High | 2 - High | stsure | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 17 | ASPAC - SIT 2
722 | Closed | User Is Inactive error message is displayed while trying to Log in with valid credentials. | ACEView | Environment | Build issue | 1 - Critical | 1 - Critical | aythom | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-11 | 0 | ASPAC - SIT 2
723 | Closed | CR037: Mismatch in the Error message getting displayed for Delete Reason Mandatory field | ASPAC Workflow | Code | Code Error | 4 - Low | 4 - Low | stsure | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 8 | ASPAC - SIT 2
724 | Closed | ASPAC workflow – Mandatory symbol (asterisk) is not present in the Department field (mandatory field), when creating a new PO work item. | ASPAC Workflow | Code | Code Error | 4 - Low | 4 - Low | stsure | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 2 | ASPAC - SIT 2
725 | Closed | ASPAC Workflow : Dropdown values of the "Operating Unit" field in the Cost Allocation tab displays many "Null" values. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | szagar | kanixd | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 17 | ASPAC - SIT 2
726 | Closed | Document: 'Search Links' window is blank when user tries to Link a document to another file | ACEView | Code | Code Error | 2 - High | 2 - High | rxloga | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 2 | ASPAC - SIT 2
727 | Closed | ASPAC Workflow: Error message is displayed for 35601-Singapore Onshore BU while creating a new PO. | ASPAC Workflow | Config-Data | App DB | 2 - High | 2 - High | szagar | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 2 | ASPAC - SIT 2
728 | Fixed | Pend: Pend duration field is not displayed in the Pend dialog box. | Workflow Design |  |  | 3 - Medium | 3 - Medium | gxfati | axdubo | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 17.7972 | ASPAC - SIT 2
729 | Open | Flags and Milestones Tab: Flags and Milestones Tab can be saved after adding comments, without entering and saving datas in PO Invoice Tab | Flags and Milestones |  |  | 3 - Medium | 3 - Medium | axplac | axdubo | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 17.7972 | ASPAC - SIT 2
730 | Closed | ASPAC Workflow: Unexpected error is getting displayed when tried to "Pend" a workitem | ASPAC Workflow | Testing | Invalid Test Case | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 2 | ASPAC - SIT 2
731 | Closed | Email broker: User could not save the document properties when ingested through email since the Ingestion User field and Originator field contains invalid values by default. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 11 | ASPAC - SIT 2
732 | New | Pend: On entering the type of reason in the Pend reason field the value in the drop down box is not getting populated automatically. | Workflow Design |  |  | 4 - Low | 4 - Low | gxfati | kxbizi | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 17.7972 | ASPAC - SIT 2
733 | Closed | Search Template: Search does not display any results when status value is selected as one of the duplicate values in "Status" field in "PO Invoice Search" | Search Template | Code | Code Error | 3 - Medium | 2 - High | axrath | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 11 | ASPAC - SIT 2
734 | New | Search Template : Mismatch in the Document Search template fields displayed in ACEView and Config Sheet | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axsavi | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
735 | Closed | Workbasket Megafilter: Pended workitems are not displayed even when "Show Pended" checkbox is checked in Megafilter | Workbasket | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 1 | ASPAC - SIT 2
736 | New | Open File and Open Case: System does not allow user to edit fields by clicking on the textbox in "Attach Case" screen | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
737 | New | Workbasket: Opening a Pended Work item from Workbasket and closing the file, returning back to Workbasket, no files are displayed | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
740 | New | Open File and Open Case: The "Select Link Type" filed in the "Attach Case" window is not allowing the user to type the values. | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
741 | New | Email_ACEView Integration: 'Document' count mismatch in the 'Indexing' tab for Test-2 Multi attachment Scenario | Email_ACEView Integration |  |  | 3 - Medium | 3 - Medium | bxheri | axdubo | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
742 | Closed | IE11 issue - cannot install D&D(Drag and Drop) plug in | ACEView | Environment | Interface System- Environment | 3 - Medium | 2 - High | axplac | axplac | 2015-05-11 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 7 | ASPAC - SIT 2
743 | Fixed | PO Invoice Processing_Actions_Duplicate drop down list displayed | ACEView |  |  | 3 - Medium | 2 - High | axplac | axdubo | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
744 | Closed | U60E8_WORKSITEMSTATUSCODE is populated with sting values | ACEView | Code | Code Error | 2 - High | 2 - High | srvxxx | srvxxx | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 3 | ASPAC - SIT 2
745 | Fixed | Search_template : Selected 'From' date is automatically getting populated in the 'To' date field in all the Date picker fields of Search Query, instead the Current date. | Search Template |  |  | 3 - Medium | 3 - Medium | gxfati | axdubo | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
746 | Fixed | Send Email : Documents (Emails with no subject line) are not getting ingested back into ACEView. | Send Email |  |  | 2 - High | 2 - High | stsure | axshan | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
747 | Closed | ASPAC Workflow_Cost Allocation: System is not displaying the saved Cost Allocation details of a workitem once it is closed and reopened. | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | gxfati | axplac | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 1 | ASPAC - SIT 2
749 | Closed | ASPAC Workflow: User is able to send Workitem for higher Approval more than once. | ASPAC Workflow | Wrongly Logged | Accepted as it is | 1 - Critical | 2 - High | axrath | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 0 | ASPAC - SIT 2
750 | Closed | Document: Unexpected error message is displayed when user tries to Link a document to another file using Search link. | Document Generation | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 2 | ASPAC - SIT 2
751 | Closed | Search Template: The "Select All" button is automatically checked when manually selected all workitems in search result. | Search Template | Wrongly Logged | Accepted as it is | 4 - Low | 4 - Low | axrath | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-13 | 0 | ASPAC - SIT 2
752 | Closed | ASPAC Workflow: Error on page is getting displayed, When the approver tries to approve the PO work item. | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | sxtsat | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 2 | ASPAC - SIT 2
753 | Closed | ASPAC Workflow: PO and T&E file status is not changing to "closed paid" after linking it with CD payment with status "CD Payment Released". | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | szagar | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-23 | 10 | ASPAC - SIT 2
754 | Closed | T&E : The title of the workitem tab is not updated after saving the new T&E workitem | ACEView | Code | Code Error | 4 - Low | 4 - Low | axrath | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 2 | ASPAC - SIT 2
755 | Closed | ASPAC Workflow : Title of the tree view tab is not getting displaying as expected for T&E Files. | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 7 | ASPAC - SIT 2
756 | Closed | ASPAC Workflow: Citi Direct ref no & Citi Direct Release date is not getting auto populated in Linked T & E file from Citi Direct work item. | ASPAC Workflow | Code | Code Error | 2 - High | 2 - High | sxtsat | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 9 | ASPAC - SIT 2
757 | Closed | ASPAC Workflow: As per the T & E Config excel, system is not displaying Citi Direct ref no & Citi Direct Release date as Citi Direct Payment No & Citi Direct Payment Date in T & E. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 14 | ASPAC - SIT 2
758 | Open | ACEView: "Select All" checkbox in "Search Template" and "Workbasket Megafilter" has inconsistent behaviour . | ACEView |  |  | 4 - Low | 4 - Low | axrath | mxkryz | 2015-05-13 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 15.7972 | ASPAC - SIT 2
759 | Closed | Search Template : Search results are not getting displayed in Cost Allocation search template. | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 8 | ASPAC - SIT 2
760 | Put On Hold | Correspondents : Only some of the field values are getting displayed in Correspondent tab. | Correspondents |  |  | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
761 | Closed | ASPAC Workflow: Country filed is not getting auto populated based on the Business unit in the T&E work itemS when a document is Scanned. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | akpand | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-15 | 1 | ASPAC - SIT 2
762 | In Progress | DaejaViewer_ACEView_Integration: Daeja viewer version varies between the document viewer and barcode viewer in ACE view. | Daeja_Viewer ACEView Integration |  |  | 2 - High | 2 - High | sxtsat | kxkana | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
763 | Closed | Email_ACEView Integration: When a work item is created with documents ingested using Email in finance indexing work item, BU & Department is getting displayed in the work item by default. | Email_ACEView Integration | Code | Code Error | 2 - High | 2 - High | sxtsat | sxtsat | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 12 | ASPAC - SIT 2
764 | New | Open File and Open case : By default Exported data are getting saved in .CSV format | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | stsure | dzmais | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
765 | Open | Search Template: "Ingestion Type" column in search results is blank for some results and displays number for some results. | Search Template |  |  | 3 - Medium | 2 - High | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
766 | New | Search Template: "File number" column is blank for some documents in "Document Search" results | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
767 | New | Search Template: "Security Policy" column is blank for some search results and displays number for some results in "Document Search" | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
768 | New | Search Template_Note Search for File: When opening a file from 'Note Search for File' search results, the opened file does not display 'Notes/Audit Trail' section by default | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | mxkryz | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
769 | New | Search Template: "Ingestion Info" column displays wrong values for some search results in "Document Search". | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
770 | Re-opened | Search Template: System displays inconsistent behaviour while saving a "PO Invoice" without entering mandatory values in "PO Document" tab and "Cost Allocation" tab | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
771 | New | Search Template: Inconsistent values are displayed in "Ingestion User" column for documents of ingestion type "EMAIL Service". | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
772 | New | Search Template: System does not display any value in "File Type" column for results belong to Finanace Indexing workitem | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
773 | Fixed | Search Template: "Ingestion Date" and "Date Created betweeen" fields in "Document Search" accepts future dates | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
774 | Closed | ACEView: Inconsistent behaviour exists between selecting a workitem by clicking on checkbox in "Search" and in "Megafilter" | ACEView | Testing | Accepted as it is | 4 - Low | 4 - Low | axrath | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 13 | ASPAC - SIT 2
775 | Closed | ASPAC Workflow: Able to Link the PO with status "Posted in PS" to a Citi Direct payment. | ASPAC Workflow | Testing | Query | 3 - Medium | 3 - Medium | szagar | szagar | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 14 | ASPAC - SIT 2
776 | New | Drag and Drop: Unable to drag and drop a document from Sharepoint into the ACEView. | Drag and Drop |  |  | 3 - Medium | 3 - Medium | akpand | axdubo | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
777 | Closed | Search Template: While searching for 'Note Search for Document', in search template, the records for 'Notes/Audit Trials' are getting displayed | Search Template | Code | Code Error | 2 - High | 1 - Critical | axrath | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 5 | ASPAC - SIT 2
778 | Open | ASPAC Workflow: User with finance indexer role is not getting Email notification, when a work item remains in finance indexing work basket more than 48 hours as per the config. | ASPAC Workflow |  |  | 2 - High | 2 - High | sxtsat | axdubo | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 14.7972 | ASPAC - SIT 2
779 | Closed | Search template_Note Search for File: Filter criteria set for 'Notes/Audit Trail' section remains same even after closing and re-opening the file | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 13 | ASPAC - SIT 2
780 | Closed | Search template_Note Search for File: Clicking on 'Reset' button in 'Notes/Audit Trail', the values are not reset, instead the filter criteria is applied when closed and re-opened the file. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 13 | ASPAC - SIT 2
781 | Closed | ASPAC Workflow: Unable to delete the multiple cost allocation entries in the cost allocation tab, when a user tries to delete by checking “Select all” check box. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | bysiva | 2015-05-14 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 12 | ASPAC - SIT 2
782 | New | AceView is not tracking the build details currently | ACEView |  |  | 4 - Low | 4 - Low | axplac | yxkhom | 2015-05-12 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 16.7972 | ASPAC - SIT 2
783 | New | Search Template: "Date Created" field in "PO Invoicing Search" is displaying irrelavant error message when "Date Created to" field is not selected and clicked on "Search" | Search Template |  |  | 4 - Low | 4 - Low | axrath | axshme | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
784 | Closed | Search Template: Error message is getting displayed after clicking on "Search" in "Search Template".The behaviour is intermittent. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-21 | 6 | ASPAC - SIT 2
785 | Closed | Search Template : Text box are not getting displayed as expected in PO Invoice search template. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 4 | ASPAC - SIT 2
786 | Open | Search Template : Mismatch in the Deleted Document Search template fields displayed in ACEView and Config Sheet | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axsavi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
788 | New | ACEView : "About" Icon is not getting displayed as expected. | ACEView |  |  | 4 - Low | 4 - Low | stsure | axdubo | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
789 | New | Search Template: No Error message is displayed when clicked on "Clone" without selecting any workitem | Search Template |  |  | 4 - Low | 4 - Low | axrath | mxkryz | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
790 | Closed | Search Template: When a File is created using clone and clicked on "Save", the generated "File Number" is same as the "File Number" of source PO. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | axrath | bysiva | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 7 | ASPAC - SIT 2
791 | Closed | ASPAC workflow: System displays higher approver name in approval PO work basket (BU: Australia), even though the approver is not assigned to that BU (Eg: Australia) in security. | ASPAC Workflow | Known Issue | Accepted as it is | 2 - High | 2 - High | sxtsat | sxtsat | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 11 | ASPAC - SIT 2
792 | Closed | Cost Allocation_PO document: User unable to Publish the PO document. Unexpected error is getting displayed. | ASPAC Workflow | Code | Code Error | 2 - High | 1 - Critical | gxfati | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 7 | ASPAC - SIT 2
793 | Closed | ASPAC Workflow : Unable to delete a Indexed document . | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | stsure | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 12 | ASPAC - SIT 2
794 | Closed | ACEView : Close button "X" is not displayed as expected in ACEView . | ACEView | Code | Code Error | 4 - Low | 4 - Low | stsure | dzmais | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 7 | ASPAC - SIT 2
795 | Closed | Search Template: Reset button is not clearing the right hand side results when user performing search functionality using Append search Results. | Search Template | Code | Code Error | 3 - Medium | 3 - Medium | sxtsat | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 12 | ASPAC - SIT 2
796 | Closed | Search template: User is able to open a file number from 'Search template' when it is locked by another user. | Search Template | Code | Code Error | 1 - Critical | 1 - Critical | axrath | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 7 | ASPAC - SIT 2
797 | New | ACEView : Filter slider is not working as expected in ACEView. | ACEView |  |  | 4 - Low | 4 - Low | stsure | kxbizi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
798 | Closed | ASPAC Workflow : System not displaying the "Values" in Send for Higher Approval drop down when "Send for Higher Approval" action is performed | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | stsure | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-28 | 13 | ASPAC - SIT 2
799 | Closed | ASPAC Work flow : Error pop is getting displayed frequently while working with Finance Indexing work item. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | szagar | szagar | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 3 | ASPAC - SIT 2
800 | New | Indexing Document: Import Info, Import Date,Import User and Import Type field names are not displayed in the application as per configuration sheet | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
801 | Ready for System Test | OA limit has not been set for the Business unit of Macau but the Higher approval list is getting displayed. | ACEView |  |  | 3 - Medium | 3 - Medium | akpand | bysiva | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
802 | Closed | ASPAC Work flow: Application performance is very slow. | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | szagar | kxkaru | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 3 | ASPAC - SIT 2
803 | Closed | Open File and Open Case: Mismatch exists between UI configuration document and ACEView- "Originator" and "Ingestion User" fields in "Document" tab | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 4 | ASPAC - SIT 2
804 | New | ASPAC Workflow : Field validation message is getting displayed for Country field in T&E Expenses processing workbasket. | ASPAC Workflow |  |  | 4 - Low | 4 - Low | stsure | dzmais | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
805 | Open | Open File and Open Case: Only one document is being hidden when all the documents are selected and clicked on "Hide" from right click menu | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
806 | New | Search Template: "Payment Due Date" column is not available in search results. | Search Template |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-05-15 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 13.7972 | ASPAC - SIT 2
807 | Open | Open File and Open Case : "Show Hidden" checkbox is not enabled after hiding a document . | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
808 | Re-opened | Mega Filter: Clicking on the Vertical tab of ‘Mega Filter’, the filter window is expanded. Applying any filter criteria, the filter is applied, but the values are not visible completely. | Workbasket |  |  | 4 - Low | 4 - Low | axrath | vxshme | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
809 | Closed | Megafilter : Clicking on the ‘Mega filter’ header tab, the expanded Mega filter window is collapsed. | Workbasket | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 9 | ASPAC - SIT 2
810 | Closed | Notes : "Action" in "Document Notes" is displayed as "39" | Notes | Code | Code Error | 2 - High | 2 - High | axrath | axrath | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 8 | ASPAC - SIT 2
811 | Closed | Open File and Open Case: In Document panel, BU and Department values are not displayed | Open File and Open Case | Testing | Query | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 0 | ASPAC - SIT 2
812 | Open | Open File and Open Case : After any modifications done in Documnts panel and refresh happens, all documents are getting selected automatically. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
813 | Closed | Notes: "Document Notes" is getting logged without selecting any document | Notes | Wrongly Logged | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 0 | ASPAC - SIT 2
814 | Closed | Open case and Open FIle: Checking 'Show Hidden' checkbox, the hidden files are not displayed. | Open File and Open Case | Testing | Not Reproducible | 3 - Medium | 2 - High | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 4 | ASPAC - SIT 2
815 | Closed | ACEView : In vendor search results, "Payment Method" column is not avialable. | ACEView | Requirement | Business Requirements Incorrect | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-18 | 0 | ASPAC - SIT 2
816 | Open | Search Template: "Data Export" buton is enabled even when no results are selected. | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
817 | New | Open file adn Open case: 'Documenty type' value for selected 'Approve Purchase' folder type, is displayed wrongly for a PO indexed document | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
818 | Closed | Notes/Audit Trail: 'Blank' value is not displayed in the 'Expand Filter' screen fields to show all records | Open File and Open Case | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-21 | 3 | ASPAC - SIT 2
819 | Closed | Open file and Open case: 'Data Export' option is not available for 'Document Notes' section in the TDD document | Open File and Open Case | Testing | Accepted as it is | 2 - High | 2 - High | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-19 | 1 | ASPAC - SIT 2
820 | Open | Open file and Open case: 'Unknown error while adding note' message is displayed when an 'Alert' note with more than 4000 characters | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
821 | Open | Open case and Open file: 'Notes record' which is added first is not displayed as First(Ascending Order). Recently added note is displayed at the first. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
822 | Closed | Open file and Open case: Clicking on 'Export to Excel' option in the 'Document Notes' tab, 'Save' dialog box is not displayed to save the file | Open File and Open Case | Known Issue | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axrath | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 2 | ASPAC - SIT 2
823 | Open | Open file and Open case: 'Save' button is enabled even before the user makes changes/modifications in the Notes. | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
824 | New | Open file and Open case: User is unable to enter 'Expiration/Reminder Date/Time' while adding a new note. User is able to only select the value from Calendar pop-up/Drop down for time | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
825 | New | Open file and Open case: There is a mismatch in 'Error message' definition while entering Past date in 'Notes' between TDD document and the application | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
826 | Open | Open file and Open Case: 'Audit Note' is generated with 'Document Re-Indexed' Action value when the user Index a document for the first time | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
827 | Open | Link payment: 'Currency' field is displayed for 'Link Payments' action when a T&E file is linked from a CitiDirect File | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
828 | Closed | Link Payments: 'Unexpected error' message is displayed when the T&E file is searched for Linking it with 'CitiDirect' file via Link Payments | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 4 | ASPAC - SIT 2
829 | Open | Create PO : There is mismatch in default values between configuration document and ACEView application | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
830 | Closed | Open file and Open case: No warning message is displayed when user modifies a note and navigates to next note without saving the changes. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 9 | ASPAC - SIT 2
831 | Closed | ASPAC Workflow : No error message is displayed when clicked on "Unlink Payments" without selecting any records. | ASPAC Workflow | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 9 | ASPAC - SIT 2
832 | Open | Open file and Open case: ' View Note' pop-up window/screen is not displayed properly | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 10.7972 | ASPAC - SIT 2
833 | Closed | Linked Payments: 'Unexpected error. Please try again' error message is displayed when user detaches a case form linked CitiDirect file. | Open File and Open Case | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-18 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 9 | ASPAC - SIT 2
834 | Closed | Workbasket : "Pend" icon is not added to the workitem after pending it. | Workbasket | Testing | Incorrect Test Data | 2 - High | 2 - High | axrath | axplac | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 1 | ASPAC - SIT 2
835 | Open | Document Generation : Warning icon for mandatory fields is not displayed properly in "PO Document" tab | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
836 | Fixed | Workbasket_Megafilter: 'Unexpected error. please try again' error message is displayed when searching for a result in 'Mega filter' | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
837 | Closed | Search Template : Unable to perform any action on search result. | Search Template | Code | Code Error | 2 - High | 1 - Critical | axrath | axplac | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 3 | ASPAC - SIT 2
838 | Open | Search template: 'Search template' UI is not displayed properly. The allignment of the fields is not good. | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
839 | Open | Workbasket_Megafilter: 'A value for File Number is invalid' error message is displayed even the valid fiel numebr is entered in Mega filter | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | vxshme | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
840 | Open | Workbasket_Mega FIlter: Filter results are not displayed according to the Applied Filter criteria | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | vxshme | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
841 | Closed | Notes/Alert: Note type - 'Query' is not available in the ACEView system. | Open File and Open Case | Known Issue | Future Fixes | 2 - High | 2 - High | axrath | axplac | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-26 | 7 | ASPAC - SIT 2
845 | Closed | ASPAC Workflow: System accepts random values in "File Number" field while creating new file from "New File" button in "Document" tab | ASPAC Workflow | Code | Code Error | 1 - Critical | 1 - Critical | axrath | axplac | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 3 | ASPAC - SIT 2
846 | New | Open file and Open Case: Document pane Filter screen - Unable to modify the 'Ingestion From' date to any future date once the date is selected | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
847 | New | Open file and Open Case: A 'Blank Column' is displayed in 'Document pane' | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
848 | New | ASPAC Workflow : There is mismatch between selected value while creating and value after creation. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
849 | New | Open file and Open case: 'Alert' icon is not displayed against a file in 'Workbasket' | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
850 | New | Workbasket_Re-assign: There is no pre-defined text values available when re-assigning a work item | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | axdubo | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
851 | New | Open file and Open case: There is no option available to set any Default filter for 'Document note', 'File note' | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
852 | New | Workbasket: 'Alert' visual indicator is not displayed fagainst the respective file in Workbasket | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
853 | New | Workbasket Share : User is able to edit(index and delete documents, change status) workitems from shared read only workbasket | Security_ACEView Integration |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
854 | Open | Index Document : After indexing a Document, "Document Indexed" icon is not visible. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
855 | Open | ACEView : When "Enter" key is pressed, "OK" button is not selected. | ACEView |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
856 | Open | ACEView : Whenever user Hover over a User's LAN ID system should display the User's Full Name and vice versa.But system does not display User's Full Name in Document panel. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
857 | Open | Open File and Open Case : When user moves up and down in Tree view using keyboard arrow keys, the documents presented in the viewer also should move.But the documents viewer does not refresh. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
858 | Open | Workbasket: The colour difference between read and unread workitems is not available in the application | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
859 | Open | ACEView : The System Environment (i.e. DEV, SIT, UAT or PRD), and the Version of the Release (i.e. 1.0), must be displayed on an area that is visible from all pages of the application, e.g. in the Browser Title Bar.But it is not displayed. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
860 | Closed | ACEView: The system should auto-populate (filter) all dropdown values when the User begins to type when focussed on a dropdown field.This functionality is not working in application. | ACEView | Product Limitation |  | 3 - Medium | 3 - Medium | axrath | axdubo | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-20 | 1 | ASPAC - SIT 2
861 | Open | Open File and Open Case : Data Export-Export only visible columns is exporting all columns. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
862 | Open | ACEview_Workbasket: While Hovering over a Locked file, the 'Name/LAN ID' of the locked user is not displayed as a tool-tip | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
863 | Open | Workbasket : Data Export option is not available in Workbasket. | Workbasket |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
864 | Open | ACEView : In Document panel, tool tip showing the data in the cell is not displayed for columns. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
865 | Put On Hold | Diary - Expected file number is not displayed when clicked on the Diary displayed on the top banner | Diary |  |  | 2 - High | 2 - High | axplac | axplac | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
866 | Open | Diary : System does not allow the user to close diary remainder screen unless the "Open File" checkbox is unchecked | Diary |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-19 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 9.7972 | ASPAC - SIT 2
867 | New | Open File and Open case : 'Document tab' shoudl be displayed by default when opening any file with a document indexed to it | Upload Document |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
868 | Open | Document Notes: Document Notes is not added when a document is Exported and Sent by Email. | Notes |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
869 | Open | Workbasket_Megafilter: There are some Blank spaces available for 'Country' field value in Megafilter. When removing these blank spaces, 'A value for Country is invalid' error message is displayed | Workbasket |  |  | 4 - Low | 4 - Low | rxloga | dzmais | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
870 | New | Document Generation: Mismatch between Configuration sheet and Field values in 'PO Document' tab | Document Generation |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
871 | Open | Workbasket Megafilter : Under "Show Pended" checkbox, "Pended Until From", "Pended Until to", "Pend Comment" fields are not available for all workbaskets. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | vxshme | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
872 | Closed | Open File and Open Case : A column name "ID" is displayed in search results in "Attach Case" search screen | Open File and Open Case | Code | Code Error | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 7 | ASPAC - SIT 2
873 | Open | Open file and Open case_Attach Case: After linking two files, User is unable to open the File-B' from 'File-A' in both '2-way' and '1-way' link type | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
874 | Fixed | Application should consistently use 'ACE View' in all screens, dialogs, messages, etc., | ACEView |  |  | 3 - Medium | 2 - High | axrath | axdubo | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
875 | Open | Drag and Drop: There is a difference in behaviour when ingestion a EMAIL via Drag and Drop | Drag and Drop |  |  | 2 - High | 2 - High | axrath | mxkryz | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
876 | Open | Open File and Open case : In Document list filters, "Recently Added", "Last 5 Days", "Last 15 days", "Last Month" options are not available to quickly filter documents | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
877 | Open | ACEView : System does not allow user to open a workitem locked by other user in read only mode. | ACEView |  |  | 2 - High | 2 - High | axrath | axplac | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
879 | Open | Attach Case : System displays files without File Number in "Attach Case" search results when user tries to link any file via Attach Case | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
880 | Open | Open File and Open case : File Type and Folder Type are not copied when copying a document from one workitem to anoother workitem. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | axshme | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
881 | New | Index Document : When user tries to close the workitem without saving document properties, the system does not display any error message. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
884 | New | Document Actions: Documetn properties copied displays Number '2' for 'Document Type' field when clicking on 'Document Send' from 'Document Actions'. | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
885 | New | Search Template: Visual indicator to indicate if the file is open for modification by another user is not displayed in search results screen | Search Template |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
886 | Closed | Document Actions: Finance indexing work item is created successfully, even though few mandatory fields are blank - 'Transaction File Type', 'Transaction Type' and 'Transaction Count' | ACEView | Testing | Accepted as it is | 2 - High | 2 - High | rxloga | axplac | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 2 | ASPAC - SIT 2
887 | Closed | ACEView: Inconsistency exists between 'Search Template' and 'Workbasket' | ACEView | Testing | Accepted as it is | 4 - Low | 4 - Low | axrath | axplac | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 7 | ASPAC - SIT 2
888 | Closed | Manage User Preferences: When user selects "Horizontal" in "Search Screen Layout" field, the search screen is displayed in Vertical and vice-versa. | Manage User Preference | Code | Code Error | 2 - High | 2 - High | axrath | axplac | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 2 | ASPAC - SIT 2
889 | Open | Copy Document: When a document with notes is copied to another file, only 'Alert' notes of the document should be copied to the new destination. But 'Diary' icon is displayed against that document in the new file. | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
890 | New | Notes: 'Audit' note is not created for creation of 'Alert/User/Diary' notes | Notes |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
891 | Deferred | Help: System displays "Coming Soon" when clicked on "Help" from "User" dropdown | ACEView | Product Limitation | Accepted as it is | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
892 | Fixed | Send Email: System throws an error message when a document is send via 'Save and Send' action. | Send Email |  |  | 2 - High | 2 - High | rxloga | axshan | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
894 | Closed | Index Document : User is not able to index child documents after ingesting a mail via "Drag and Drop". | Open File and Open Case | Requirement | Business Requirements Incorrect | 2 - High | 1 - Critical | axrath | axplac | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 6 | ASPAC - SIT 2
895 | Closed | ACEView : "Status" does not have same values across the application | ACEView | Product Limitation |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-21 | 0 | ASPAC - SIT 2
896 | New | Open File and Open Case : Unable to hide "Document Description"column in document panel. | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | axsavi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
897 | New | ACEview: All the 'Columns headers' are not available for filtering the Search results | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | mxkryz | 2015-05-20 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 8.7972 | ASPAC - SIT 2
898 | Open | ACEView : When a User hides / shows Columns, this preference is not displayed when user Logs out and logs back in. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | mxkryz | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
899 | Open | Upload Document: On Indexing a document in Finance Indexing work item, document status is displayed as New/Not Indexed. | Upload Document |  |  | 3 - Medium | 3 - Medium | szagar | kxbizi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
901 | Closed | ACEview_Document: 'Unique ID' field is not available for the document when 'Move' action is performed in a file | ACEView | Testing | Incorrect Test Data | 3 - Medium | 3 - Medium | rxloga | bysiva | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 1 | ASPAC - SIT 2
902 | New | Document Upload: Change the wording on the Dialogue Box while uploading a document into a File | Upload Document |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
903 | Open | ASPAC workflow : System allow to Re-assign CD workitem to PO Processor where the PO Processor has no access to "Citidirect Payment approval" workbasket. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | stsure | dzmais | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
904 | New | Open File & Open Case: When Copying across Files with the same Document Taxonomy, the copied document from File A is not getting copied under Document type of File B. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | gxfati | axshme | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
905 | New | ACEview: Inconsistency in the application behaviour - Pagination footer tab and 'Column Header' section | ACEView |  |  | 4 - Low | 4 - Low | rxloga | axsavi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
906 | Open | Open File & Open Case: When Copying document across Files with the different Document Taxonomy, Document type of File A is not getting changed to Document type of File B. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | gxfati | axshme | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
907 | Open | ACEview: All records are selected when 'Column Header' is moved/re-ordered in Home result page | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | axshme | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
908 | New | Open File and Open case : "Linked Files" folder in tree view is not collapsed by default. | Open File and Open Case |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
909 | In Progress | Daeja viewer : When opening an email with attachments in Daeja viewer , attachment explorer view is not getting displayed by default. | Daeja_Viewer ACEView Integration |  |  | 3 - Medium | 3 - Medium | stsure | stsure | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
910 | Open | ASPAC Workflow: System is not displaying warning message, if a user selects “Finance Restricted” in file level security groups field when a user assigned to only “None” in Security. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | sxtsat | axsavi | 2015-05-21 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
912 | Open | DTSI Issue_Vat_applicability could be ‘N’ if not ‘O’ for ‘Out of scope’ | ACEView |  |  | 3 - Medium | 3 - Medium | axplac | hvpras | 2015-05-21 | Vega Interchange | End to End - Cycle 1 | Release 1_ASPAC |  | 7.7972 | ASPAC - SIT 2
913 | New | Document Generation – Mandatory symbol (asterisk) is not present in the Required fields of PO Document tab. | Document Generation |  |  | 4 - Low | 4 - Low | stsure | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
914 | Open | Workflow design: Unable to perform Bulk Indexing of multiple Work items/Documents | Workflow Design |  |  | 3 - Medium | 3 - Medium | stsure | bybull | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
915 | Open | Document Generation: System generating incorrect year format while generating the PO document in IE8 | Document Generation |  |  | 4 - Low | 4 - Low | sxtsat | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
916 | Closed | Document Generation_PO Document: Downloaded PO Document is not getting saved in Word or Excel format. | Document Generation | Product Limitation |  | 3 - Medium | 3 - Medium | gxfati | axsavi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-22 | 0 | ASPAC - SIT 2
917 | Open | Document Generation – Document properties are not getting displayed as expected for generated PO Document. | Document Generation |  |  | 3 - Medium | 3 - Medium | stsure | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
918 | Closed | The send for Higher Approval drop down values are not loading properly on click of Actions outside a work item. | ASPAC Workflow | Code | Code Error | 3 - Medium | 2 - High | aythom | axplac | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 5 | ASPAC - SIT 2
919 | Open | Aceview : Icons are not getting displayed as expected for different document types in Document list. | ACEView |  |  | 4 - Low | 4 - Low | stsure | mxkryz | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
920 | Open | ACEView : Icons are not getting displayed for document action and case action List. | ACEView |  |  | 4 - Low | 4 - Low | stsure | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
921 | In Progress | Search Template : Error message is displayed while opening a PO using Search Template with status Invoice Approved Pending Manual Post. | Search Template |  |  | 2 - High | 2 - High | szagar | vxshme | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
922 | New | ACEview: 'Unlock/Open' icon is displayed when a user opens a work item locked by another user in Read-only mode and closes the file | ACEView |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
923 | New | ACEview: 'Read/Unread' icon is not displayed for a document | ACEView |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
924 | Closed | ACEview: The workitems/files opened by user remains locked even after the user logs out of ACEview. | ACEView | Code | Code Error | 3 - Medium | 3 - Medium | rxloga | axplac | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 5 | ASPAC - SIT 2
925 | New | Link Payments : When user selects "Link Payment" without selecting any record, the system closes the "Link Payments" screen | ACEView |  |  | 4 - Low | 4 - Low | axrath | dzmais | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
929 | Open | Search Template : Cost Allocation search is not displaying proper results. | Search Template |  |  | 2 - High | 3 - Medium | axrath | axsavi | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
930 | New | Daeja Viewer_Annotations: Document annotations is not getting retained when the document is moved to another file using 'Move' action. | ACEView |  |  | 3 - Medium | 3 - Medium | gxfati | gxfati | 2015-05-22 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 6.7972 | ASPAC - SIT 2
932 | New | Document Notes: There is no option for user to add note from ‘Document Indexing Panel’ | Notes |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
933 | New | Document Indexing: In ‘Auto-Fill’ action, even the ‘Document Description’ field is copied to the next file. Unable to differentiate/demarcate multiple files if it has same description | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | kxbizi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
934 | New | Search Template: "Document Search" is not displaying any results when "Ingestion Type" field is entered. | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
935 | New | Document Indexing: In Document indexing tab, naming of ‘Auto-Fil Next’ field is displayed as ‘Auto-Fill’ | ACEView |  |  | 4 - Low | 4 - Low | rxloga | kxbizi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
936 | New | ACEview: The drop-down list for selecting the columns to be shown/hidden is not displayed in ascending order | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | axshme | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
937 | New | ACEview: There is no ‘New File’ option available for the user on the Search Results of Document Indexing panel | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | mxkryz | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
938 | New | Workbasket_Megafilter: Applying a filter to the ‘Queue’, the number of Pended Work items in the Queue is not altered based on the applied filter | ACEView |  |  | 4 - Low | 4 - Low | rxloga | vxshme | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
939 | New | Workbasket: There is no option available for user to change the priority of any work item and re-assign the same to another user in one action from Work basket | Workbasket |  |  | 3 - Medium | 3 - Medium | rxloga | j9norb | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
940 | New | Search template: When results are appended in ‘Search template’ ‘Sorting’ and manipulating appended searches as a single set of results is not working | Search Template |  |  | 3 - Medium | 3 - Medium | rxloga | axshme | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
941 | New | ACEview: The menu option for ‘View’ selection should be displayed in the right side of the page | ACEView |  |  | 4 - Low | 4 - Low | rxloga | mxkryz | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
942 | New | Search Template: Search results are not displayed when "Note Type" field is selected as "All" . | Search Template |  |  | 3 - Medium | 3 - Medium | axrath | dzmais | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
943 | Ready for System Test | ACEView : There is no opion to save and set default filter for filters in "Document Notes" and "Notes/Audit Trial" and "Document List" tabs. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | bysiva | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
944 | Closed | Datacap Scanning : The option "Auto" for the "Page Layout" is not present in web-based scanning tool. | Datacap Scanning | Requirement | Business Requirements Incorrect | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 1 | ASPAC - SIT 2
945 | Closed | Datacap Scanning : There is no option to select "Number of Pages" in document in web-based scanning tool. | Datacap Scanning | Requirement | Accepted as it is | 3 - Medium | 3 - Medium | axrath | axplac | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 1 | ASPAC - SIT 2
946 | Closed | Manage User Preference: There is no option to define a language preference in the User Preference section. | Manage User Preference | Known Issue | Future Fixes | 3 - Medium | 3 - Medium | akpand | jxkosh | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 1 | ASPAC - SIT 2
947 | New | ACE View: No option is available for User to Select All columns or Deselect All columns at once in ACE View. | ACEView |  |  | 3 - Medium | 3 - Medium | szagar | j9norb | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
948 | New | ASPAC Workflow_Closed PO: Documents are not getting added to Closed Workitems by using Upload Ingestion method. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
949 | Closed | ASPAC Workflow: Work item is changing the status to "Invoice approved - pending auto post", when a user checks "Auto Post to PS" and clicks "No" in the warning message. | ASPAC Workflow | Code | Code Error | 2 - High | 1 - Critical | sxtsat | axplac | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 1 | ASPAC - SIT 2
950 | In Progress | Flags and Milestones: Invoice checked milestone is not getting highlighted automatically in PO file. | Flags and Milestones |  |  | 2 - High | 2 - High | gxfati | axsavi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
951 | Open | ASPAC Workflow : For "Invoice Arrived" status, "Department" field is mandatory.But it is read only field in "Goods Arrived" status. | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | axrath | bybull | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
952 | Open | ACEView : There is no option to get the URL of the File/Workitem. | ACEView |  |  | 3 - Medium | 3 - Medium | axrath | axrath | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
953 | New | Upload: File Number generated for the file created using Direct Upload is not in the proper format. | Upload Document |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
954 | New | Notes/Audit Trilal : The Expiration date is set to "01/01/1970" by default when changing an "User" or "Inactive" note to "Alert" | Notes |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
955 | In Progress | ASPAC workflow : Dropdown values are getting repeated in Send invoice for approval dropdown | ASPAC Workflow |  |  | 3 - Medium | 3 - Medium | stsure | yxkhom | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
956 | Open | Search template : Alt account dropdown values are not getting populated | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
957 | New | Document Generation : After generating a PO Document, system should add "File Name" as "YYYYMMDD – [File Number] Purchase Order.pdf" to the document.But "File Name" is not present in the application. | Document Generation |  |  | 3 - Medium | 3 - Medium | axrath | kxbizi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
958 | Closed | Cost Allocation - Alt account field displayed the dropdown vlaues as 'Null' | ACEView | Code | Code Error | 1 - Critical | 1 - Critical | axplac | kanixd | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 0 | ASPAC - SIT 2
959 | New | When a document is closed in the viewer, it is not getting un-selected in the document list | Daeja_Viewer ACEView Integration |  |  | 4 - Low | 4 - Low | akpand | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
960 | Fixed | ACEview: When Approving a Workitem using 'Actions' in workbasket( Personal/Public), unexpected error message is displayed. | ACEView |  |  | 3 - Medium | 3 - Medium | rxloga | axdubo | 2015-05-26 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 2.7972 | ASPAC - SIT 2
961 | New | Count of the number of Un-Read Workitems in a Queue is not displayed correctly in the bottom of screen when a Queue filter is used. | ACEView |  |  | 4 - Low | 4 - Low | akpand | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
962 | Open | ACE View : An ActiveX Control pop up is displayed every time the user login into ACE View system. | ACEView |  |  | 3 - Medium | 1 - Critical | szagar | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
963 | New | The number of Workitems to be displayed per page within the Queues is not 30 by default. | Workbasket |  |  | 4 - Low | 4 - Low | akpand | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
964 | Closed | The Approver names is displayed multiple times when clicking on the dropdown for Higher Approve in the pop-up for "Send for Higher Approval" - IE11 issue | ACEView | Wrongly Logged | Duplicate | 3 - Medium | 3 - Medium | axplac | axsavi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC | 2015-05-27 | 0 | ASPAC - SIT 2
965 | New | Document Generation_PO Document:After generating a Document from a Template, the User is not being provided by the option to automatically index the document back to the File / Workitem. | Document Generation |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
966 | New | Send Email: If the Document(s) has annotations, when the User selects to email it out, system is not generating any option for emailing the particular document with or without its annotations. | Send Email |  |  | 3 - Medium | 3 - Medium | gxfati | kxbizi | 2015-05-27 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 1.7972 | ASPAC - SIT 2
967 | New | Search template : File type is not getting displayed in search result for "Deleted Document search" template. | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axsavi | 2015-05-28 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 0.79721 | ASPAC - SIT 2
968 | New | Search template : Mismatch in the search criteria dropdown values and search result in "Delete document"search template | Search Template |  |  | 4 - Low | 4 - Low | stsure | axsavi | 2015-05-28 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 0.79721 | ASPAC - SIT 2
969 | New | Search Template : Ingestion type is not getting displayed as "Single Select Choice List' field in Search template. | Search Template |  |  | 3 - Medium | 3 - Medium | stsure | axsavi | 2015-05-28 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 0.79721 | ASPAC - SIT 2
970 | New | Index Document : Unable to edit document description of the child document under a batch. | Open File and Open Case |  |  | 3 - Medium | 3 - Medium | axrath | axsavi | 2015-05-28 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 0.79721 | ASPAC - SIT 2
971 | Open | Send Email: Empty Document is getting attached when a user performs Send Email functionality. | Send Email |  |  | 2 - High | 1 - Critical | sxtsat | axsavi | 2015-05-28 | ACEView | End to End - Cycle 1 | Release 1_ASPAC |  | 0.79721 | ASPAC - SIT 2

## Defect Dashboard (hidden)
Apollo Refresh - Release 1 - Defect Summary - Build Plan Wise
Build Plan - Split Up
| A | Build 1A - Cycle 1 Execution
| B | Build 1A - Cycle 2 Execution
| C | Build 1B - Cycle 1 Execution
| D | Build 1B - Cycle 2 Execution
| E | Build 1C - Cycle 1 Execution
| F | Build 1C - Cycle 2 Execution
| G | E2E Testing - Cycle 1 Execution
| H | E2E Testing - Cycle 2 Execution
| I | Freeze Cycle Execution
| J | Automation Testing
| K | Performance Testing
Apollo Refresh - Release 1 - Defect Summary - Status Wise